## Sheet1
Doc No | Doc Name | Discipline | Doc Type | P.Start | A.Start | P.IDC | A.IDC | P.IFR | A.IFR | P.IFA | A.IFA | P.AFC | A.AFC
2021-4569-3H-0001 | Electrical Design Basis | EL | Narratives | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-07-19 | 2025-07-19 | 2026-01-27
2021-4569-3H-0002 | Electrical Design and Operating Philosophy | EL | Narratives | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-07-19 | 2025-07-19 | 2026-02-03
2021-4569-3H-0003 | Power System Operating Philosophy | EL | Narratives | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-07-26 | 2025-07-26 | 2026-02-10
2021-4569-3H-0004 | Black Start Procedure | EL | Narratives | 2026-01-01 |  | 2026-01-08 |  | 2026-01-13 |  | 2026-03-17 |  | 2026-06-30
2021-4569-3J-0001 | ST-Electrical Load List Calculation | EL | Calculation | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-10-28 |  | 2026-03-17
2021-4569-3J-0002 | Electrical Load Flow Study | EL | Calculation | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-11-25 |  | 2026-05-05
2021-4569-3J-0003 | Electrical Short Circuit Calculation | EL | Calculation | 2025-06-28 | 2025-06-28 | 2025-07-04 | 2025-07-04 | 2025-07-08 | 2025-07-08 | 2025-12-02 |  | 2026-05-12
2021-4569-3J-0004 | Motor Starting Calculation | EL | Calculation | 2025-06-28 | 2025-06-28 | 2025-07-04 | 2025-07-04 | 2025-07-08 | 2025-07-08 | 2025-12-09 |  | 2026-05-19
2021-4569-3J-0005 | Electrical Harmonic Study | EL | Calculation | 2025-06-28 | 2025-06-28 | 2025-07-09 | 2025-07-09 | 2025-07-14 | 2025-07-14 | 2025-12-16 |  | 2026-05-26
2021-4569-3J-0006 | UPS Sizing Calculation | EL | Calculation | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-07-19 | 2025-07-19 | 2026-06-19
2021-4569-3J-0007 | Lighting Calculation Design Report | EL | Calculation | 2025-11-06 |  | 2025-11-13 |  | 2025-11-18 |  | 2026-02-03 |  | 2026-04-21
2021-4569-3J-0008 | Electrical Equipment Heat Emissions Calculation (Building) | EL | Calculation | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-10-21 |  | 2026-04-07
2021-4569-3J-0009 | Cable Sizing Report | EL | Calculation | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-11-04 |  | 2026-04-21
2021-4569-3J-0010 | Main Equipment Sizing Calculation | EL | Calculation | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-11-11 |  | 2026-03-31
2021-4569-3J-0011 | Transient Stability Study | EL | Calculation | 2025-12-11 |  | 2025-12-18 |  | 2025-12-23 |  | 2026-06-02 |  | 2026-07-07
2021-4569-3J-0012 | Relay Coordination Study | EL | Calculation | 2026-06-04 |  | 2026-06-11 |  | 2026-06-16 |  | 2026-07-31 |  | 2026-09-14
2021-4569-3J-0013 | Arc Flash Calculation | EL | Calculation | 2025-12-18 |  | 2025-12-25 |  | 2025-12-30 |  | 2026-06-09 |  | 2026-07-14
2021-4569-3J-0014 | Neutral Earthing Resistor Sizing | EL | Calculation | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-08-23 | 2025-08-23 | 2026-04-28
2021-4569-3L-0001 | Electrical Requirement for Offshore Facilities Specification | EL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-07-19 | 2025-07-19 | 2026-03-03
2021-4569-3L-0002 | Electrical Requirements for Package Equipment Specification | EL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-07-19 | 2025-07-19 | 2026-03-10
2021-4569-3L-0003 | Navigational Aids Specification | EL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-07-21 | 2025-07-21 | 2026-05-19
2021-4569-3L-0004 | Induction Motors Specification (Medium Voltage & Low Voltage) | EL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-07-26 | 2025-07-26 | 2026-03-17
2021-4569-3L-0005 | Earthing and Bonding Specification | EL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-07-21 | 2025-07-21 | 2026-05-19
2021-4569-3L-0006 | Neutral Earthing Resistor Specification | EL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-07-21 | 2025-07-21 | 2026-05-26
2021-4569-3L-0007 | Electrical Cable Specification | EL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-07-16 | 2025-07-16 | 2026-05-26
2021-4569-3L-0008 | Electrical Equipment Tropic Proofing Specification | EL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-08-08 | 2025-08-08 | 2026-02-17
2021-4569-3L-0009 | Electrical Equipment Testing and Commissioning Specification | EL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-08-08 | 2025-08-08 | 2026-03-24
2021-4569-3L-0010 | E-House Building Specification | EL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-07-23 | 2025-07-23 | 2026-03-31
2021-4569-3L-0011 | Electrical Heater Specification | EL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-07-19 | 2025-07-19 | 2026-05-19
2021-4569-3L-0012 | Specification for Lighting Fixture, Socket Outlet, Junction Box, Cable Gland, Cable Tray and Electrical Bulk Material | EL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-12 | 2025-07-12 | 2025-09-04 | 2025-09-04 | 2026-05-26
2021-4569-3L-0013 | Variable Frequency Drive/ Softstarter Specification | EL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-08 | 2025-07-08 | 2025-08-26 | 2025-08-26 | 2026-04-14
2021-4570-3L-0001 | Synchronous Generator Specification | EL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-07-23 | 2025-07-23 | 2025-10-07 | 2025-10-02
2021-4570-3L-0002 | Power Management System Specification | EL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-07-23 | 2025-07-23 | 2025-10-14 | 2025-10-16
2021-4573-3L-0001 | LV Switchgear & MCC Specification | EL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-02 | 2025-07-02 | 2025-07-19 | 2025-07-19 | 2026-02-10
2021-4572-3L-0001 | MV Switchgear & MCC Specification | EL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-01 | 2025-07-01 | 2025-07-19 | 2025-07-19 | 2026-02-17
2021-4572-3L-0002 | Liquid Filled Power Transformer Specification | EL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-07-19 | 2025-07-19 | 2026-04-07
2021-4574-3L-0001 | Uninterruptible Power Supply (UPS) Specification | EL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-02 | 2025-07-02 | 2025-07-19 | 2025-07-19 | 2026-06-02
2021-4574-3L-0002 | DC Supply System Specification | EL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-02 | 2025-07-02 | 2025-07-19 | 2025-07-19 | 2026-06-02
2021-4575-3L-0001 | Small Power & Lighting Transformer Specification | EL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-02 | 2025-07-02 | 2025-07-26 | 2025-07-26 | 2026-04-14
2021-4577-3L-0001 | Heat Tracing System Specification | EL | Specification | 2025-07-07 | 2025-07-07 | 2025-07-08 | 2025-07-08 | 2025-07-19 | 2025-07-19 | 2025-08-29 | 2025-08-29 | 2026-07-14
2021-4569-3M-0001 | ST-CGF Datasheet for LV Induction Motors (Typical) | EL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-08 | 2025-07-26 | 2025-07-26 | 2025-12-16
2021-4569-3M-0002 | ST-CGF Datasheet for Navigational Aids System | EL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-08 | 2025-07-21 | 2025-07-21 | 2026-06-02
2021-4569-3M-0003 | ST-CGF Datasheet for Neutral Earthing Resistor & Control Panel | EL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-08 | 2025-07-21 | 2025-07-21 | 2026-06-02
2021-4569-3M-0004 | ST-CGF Datasheet for Local Control Station | EL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-23 | 2025-07-23 | 2025-08-21 | 2025-08-21 | 2026-06-02
2021-4569-3M-0005 | ST-CGF Datasheet for LV VFD | EL | Datasheet | 2025-07-05 | 2025-07-05 | 2025-06-30 | 2025-06-30 | 2025-07-23 | 2025-07-23 | 2025-08-21 | 2025-08-21 | 2026-04-21
2021-4569-3M-0006 | ST-CGF Datasheet for Lighting Fixture | EL | Datasheet | 2025-07-17 | 2025-07-17 | 2025-07-22 | 2025-07-22 | 2025-07-31 | 2025-07-31 | 2025-11-28 |  | 2026-07-21
2021-4569-3M-0007 | ST-CGF Datasheet for HP Flare Scrubber Heaters | EL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-08 | 2025-07-19 | 2025-07-19 | 2026-07-21
2021-4569-3M-0010 | ST-CGF Datasheet for Closed Drain Vessel Heater | EL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-08 | 2025-07-19 | 2025-07-19 | 2026-07-21
2021-4569-3M-0011 | ST-CGF Datasheet for Open Drain Tank Heater | EL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-08 | 2025-07-19 | 2025-07-19 | 2026-07-21
2021-4569-3M-0012 | ST-CGF Datasheet for Glycol Reboiler Heaters | EL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-08 | 2025-07-19 | 2025-07-19 | 2026-07-21
2021-4569-3M-0013 | ST-CGF Datasheet for Fuel Gas Super Heaters | EL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-08 | 2025-07-19 | 2025-07-19 | 2026-07-21
2021-4569-3M-0009 | ST-CGF Datasheet for MV/ LV Softstarter | EL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-08 | 2025-07-31 | 2025-07-31 | 2026-04-14
2021-4573-3M-0001 | ST-CGF Datasheet for LV Switchgear & MCC | EL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-02 | 2025-07-02 | 2025-08-08 | 2025-08-08 | 2026-04-21
2021-4570-3M-0001 | ST-CGF Synchronous Generator Datasheet (Alternator for GTG) | EL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-24 | 2025-07-01 | 2025-07-01 | 2025-07-23 | 2025-07-23 | 2026-01-13
2021-4570-3M-0002 | ST-CGF Synchronous Generator Datasheet (Alternator for EDG) | EL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-07-14 | 2025-07-14 | 2026-01-13
2021-4572-3M-0001 | ST-CGF Datasheet for MV Switchgear & MCC | EL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-02 | 2025-07-02 | 2025-08-14 | 2025-08-14 | 2026-04-28
2021-4572-3M-0002 | ST-CGF Datasheet for Liquid Filled Power Transformer | EL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-02 | 2025-07-02 | 2025-08-14 | 2025-08-14 | 2026-06-23
2021-4572-3M-0003 | ST-CGF Datasheet for MV Motor (Typical) | EL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-02 | 2025-07-02 | 2025-07-23 | 2025-07-23 | 2026-01-20
2021-4572-3M-0004 | ST-CGF Datasheet for MV Submersible Motor (Typical) | EL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-02 | 2025-07-02 | 2025-07-23 | 2025-07-23 | 2026-01-27
2021-4574-3M-0001 | ST-CGF Datasheet for UPS & UPS Distribution Board | EL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-02 | 2025-07-02 | 2025-07-23 | 2025-07-23 | 2026-07-28
2021-4575-3M-0001 | ST-CGF Small Power & Lighting Transformer Datasheet | EL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-02 | 2025-07-02 | 2025-08-21 | 2025-08-21 | 2026-06-23
2021-4575-3M-0002 | ST-CGF Datasheet for Distribution Boards | EL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-02 | 2025-07-02 | 2025-08-04 | 2025-08-04 | 2026-06-09
2021-4575-3M-0003 | ST-CGF Datasheet JB and JB Schedule | EL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-16 | 2025-07-16 | 2025-08-14 | 2025-08-14 | 2026-06-09
2021-4577-3M-0001 | ST-CGF Datasheet for Heat Tracing System & Heat Tracing Distribution Panel | EL | Datasheet | 2025-11-27 |  | 2025-12-04 |  | 2025-12-09 |  | 2026-01-13 |  | 2026-07-28
2021-4569-3U-0001 | Electrical Equipment List | EL | Register | 2026-03-05 |  | 2026-03-12 |  | 2026-03-17 |  | 2026-06-02 |  | 2026-07-07
2021-4569-3U-0002 | Explosion Proof Equipment List | EL | Register | 2026-03-12 |  | 2026-03-19 |  | 2026-03-24 |  | 2026-06-09 |  | 2026-07-17
2021-4569-35-0001 | ST-CGF Electrical Cable Schedule | EL | Drawing | 2025-08-28 | 2025-08-28 | 2025-09-16 | 2025-09-19 16:08 | 2025-09-19 | 2025-09-25 | 2025-12-23 |  | 2026-05-12
2021-4573-3V-0002 | Bid Evaluation Criteria for LV VFD & Softstarter | EL | Bid | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 |  |  | 2025-08-08 | 2025-08-08
2021-4574-3V-0001 | Bid Evaluation Criteria for UPS System & UPS Distribution Boards | EL | Bid | 2025-07-03 | 2025-07-03 | 2025-06-30 | 2025-06-30 | 2025-07-14 | 2025-07-14 |  |  | 2025-08-08 | 2025-08-08
2021-4572-3V-0002 | Bid Evaluation Criteria for Power Transformers | EL | Bid | 2025-06-28 | 2025-06-28 | 2025-07-10 | 2025-07-10 | 2025-07-16 | 2025-07-16 |  |  | 2025-09-26 | 2025-09-17
2021-4575-3V-0001 | Bid Evaluation Criteria for Distribution Boards | EL | Bid | 2025-07-17 | 2025-07-17 | 2025-07-09 | 2025-07-09 | 2025-07-26 | 2025-07-26 |  |  | 2025-08-25 | 2025-08-25
2021-4569-3V-0001 | Bid Evaluation Criteria For MV/LV Switchgear & MCC | EL | Bid | 2025-07-17 | 2025-07-17 | 2025-07-15 | 2025-07-15 | 2025-07-19 | 2025-07-19 |  |  | 2025-08-29 | 2025-08-29
2021-4577-3V-0001 | Bid Evaluation Criteria for Heat Tracing System | EL | Bid | 2025-07-03 | 2025-07-03 | 2025-07-16 | 2025-07-16 | 2025-07-16 | 2025-07-16 |  |  | 2025-08-14 | 2025-08-14
2021-4569-3V-0003 | Bid Evaluation Criteria For Neutral Grounding Resistor | EL | Bid | 2025-07-21 | 2025-07-21 | 2025-07-16 | 2025-07-16 | 2025-07-31 | 2025-07-31 |  |  | 2025-08-26 | 2025-08-26
2021-4575-3V-0002 | Bid Evaluation Criteria for Lighting Fixtures and Accessories | EL | Bid | 2025-06-28 | 2025-06-28 | 2025-07-28 | 2025-07-28 | 2025-07-23 | 2025-07-23 |  |  | 2025-09-26 | 2025-09-29
2021-4569-3V-0005 | Bid Evaluation Criteria for E&I Cables | EL | Bid | 2025-07-21 | 2025-07-21 | 2025-07-11 | 2025-07-11 | 2025-07-31 | 2025-07-31 |  |  | 2025-08-26 | 2025-08-26
2021-4569-3V-0006 | Bid Evaluation Criteria for E&I Cable Glands | EL | Bid | 2025-07-21 | 2025-07-21 | 2025-07-28 | 2025-07-28 | 2025-07-31 | 2025-07-31 |  |  | 2025-08-26 | 2025-08-26
2021-4569-3V-0007 | Bid Evaluation Criteria for E&I Cable Ladder Tray | EL | Bid | 2025-07-10 | 2025-07-10 | 2025-07-28 | 2025-07-28 | 2025-07-23 | 2025-07-23 |  |  | 2025-08-21 | 2025-08-21
2021-4575-3V-0003 | Bid Evaluation Criteria for E&I Junction Box, SO and LCS | EL | Bid | 2025-06-28 | 2025-06-28 | 2025-07-18 | 2025-07-18 | 2025-07-02 | 2025-07-02 |  |  | 2025-08-08 | 2025-08-08
2021-4569-3V-0009 | Bid Evaluation Criteria for E&I Earthing Material | EL | Bid | 2025-07-10 | 2025-07-10 | 2025-06-30 | 2025-06-30 | 2025-07-23 | 2025-07-23 |  |  | 2025-08-21 | 2025-08-21
2021-4569-3V-0010 | Bid Evaluation Criteria for E&I Steel Support | EL | Bid | 2025-07-17 | 2025-07-17 | 2025-07-18 | 2025-07-18 | 2025-08-04 | 2025-08-04 |  |  | 2025-08-28 | 2025-08-28
2021-4569-3V-0011 | Bid Evaluation Criteria for E&I Miscellaneous | EL | Bid | 2025-07-10 | 2025-07-10 | 2025-07-29 | 2025-07-29 | 2025-07-19 | 2025-07-19 |  |  | 2025-08-21 | 2025-08-21
2021-4569-3V-0012 | Bid Evaluation Criteria for E&I MCT | EL | Bid | 2025-07-17 | 2025-07-17 | 2025-07-16 | 2025-07-16 | 2025-08-04 | 2025-08-04 |  |  | 2025-09-06 | 2025-09-10
2021-4569-3V-0002 | Bid Evaluation Criteria for Navigational Aids System | EL | Bid | 2025-07-19 | 2025-07-19 | 2025-07-29 | 2025-07-29 | 2025-07-21 | 2025-07-21 |  |  | 2025-08-21 | 2025-08-21
2021-4570-3W-0001 | Technical Requisition for Gas Turbine Generator | EL | Procurement | 2025-06-28 | 2025-06-28 | 2025-07-16 | 2025-07-16 | 2025-07-01 | 2025-07-01 | 2025-07-19 | 2025-07-19 | 2025-11-15
2021-4572-3W-0001 | Technical Requisition for MV/LV Switchgear & MCC | EL | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-19 | 2025-07-19 | 2025-08-28 | 2025-08-28 | 2025-12-30
2021-4572-3W-0010 | Technical Requisition for Brown Field Modification of MV/LV Switchgear & MCC | EL | Procurement | 2025-09-26 | 2025-09-26 | 2025-10-03 | 2025-10-09 16:56 | 2025-10-08 | 2025-10-09 | 2025-10-22 |  | 2026-03-01
2021-4573-3W-0002 | Technical Requisition for LV VFD & Softstarter | EL | Procurement | 2025-08-20 | 2025-08-20 | 2025-08-21 | 2025-08-28 10:15 | 2025-08-28 | 2025-08-28 | 2025-09-22 | 2025-09-25 | 2026-01-15
2021-4574-3W-0001 | Technical Requisition for UPS System & UPS Distribution Boards | EL | Procurement | 2025-06-28 | 2025-06-28 | 2025-08-21 | 2025-08-21 | 2025-07-19 | 2025-07-19 | 2025-08-29 | 2025-08-29 | 2026-01-06
2021-4572-3W-0002 | Technical Requisition for Power Transformers | EL | Procurement | 2025-06-28 | 2025-06-28 | 2025-07-01 | 2025-07-01 | 2025-07-08 | 2025-07-08 | 2025-09-25 | 2025-09-17 | 2025-12-28
2021-4575-3W-0001 | Technical Requisition for Distribution Boards | EL | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-16 | 2025-07-16 | 2025-08-23 | 2025-08-23 | 2026-01-07
2021-4569-3W-0002 | Technical Requisition for Navigational Aids System | EL | Procurement | 2025-07-03 | 2025-07-03 | 2025-07-05 | 2025-07-05 | 2025-07-16 | 2025-07-16 | 2025-08-25 | 2025-08-25 | 2026-01-31
2021-4577-3W-0001 | Technical Requisition for Heat Tracing System | EL | Procurement | 2025-12-21 |  | 2025-12-28 |  | 2026-01-02 |  | 2026-02-15 |  | 2026-06-16
2021-4569-3W-0006 | Technical Requisition For Neutral Grounding Resistor | EL | Procurement | 2025-07-10 | 2025-07-10 | 2025-07-09 | 2025-07-09 | 2025-07-16 | 2025-07-16 | 2025-08-25 | 2025-08-25 | 2025-12-17
2021-4575-3W-0002 | Technical Requisition for Lighting Fixtures and Accessories | EL | Procurement | 2025-11-06 | 2025-10-10 11:18 | 2025-11-13 | 2025-10-10 11:18 | 2025-11-18 | 2025-10-10 | 2025-11-30 |  | 2026-03-22
2021-4569-3W-0001 | Technical Requisition for E&I Cables | EL | Procurement | 2025-09-30 | 2025-09-30 | 2025-10-07 | 2025-10-03 09:19 | 2025-10-12 | 2025-10-10 | 2025-10-26 |  | 2026-02-10
2021-4569-3W-0003 | Technical Requisition for E&I Cable Glands | EL | Procurement | 2025-10-27 |  | 2025-11-03 |  | 2025-11-08 |  | 2025-11-22 |  | 2026-03-09
2021-4569-3W-0004 | Technical Requisition for E&I Cable Ladder Tray | EL | Procurement | 2025-10-26 |  | 2025-11-02 |  | 2025-11-07 |  | 2025-11-21 |  | 2026-03-08
2021-4575-3W-0003 | Technical Requisition for Electrical Junction Box, SO and LCS | EL | Procurement | 2025-11-07 |  | 2025-11-14 |  | 2025-11-19 |  | 2025-12-03 |  | 2026-03-20
2021-4569-3W-0005 | Technical Requisition for E&I Earthing Material | EL | Procurement | 2025-09-25 | 2025-09-25 | 2025-10-02 | 2025-10-02 07:38 | 2025-10-07 | 2025-10-06 | 2025-10-21 |  | 2026-02-05
2021-4569-3W-0007 | Technical Requisition for E&I Steel Support | EL | Procurement | 2025-07-28 | 2025-07-28 | 2025-08-07 | 2025-08-07 | 2025-08-14 | 2025-08-14 | 2025-09-19 | 2025-09-17 | 2025-12-08
2021-4569-3W-0008 | Technical Requisition for E&I Miscellaneous | EL | Procurement | 2025-08-31 | 2025-08-31 | 2025-09-07 | 2025-09-10 10:34 | 2025-09-12 | 2025-09-10 | 2025-09-26 | 2025-09-26 | 2026-01-11
2021-4569-3W-0009 | Technical Requisition for E&I MCT | EL | Procurement | 2025-09-30 | 2025-09-30 | 2025-10-07 | 2025-10-03 15:08 | 2025-10-12 | 2025-10-11 | 2025-10-26 |  | 2026-02-10
2021-4570-3W-0101 | Technical Bid Evaluation for Gas Turbine Generator | EL | Procurement | 2025-10-23 |  | 2025-10-28 |  | 2025-10-30 |  |  |  | 2025-11-13
2021-4572-3W-0101 | Technical Bid Evaluation for MV/LV Switchgear & MCC | EL | Procurement | 2025-12-02 |  | 2025-12-09 |  | 2025-12-14 |  |  |  | 2025-12-28
2021-4572-3W-0110 | Technical Bid Evaluation for Brown Field Modification of MV/LV Switchgear & MCC | EL | Procurement | 2026-01-09 |  | 2026-01-16 |  | 2026-01-21 |  |  |  | 2026-01-28
2021-4573-3W-0102 | Technical Bid Evaluation for LV VFD & Softstarter | EL | Procurement | 2025-12-03 |  | 2025-12-10 |  | 2025-12-15 |  |  |  | 2025-12-31
2021-4574-3W-0101 | Technical Bid Evaluation for UPS System & UPS Distribution Boards | EL | Procurement | 2025-12-01 |  | 2025-12-08 |  | 2025-12-13 |  |  |  | 2025-12-14
2021-4572-3W-0102 | Technical Bid Evaluation for Power Transformers | EL | Procurement | 2025-12-01 |  | 2025-12-08 |  | 2025-12-13 |  |  |  | 2025-12-05
2021-4575-3W-0101 | Technical Bid Evaluation for Distribution Boards | EL | Procurement | 2025-11-17 |  | 2025-11-24 |  | 2025-11-29 |  |  |  | 2025-12-06
2021-4569-3W-0102 | Technical Bid Evaluation for Navigational Aids System | EL | Procurement | 2025-12-11 |  | 2025-12-18 |  | 2025-12-23 |  |  |  | 2025-12-30
2021-4577-3W-0101 | Technical Bid Evaluation for Heat Tracing System | EL | Procurement | 2026-04-26 |  | 2026-05-03 |  | 2026-05-08 |  |  |  | 2026-05-15
2021-4569-3W-0106 | Technical Bid Evaluation For Neutral Grounding Resistor | EL | Procurement | 2025-11-18 |  | 2025-11-25 |  | 2025-11-30 |  |  |  | 2026-05-15
2021-4575-3W-0102 | Technical Bid Evaluation for Lighting Fixtures and Accessories | EL | Procurement | 2026-01-30 |  | 2026-02-06 |  | 2026-02-11 |  |  |  | 2026-02-18
2021-4569-3W-0101 | Technical Bid Evaluation for Electrical Cables | EL | Procurement | 2025-12-21 |  | 2025-12-28 |  | 2026-01-02 |  |  |  | 2026-02-18
2021-4569-3W-0103 | Technical Bid Evaluation for E&I Cable Glands | EL | Procurement | 2026-01-17 |  | 2026-01-24 |  | 2026-01-29 |  |  |  | 2026-02-05
2021-4569-3W-0104 | Technical Bid Evaluation for E&I Cable Ladder Tray | EL | Procurement | 2026-01-16 |  | 2026-01-23 |  | 2026-01-28 |  |  |  | 2026-02-05
2021-4575-3W-0103 | Technical Bid Evaluation for Electrical Junction Box, SO and LCS | EL | Procurement | 2026-01-28 |  | 2026-02-04 |  | 2026-02-09 |  |  |  | 2026-02-16
2021-4569-3W-0105 | Technical Bid Evaluation for E&I Earthing Material | EL | Procurement | 2025-12-16 |  | 2025-12-23 |  | 2025-12-28 |  |  |  | 2026-02-16
2021-4569-3W-0107 | Technical Bid Evaluation for E&I Steel Support | EL | Procurement | 2025-11-11 |  | 2025-11-18 |  | 2025-11-23 |  |  |  | 2025-12-07
2021-4569-3W-0108 | Technical Bid Evaluation for E&I Miscellaneous | EL | Procurement | 2025-11-28 |  | 2025-12-05 |  | 2025-12-10 |  |  |  | 2025-12-24
2021-4569-3W-0109 | Technical Bid Evaluation for E&I MCT | EL | Procurement | 2025-12-21 |  | 2025-12-26 |  | 2025-12-31 |  |  |  | 2026-01-14
2021-4569-30-0001 | Electrical Drawing Index | EL | Drawing | 2025-07-10 | 2025-07-10 | 2025-07-16 | 2025-07-23 17:28 | 2025-07-23 | 2025-07-23 | 2025-09-30 | 2025-10-06 | 2026-01-06
2021-4569-30-0002 | Electrical Document Index | EL | Drawing | 2025-07-17 | 2025-07-17 | 2025-07-18 | 2025-07-18 | 2025-08-08 | 2025-08-08 | 2025-10-07 | 2025-10-13 | 2026-01-13
2021-4569-30-0003 | Electrical Legends & Symbols | EL | Drawing | 2025-07-24 | 2025-07-24 | 2025-08-04 | 2025-08-04 | 2025-08-08 | 2025-08-08 | 2025-10-14 | 2025-10-14 | 2026-01-20
2021-4569-32-0001 | Typical Control Schematic Diagram - LV Motor Type A | EL | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-04 | 2025-08-04 | 2025-07-01 | 2025-07-01 | 2025-10-14 | 2025-10-16 | 2026-01-20
2021-4569-32-0002 | Typical Control Schematic Diagram - LV Motor With LCP - Type B | EL | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-01 | 2025-07-01 | 2025-10-14 | 2025-10-16 | 2026-01-20
2021-4569-32-0003 | Typical Control Schematic Diagram - MV Motor Type A | EL | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-01 | 2025-07-01 | 2025-10-21 |  | 2026-01-27
2021-4569-32-0004 | Typical Control Schematic Diagram - MV Motor With Soft Starter - Type B | EL | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-01 | 2025-07-01 | 2025-10-21 |  | 2026-01-27
2021-4569-32-0005 | Typical Control Schematic Diagram - Full Voltage Contactor Feeder Type C1 | EL | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-01 | 2025-07-01 | 2025-10-21 |  | 2026-01-27
2021-4569-32-0006 | Typical Control Schematic Diagram - Full Voltage Feeder Type C2 | EL | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-01 | 2025-07-01 | 2025-10-21 |  | 2026-01-27
2021-4569-32-0007 | Typical Control Schematic Diagram - Full Voltage Thyristor Control Type D | EL | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-01 | 2025-07-01 | 2025-10-28 |  | 2026-02-03
2021-4569-32-0008 | Typical Control Schematic Diagram - Lighting System | EL | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-01 | 2025-07-01 | 2025-08-26 | 2025-08-26 | 2026-03-10
2021-4570-32-0001 | ST-CGF Control Schematic Diagram - Gas Turbine Generator Package | EL | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-10-28 |  | 2026-02-03
2021-4571-32-0001 | ST-CGF Control Schematic Diagram - Emergency Diesel Generator | EL | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-01 | 2025-07-01 | 2025-10-28 |  | 2026-02-03
2021-4569-32-0015 | ST-CGF Overall Electrical One Line Diagram | EL | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-01 | 2025-07-01 | 2025-11-04 |  | 2026-03-24
2021-4569-32-0016 | ST-CGF One Line Diagram - Earthing System | EL | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-01 | 2025-07-01 | 2025-08-11 | 2025-08-11 | 2026-03-17
2021-4572-32-0001 | ST-CGF One Line Diagram - 4160V MV Switchgear/ MCC | EL | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-02 | 2025-07-02 | 2025-11-11 |  | 2026-03-31
2021-4573-32-0001 | ST-CGF One Line Diagram - 480V LV Switchgear/ MCC | EL | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-19 | 2025-07-19 | 2025-11-18 |  | 2026-04-07
2021-4574-32-0001 | ST-CGF One Line Diagram - UPS Electrical | EL | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-07-02 | 2025-07-02 | 2025-08-08 | 2025-08-08 | 2026-06-26
2021-4574-32-0002 | ST-CGF One Line Diagram - UPS Distribution Board for Electrical | EL | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-02 | 2025-07-02 | 2025-08-08 | 2025-08-08 | 2026-07-03
2021-4574-32-0003 | ST-CGF One Line Diagram - UPS Distribution Boards for Instrument & Telecom | EL | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-02 | 2025-07-02 | 2025-08-08 | 2025-08-08 | 2026-07-10
2021-4574-32-0004 | ST-CGF One Line Diagram - 24V DC Navigational Aids | EL | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-04 | 2025-07-08 | 2025-08-14 | 2025-08-14 | 2026-03-24
2021-4574-32-0005 | ST-CGF One Line Diagram - PAGA Battery Charger | EL | Drawing | 2025-08-07 | 2025-08-07 | 2025-06-29 | 2025-06-29 | 2025-08-21 | 2025-08-21 | 2025-10-28 |  | 2026-01-20
2021-4575-32-0001 | ST-CGF One Line Diagram - Lighting & Small Power 230VAC Distribution Board | EL | Drawing | 2025-07-12 | 2025-07-12 | 2025-08-14 | 2025-08-14 | 2025-07-19 | 2025-07-19 | 2025-11-25 |  | 2026-03-31
2021-4577-32-0001 | ST-CGF One Line Diagram - Electrical Heat Tracing | EL | Drawing | 2026-01-03 |  | 2026-01-10 |  | 2026-01-15 |  | 2026-04-07 |  | 2026-08-11
2021-4570-34-0002 | ST-CGF Power Management System Block Diagram | EL | Drawing | 2025-11-20 |  | 2025-11-27 |  | 2025-12-02 |  | 2026-01-27 |  | 2026-04-07
2021-4570-34-0001 | ST-CGF Electrical Block Diagram - Gas Turbine Generators | EL | Drawing | 2025-11-27 |  | 2025-12-04 |  | 2025-12-09 |  | 2026-02-03 |  | 2026-04-14
2021-4571-34-0001 | ST-CGF Electrical Block Diagram - Emergency Diesel Generator | EL | Drawing | 2026-04-02 |  | 2026-04-09 |  | 2026-04-14 |  | 2026-05-26 |  | 2026-06-30
2021-4574-34-0001 | ST-CGF Electrical Block Diagram - UPS System | EL | Drawing | 2026-04-02 |  | 2026-04-09 |  | 2026-04-14 |  | 2026-08-18 |  | 2026-09-27
2021-4574-34-0002 | ST-CGF Electrical Block Diagram - 24VDC Navigational Aids | EL | Drawing | 2026-03-12 |  | 2026-03-19 |  | 2026-03-24 |  | 2026-05-05 |  | 2026-07-28
2021-4575-34-0001 | ST-CGF Electrical Block Diagram - Lighting & Small Power Distribution Boards | EL | Drawing | 2025-11-20 |  | 2025-11-27 |  | 2025-12-02 |  | 2026-04-08 |  | 2026-07-21
2021-4569-34-0001 | ST-CGF Electrical Block Diagram Gas Turbine Compressors | EL | Drawing | 2025-12-04 |  | 2025-12-11 |  | 2025-12-16 |  | 2026-02-10 |  | 2026-04-21
2021-4569-34-0003 | ST-CGF Electrical Block Diagram Cooling Water Circulation Pumps | EL | Drawing | 2025-12-18 |  | 2025-12-25 |  | 2025-12-30 |  | 2026-03-03 |  | 2026-05-05
2021-4569-34-0004 | ST-CGF Electrical Block Diagram Seawater Lift Pumps | EL | Drawing | 2025-12-25 |  | 2026-01-01 |  | 2026-01-06 |  | 2026-03-03 |  | 2026-05-12
2021-4569-34-0005 | ST-CGF Electrical Block Diagram Instrument Air Compressor | EL | Drawing | 2026-04-09 |  | 2026-04-16 |  | 2026-04-21 |  | 2026-06-02 |  | 2026-07-07
2021-4569-34-0006 | ST-CGF Electrical Block Diagram - Pedestal Crane | EL | Drawing | 2026-04-09 |  | 2026-04-16 |  | 2026-04-21 |  | 2026-08-25 |  | 2026-10-04
2021-4569-34-0007 | ST-CGF Electrical Block Diagram - HVAC System | EL | Drawing | 2026-04-16 |  | 2026-04-23 |  | 2026-04-28 |  | 2026-06-09 |  | 2026-07-14
2021-4577-34-0001 | ST-CGF Electrical Block Diagram - Electrical Heat Tracing | EL | Drawing | 2026-08-20 |  | 2026-08-27 |  | 2026-09-01 |  | 2026-09-22 |  | 2026-10-13
2021-4570-34-0003 | ST-CGF Electrical Interconnection Wiring Diagram - Gas Turbine Generators | EL | Drawing | 2026-07-02 |  | 2026-07-09 |  | 2026-07-14 |  | 2026-09-08 |  | 2026-10-20
2021-4571-34-0002 | ST-CGF Electrical Interconnection Wiring Diagram - Emergency Diesel Generator | EL | Drawing | 2026-07-16 |  | 2026-07-23 |  | 2026-07-28 |  | 2026-09-01 |  | 2026-10-20
2021-4572-34-0001 | ST-CGF Electrical Interconnection Wiring Diagram - MV Switchgear/MCC | EL | Drawing | 2026-07-16 |  | 2026-07-23 |  | 2026-07-28 |  | 2026-09-01 |  | 2026-10-13
2021-4573-34-0001 | ST-CGF Electrical Interconnection Wiring Diagram - LV Switchgear/MCC | EL | Drawing | 2026-07-23 |  | 2026-07-30 |  | 2026-08-04 |  | 2026-09-08 |  | 2026-10-20
2021-4569-34-00021 | ST-CGF Electrical Interconnection Wiring Diagram - PMS system | EL | Drawing | 2026-07-09 |  | 2026-07-16 |  | 2026-07-21 |  | 2026-09-15 |  | 2026-10-27
2021-4574-34-0003 | ST-CGF Electrical Interconnection Wiring Diagram - UPS System | EL | Drawing | 2026-08-27 |  | 2026-09-03 |  | 2026-09-08 |  | 2026-10-13 |  | 2026-11-10
2021-4574-34-0004 | ST-CGF Electrical Interconnection Wiring Diagram - 24VDC Navigational Aids | EL | Drawing | 2026-07-23 |  | 2026-07-30 |  | 2026-08-04 |  | 2026-09-08 |  | 2026-10-20
2021-4577-34-0002 | ST-CGF Electrical Interconnection Wiring Diagram - Electrical Heat Tracing | EL | Drawing | 2026-09-15 |  | 2026-09-22 |  | 2026-09-27 |  | 2026-11-03 |  | 2026-12-01
2021-4575-34-0002 | ST-CGF Electrical Interconnection Wiring Diagram - Lighting and Small Power Distribution Boards | EL | Drawing | 2026-07-30 |  | 2026-08-06 |  | 2026-08-11 |  | 2026-09-15 |  | 2026-10-27
2021-4574-34-0005 | ST-CGF Electrical Interconnection Wiring Diagram - UPS Distribution Board | EL | Drawing | 2026-09-03 |  | 2026-09-10 |  | 2026-09-15 |  | 2026-10-20 |  | 2026-11-17
2021-4569-34-0014 | ST-CGF Electrical Interconnection Wiring Diagram - HVAC System | EL | Drawing | 2026-07-30 |  | 2026-08-06 |  | 2026-08-11 |  | 2026-09-08 |  | 2026-10-27
2021-4569-34-0016 | ST-CGF Electrical Interconnection Wiring Diagram - Gas Turbine Compressors | EL | Drawing | 2026-07-16 |  | 2026-07-23 |  | 2026-07-28 |  | 2026-09-22 |  | 2026-11-03
2021-4569-34-0018 | ST-CGF Electrical Interconnection Wiring Diagram - Sea Water Lift Pump | EL | Drawing | 2026-07-23 |  | 2026-07-30 |  | 2026-08-04 |  | 2026-09-29 |  | 2026-11-10
2021-4569-34-0019 | ST-CGF Electrical Interconnection Wiring Diagram - Instrument Air Compressor | EL | Drawing | 2026-08-06 |  | 2026-08-13 |  | 2026-08-18 |  | 2026-09-15 |  | 2026-11-03
2021-4569-34-0020 | ST-CGF Electrical Interconnection Wiring Diagram - Electrical Heaters | EL | Drawing | 2026-09-10 |  | 2026-09-17 |  | 2026-09-22 |  | 2026-10-27 |  | 2026-11-24
2021-4569-34-0008 | Typical Installation Details Cable Tray & Ladder | EL | Drawing | 2025-07-12 | 2025-07-12 | 2025-07-07 | 2025-07-14 11:40 | 2025-07-14 | 2025-07-14 | 2025-10-28 |  | 2026-05-05
2021-4569-34-0009 | Typical Earthing Installation Details | EL | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-09 | 2025-07-09 | 2025-07-19 | 2025-07-19 | 2025-11-04 |  | 2026-05-12
2021-4569-34-0010 | Typical Lighting Installation Details | EL | Drawing | 2025-07-03 | 2025-07-03 | 2025-07-18 | 2025-07-18 | 2025-07-26 | 2025-07-26 | 2025-11-11 |  | 2026-05-19
2021-4569-34-0011 | Typical Power & Control Installation Detail | EL | Drawing | 2025-07-12 | 2025-07-12 | 2025-07-18 | 2025-07-18 | 2025-07-14 | 2025-07-14 | 2025-12-02 |  | 2026-05-12
2021-4569-34-0012 | Typical Navigational Aids Installation Details | EL | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-07-19 | 2025-07-19 | 2025-12-09 |  | 2026-05-19
2021-4569-34-0013 | Typical Junction Box Installation Details | EL | Drawing | 2025-07-03 | 2025-07-03 | 2025-07-18 | 2025-07-18 | 2025-07-26 | 2025-07-26 | 2025-12-16 |  | 2026-05-26
2021-4569-36-0001 | ST-CGF E-House Buildings – Electrical Equipment Layout | EL | Drawing | 2025-07-03 | 2025-07-03 | 2025-07-23 | 2025-07-23 | 2025-07-26 | 2025-07-26 | 2026-01-10 |  | 2026-05-26
2021-4569-36-0002 | ST-CGF E-House Buildings - Lighting & Small Power Layout | EL | Drawing | 2025-11-06 | 2025-10-03 15:08 | 2025-11-13 | 2025-10-03 15:08 | 2025-11-18 |  | 2026-02-03 |  | 2026-06-02
2021-4569-36-0003 | ST-CGF E-House Buildings - Cable Tray / Ladder Layout | EL | Drawing | 2025-09-11 | 2025-09-11 | 2025-09-18 | 2025-09-19 07:30 | 2025-09-23 | 2025-09-25 | 2026-03-10 |  | 2026-06-23
2021-4569-36-0031 | ST-CGF E-House Buildings - Cable Routing Layout | EL | Drawing | 2026-04-30 |  | 2026-05-07 |  | 2026-05-12 |  | 2026-07-28 |  | 2026-09-08
2021-4569-36-0004 | ST-CGF E-House Buildings - Earthing & Bonding Layout | EL | Drawing | 2025-09-18 | 2025-09-18 | 2025-09-25 | 2025-10-01 15:06 | 2025-09-30 | 2025-10-01 | 2026-01-17 |  | 2026-06-02
2021-4569-36-0005 | ST-CGF E-House Buildings - Multi Cable Transit (MCT) Layout | EL | Drawing | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-03 14:26 | 2025-10-07 | 2025-10-09 | 2026-01-27 |  | 2026-06-02
2021-4569-36-0030 | ST-CGF E-House Buildings - Multi Cable Transit (MCT) Detail | EL | Drawing | 2025-12-04 | 2025-10-10 10:20 | 2025-12-11 | 2025-10-10 10:20 | 2025-12-16 |  | 2026-05-26 |  | 2026-10-20
2021-4569-36-0006 | ST-CGF Lighting & Small Power Layout Main Deck | EL | Drawing | 2025-11-13 |  | 2025-11-20 |  | 2025-11-25 |  | 2026-02-10 |  | 2026-06-09
2021-4569-36-0007 | ST-CGF Lighting & Small Power Layout Intermediate Deck | EL | Drawing | 2025-11-20 |  | 2025-11-27 |  | 2025-12-02 |  | 2026-02-17 |  | 2026-06-16
2021-4569-36-0008 | ST-CGF Lighting & Small Power Layout Cellar Deck | EL | Drawing | 2025-11-27 |  | 2025-12-04 |  | 2025-12-09 |  | 2026-03-03 |  | 2026-06-23
2021-4569-36-0009 | ST-CGF Lighting & Small Power Layout Sub-Cellar Deck (Closed Drain Deck) | EL | Drawing | 2025-12-04 |  | 2025-12-11 |  | 2025-12-16 |  | 2026-03-10 |  | 2026-06-30
2021-4569-36-0010 | ST-CGF Lighting & Small Power Layout Top of Jacket | EL | Drawing | 2025-12-11 |  | 2025-12-18 |  | 2025-12-23 |  | 2026-03-10 |  | 2026-07-07
2021-4569-36-0011 | ST-CGF Cable Ladder / Tray Layout Main Deck | EL | Drawing | 2025-10-02 | 2025-10-02 | 2025-10-09 | 2025-10-03 15:13 | 2025-10-14 | 2025-10-10 | 2026-03-17 |  | 2026-06-30
2021-4569-36-0012 | ST-CGF Cable Ladder / Tray Layout Intermediate Deck | EL | Drawing | 2025-10-09 | 2025-10-09 | 2025-10-16 | 2025-10-03 15:17 | 2025-10-21 | 2025-10-10 | 2026-03-24 |  | 2026-07-07
2021-4569-36-0013 | ST-CGF Cable Ladder / Tray Layout Cellar Deck | EL | Drawing | 2025-10-16 | 2025-10-16 | 2025-10-23 | 2025-10-08 14:08 | 2025-10-28 |  | 2026-03-31 |  | 2026-07-14
2021-4569-36-0014 | ST-CGF Cable Ladder / Tray Layout Sub-Cellar Deck (Closed Drain Deck) | EL | Drawing | 2025-10-23 | 2025-10-08 14:08 | 2025-10-30 | 2025-10-08 14:08 | 2025-11-04 |  | 2026-04-07 |  | 2026-07-21
2021-4569-36-0015 | ST-CGF Cable Routing Layout Main Deck | EL | Drawing | 2026-05-07 |  | 2026-05-14 |  | 2026-05-19 |  | 2026-08-04 |  | 2026-09-15
2021-4569-36-0016 | ST-CGF Cable Routing Layout Intermediate Deck | EL | Drawing | 2026-05-14 |  | 2026-05-21 |  | 2026-05-26 |  | 2026-08-11 |  | 2026-09-22
2021-4569-36-0017 | ST-CGF Cable Routing Layout Cellar Deck | EL | Drawing | 2026-05-21 |  | 2026-05-28 |  | 2026-06-02 |  | 2026-08-18 |  | 2026-09-29
2021-4569-36-0018 | ST-CGF Cable Routing Layout Sub-Cellar Deck (Closed Drain Desk) | EL | Drawing | 2026-05-28 |  | 2026-06-04 |  | 2026-06-09 |  | 2026-08-25 |  | 2026-10-06
2021-4569-36-0020 | ST-CGF Earthing & Bonding Layout Main Deck | EL | Drawing | 2025-09-25 | 2025-09-25 | 2025-10-02 | 2025-10-09 16:56 | 2025-10-07 | 2025-10-09 | 2026-01-24 |  | 2026-06-09
2021-4569-36-0021 | ST-CGF Earthing & Bonding Layout Intermediate Deck | EL | Drawing | 2025-10-02 | 2025-10-02 | 2025-10-09 | 2025-10-10 20:40 | 2025-10-14 | 2025-10-10 | 2026-01-31 |  | 2026-06-16
2021-4569-36-0022 | ST-CGF Earthing & Bonding Layout Cellar Deck | EL | Drawing | 2025-10-09 | 2025-10-09 | 2025-10-16 |  | 2025-10-21 |  | 2026-02-07 |  | 2026-06-23
2021-4569-36-0023 | ST-CGF Earthing & Bonding Layout Sub-Cellar Deck (Closed Drain Deck) | EL | Drawing | 2025-10-16 | 2025-10-16 | 2025-10-23 |  | 2025-10-28 |  | 2026-02-14 |  | 2026-06-30
2021-4569-36-0024 | ST-CGF Earthing & Bonding Layout Top of Jacket | EL | Drawing | 2025-10-23 |  | 2025-10-30 |  | 2025-11-04 |  | 2026-02-14 |  | 2026-07-07
2021-4569-36-0027 | CGF-PIP Bridge Cable Routing Layout | EL | Drawing | 2026-06-04 |  | 2026-06-11 |  | 2026-06-16 |  | 2026-09-01 |  | 2026-10-13
2021-4569-36-0028 | ST-CGF Navigational Aids Layout Drawing | EL | Drawing | 2025-09-11 | 2025-09-11 | 2025-09-22 | 2025-09-17 16:57 | 2025-09-29 | 2025-09-17 | 2026-01-20 |  | 2026-07-28
2021-4569-38-0001 | ST-CGF Bulk MTO for Electrical Cables | EL | Drawing | 2025-10-14 | 2025-10-14 | 2025-10-21 |  | 2025-10-26 |  | 2026-01-16 |  | 2026-07-21
2021-4569-38-0002 | ST-CGF Bulk MTO for Lighting Fixtures | EL | Drawing | 2025-11-18 |  | 2025-11-25 |  | 2025-11-30 |  | 2026-02-25 |  | 2026-07-21
2021-4569-38-0003 | ST-CGF Bulk MTO for Electrical Tray, Ladder & Accessories | EL | Drawing | 2025-11-09 |  | 2025-11-16 |  | 2025-11-21 |  | 2026-02-11 |  | 2026-06-16
2021-4569-38-0004 | ST-CGF Bulk MTO for Electrical Earthing Material | EL | Drawing | 2025-10-23 |  | 2025-10-30 |  | 2025-11-04 |  | 2026-01-11 |  | 2026-06-23
2021-4569-38-0005 | ST-CGF Bulk MTO for Electrical Cable Glands | EL | Drawing | 2025-11-10 |  | 2025-11-17 |  | 2025-11-22 |  | 2026-02-12 |  | 2026-07-21
2021-4569-38-0006 | ST-CGF Bulk MTO for Electrical Receptacles, Plugs | EL | Drawing | 2025-11-21 |  | 2025-11-28 |  | 2025-12-03 |  | 2026-03-03 |  | 2026-07-21
2021-4569-38-0007 | ST-CGF Bulk MTO for Electrical Junction Boxes | EL | Drawing | 2025-11-21 |  | 2025-11-28 |  | 2025-12-03 |  | 2026-03-03 |  | 2026-07-21
2021-4569-38-0008 | ST-CGF Bulk MTO for Electrical Local Control Stations | EL | Drawing | 2025-11-21 |  | 2025-11-28 |  | 2025-12-03 |  | 2026-03-03 |  | 2026-07-21
2021-4569-38-0009 | ST-CGF Bulk MTO for Electrical Steel Supports | EL | Drawing | 2025-08-11 | 2025-08-11 | 2025-08-18 | 2025-08-25 10:15 | 2025-08-25 | 2025-08-25 | 2025-11-13 |  | 2026-05-05
2021-4569-38-0010 | ST-CGF Bulk MTO for Electrical MCT | EL | Drawing | 2025-10-14 | 2025-10-14 | 2025-10-21 |  | 2025-10-26 |  | 2026-01-16 |  | 2026-06-16
2021-4569-38-0011 | ST-CGF Bulk MTO for Electrical Miscellaneous | EL | Drawing | 2025-09-14 | 2025-09-14 | 2025-09-21 | 2025-09-25 10:09 | 2025-09-26 | 2025-09-25 | 2025-12-17 |  | 2026-06-23
2021-4570-3V-0001 | Bid Evaluation Criteria for Gas Turbine Generator | EL | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-01 | 2025-07-01 |  |  | 2025-07-19 | 2025-07-19
2021-4575-3W-0201 | Technical Requisition for Distribution Boards & Small Power Transformer (LQ2 Module) | EL | Procurement | 2025-08-29 | 2025-08-29 | 2025-09-05 | 2025-09-08 14:56 | 2025-09-22 | 2025-09-25 | 2025-10-22 | 2025-10-09 | 2026-02-02
2021-4575-3W-0202 | Technical Requisition for Lighting Fixtures (Brown Field) | EL | Procurement | 2025-10-17 | 2025-10-17 | 2025-10-22 | 2025-10-02 09:39 | 2025-10-27 | 2025-10-06 | 2025-11-10 |  | 2026-03-23
2021-4569-3W-0201 | Technical Requisition for E&I Cables (Brown Field) | EL | Procurement | 2025-10-22 |  | 2025-10-27 |  | 2025-11-01 |  | 2025-11-15 |  | 2026-03-23
2021-4569-3W-0203 | Technical Requisition for E&I Cable Glands (Brown Field) | EL | Procurement | 2025-11-12 |  | 2025-11-17 |  | 2025-11-22 |  | 2025-12-06 |  | 2026-04-13
2021-4569-3W-0204 | Technical Requisition for E&I Cable Tray, Ladder & Accessories (Brown Field) | EL | Procurement | 2025-10-04 | 2025-10-04 | 2025-10-11 |  | 2025-10-16 |  | 2025-10-30 |  | 2026-03-07
2021-4575-3W-0203 | Technical Requisition for E&I JB, Socket Outlet & RCU (Brown Field) | EL | Procurement | 2025-10-22 |  | 2025-10-27 |  | 2025-11-01 |  | 2025-11-15 |  | 2026-03-23
2021-4569-3W-0205 | Technical Requisition for E&I Earthing Material (Brown Field) | EL | Procurement | 2025-07-27 | 2025-07-27 | 2025-08-04 | 2025-08-11 17:32 | 2025-08-11 | 2025-08-11 | 2025-09-30 | 2025-09-25 | 2025-12-26
2021-4569-3W-0207 | Technical Requisition for E&I Steel Support (Brown Field) | EL | Procurement | 2025-08-18 | 2025-08-18 | 2025-09-18 | 2025-09-19 15:49 | 2025-09-23 | 2025-09-25 | 2025-10-07 | 2025-10-10 | 2026-01-26
2021-4569-3W-0208 | Technical Requisition for E&I Miscellaneous (Brown Field) | EL | Procurement | 2025-10-22 |  | 2025-10-27 |  | 2025-11-01 |  | 2025-11-15 |  | 2026-03-23
2021-4575-3W-0301 | Technical Bid Evaluation for Distribution Boards & Small Power Transformer (LQ2 Module) | EL | Procurement | 2025-12-15 |  | 2025-12-22 |  | 2025-12-27 |  |  |  | 2026-01-03
2021-4575-3W-0302 | Technical Bid Evaluation for Lighting Fixtures (Brown Field) | EL | Procurement | 2026-01-11 |  | 2026-01-18 |  | 2026-01-23 |  |  |  | 2026-02-02
2021-4569-3W-0301 | Technical Bid Evaluation for E&I Cables (Brown Field) | EL | Procurement | 2026-01-11 |  | 2026-01-18 |  | 2026-01-23 |  |  |  | 2026-02-02
2021-4569-3W-0303 | Technical Bid Evaluation for E&I Cable Glands (Brown Field) | EL | Procurement | 2026-02-23 |  | 2026-03-02 |  | 2026-03-07 |  |  |  | 2026-03-14
2021-4569-3W-0304 | Technical Bid Evaluation for E&I Cable Tray, Ladder & Accessories (Brown Field) | EL | Procurement | 2026-01-17 |  | 2026-01-24 |  | 2026-01-29 |  |  |  | 2026-02-05
2021-4575-3W-0303 | Technical Bid Evaluation for E&I JB, Socket Outlet & RCU (Brown Field) | EL | Procurement | 2026-02-02 |  | 2026-02-09 |  | 2026-02-14 |  |  |  | 2026-02-21
2021-4569-3W-0305 | Technical Bid Evaluation for E&I Earthing Material (Brown Field) | EL | Procurement | 2025-11-30 |  | 2025-12-07 |  | 2025-12-12 |  |  |  | 2025-12-19
2021-4569-3W-0307 | Technical Bid Evaluation for E&I Steel Support (Brown Field) | EL | Procurement | 2025-12-08 |  | 2025-12-15 |  | 2025-12-20 |  |  |  | 2025-12-27
2021-4569-3W-0308 | Technical Bid Evaluation for E&I Miscellaneous (Brown Field) | EL | Procurement | 2026-02-02 |  | 2026-02-09 |  | 2026-02-14 |  |  |  | 2026-02-21
2021-4572-3V-0210 | Bid Evaluation Criteria for Brown Field Modification of MV/LV Switchgear & MCC | EL | Bid | 2025-09-16 | 2025-09-16 | 2025-10-16 |  | 2025-10-21 |  |  |  | 2025-11-04
2021-4575-3V-0201 | Bid Evaluation Criteria for Distribution Boards & Small Power Transformer (LQ2 Module) | EL | Bid | 2025-08-22 | 2025-08-22 | 2025-09-21 | 2025-09-22 15:32 | 2025-09-26 | 2025-10-01 |  |  | 2025-10-10
2021-4575-3V-0202 | Bid Evaluation Criteria for Lighting Fixtures and Accessories (Brown Field) | EL | Bid | 2025-09-11 | 2025-09-11 | 2025-10-11 | 2025-10-02 15:57 | 2025-10-16 | 2025-10-06 |  |  | 2025-10-30
2021-4569-3V-0205 | Bid Evaluation Criteria for E&I Cables (Brown Field) | EL | Bid | 2025-09-16 | 2025-09-16 | 2025-10-16 |  | 2025-10-21 |  |  |  | 2025-11-04
2021-4569-3V-0206 | Bid Evaluation Criteria for E&I Cable Glands (Brown Field) | EL | Bid | 2025-11-05 |  | 2025-12-05 |  | 2025-12-10 |  |  |  | 2025-12-24
2021-4569-3V-0207 | Bid Evaluation Criteria for E&I Cable Ladder Tray (Brown Field) | EL | Bid | 2025-09-29 | 2025-09-29 | 2025-10-29 |  | 2025-11-03 |  |  |  | 2025-11-17
2021-4575-3V-0203 | Bid Evaluation Criteria for Electrical Junction Box, SO and LCS (Brown Field) | EL | Bid | 2025-10-15 | 2025-10-15 | 2025-11-14 |  | 2025-11-19 |  |  |  | 2025-12-03
2021-4569-3V-0209 | Bid Evaluation Criteria for E&I Earthing Material (Brown Field) | EL | Bid | 2025-08-11 | 2025-08-11 | 2025-09-10 | 2025-09-17 16:57 | 2025-09-15 | 2025-09-17 |  |  | 2025-09-29 | 2025-10-09
2021-4569-3V-0210 | Bid Evaluation Criteria for E&I Steel Support (Brown Field) | EL | Bid | 2025-08-20 | 2025-08-20 | 2025-09-19 | 2025-09-17 16:57 | 2025-09-24 | 2025-09-17 |  |  | 2025-10-08 | 2025-10-09
2021-4569-3V-0211 | Bid Evaluation Criteria for E&I Miscellaneous (Brown Field) | EL | Bid | 2025-07-18 | 2025-07-18 | 2025-11-28 |  | 2025-12-03 |  |  |  | 2025-12-27
2021-4569-3V-0212 | Bid Evaluation Criteria for E&I MCT (Brown Field) | EL | Bid | 2025-08-11 | 2025-08-11 | 2025-09-10 | 2025-09-17 16:57 | 2025-09-15 | 2025-09-17 |  |  | 2025-09-29 | 2025-10-09
2021-4569-3V-0213 | Bid Evaluation Criteria for E&I Universal Support (LQ2 Module) | EL | Bid | 2025-08-11 | 2025-08-11 | 2025-09-10 | 2025-09-17 16:57 | 2025-09-15 | 2025-09-17 |  |  | 2025-10-09 | 2025-10-16
2021-4506-4H-0001 | Control, Automation & Shutdown Philosophy | IN | Narratives | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-03 | 2025-08-29 | 2025-08-29 | 2025-12-25
2021-4506-4H-0002 | Reset Override & Alarm Management Philosophy | IN | Narratives | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-29 | 2025-08-29 | 2025-12-25
2021-4506-4H-0003 | Downhole Monitoring System & Interface | IN | Narratives | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-10-02 | 2025-10-03 | 2026-01-06
2021-4506-4H-0004 | Metering Philosophy | IN | Narratives | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-29 | 2025-08-29 | 2025-12-25
2021-4506-4H-0005 | Control Narrative | IN | Narratives | 2025-11-01 |  | 2025-12-01 |  | 2025-12-08 |  | 2026-02-06 |  | 2026-06-06
2021-4506-4J-0003 | Instrument Air Consumption Calculation | IN | Calculation | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-19 | 2025-07-19 | 2025-11-22 |  | 2026-02-27
2021-4506-4J-0004 | Instrument & Control Power Consumption Calculation | IN | Calculation | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-26 | 2025-07-26 | 2025-11-21 |  | 2026-02-27
2021-4509-4J-0001 | ST-CGF Telecom Power Consumption | IN | Calculation | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-26 | 2025-07-26 | 2025-11-21 |  | 2026-02-27
2021-4576-4J-0003 | ST-CGF PAGA Power Consumption | IN | Calculation | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-08-04 | 2025-08-04 | 2025-11-28 |  | 2026-02-27
2021-4506-4J-0005 | Instrument Equipment Weight Estimate | IN | Calculation | 2025-07-01 | 2025-07-01 | 2025-08-14 | 2025-08-14 08:16 | 2025-09-15 | 2025-09-26 | 2025-12-12 |  | 2026-03-12
2021-4504-4L-0001 | Fire & Gas Detection Equipment Specification | IN | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-09-25 | 2025-09-26 | 2026-01-13
2021-4506-4L-0001 | Instrument Design Specification | IN | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-29 | 2025-08-29 | 2026-01-22
2021-4506-4L-0002 | Instrument Installation Specification | IN | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-10-02 | 2025-10-10 | 2026-01-06
2021-4506-4L-0003 | Control System General Specification | IN | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-29 | 2025-08-29 | 2026-01-22
2021-4506-4L-0004 | Wellhead Control Panel Specification | IN | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-23 | 2025-08-23 | 2026-02-05
2021-4506-4L-0005 | Instrument Requirements for Package Equipment Specification | IN | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-29 | 2025-08-29 | 2026-01-22
2021-4506-4L-0006 | Export Gas Metering System Specification | IN | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-29 | 2025-08-29 | 2026-01-22
2021-4507-4L-0001 | Basic Process Control System Specification | IN | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-21 | 2025-08-21 | 2026-01-22
2021-4576-4L-0001 | ST-CGF PAGA Specification | IN | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-10-02 | 2025-10-03 | 2026-01-06
2021-4508-4L-0001 | Safety Instrumented System Specification | IN | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-21 | 2025-08-21 | 2026-01-22
2021-4506-4L-0011 | Specification for Instrument and Telecom Cable | IN | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-09-25 | 2025-09-26 | 2026-01-05
2021-4504-4M-0001 | Datasheet for Gas Detectors | IN | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-28 | 2025-08-04 14:01 | 2025-08-04 | 2025-08-04 | 2025-10-26 |  | 2026-01-27
2021-4504-4M-0002 | Datasheet for Flame Detectors | IN | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-28 | 2025-08-04 14:01 | 2025-08-04 | 2025-08-04 | 2025-10-26 |  | 2026-01-27
2021-4504-4M-0003 | Datasheet for Smoke Detectors | IN | Datasheet | 2025-06-28 | 2025-06-28 | 2025-08-02 | 2025-08-09 11:05 | 2025-08-09 | 2025-08-09 | 2025-10-26 |  | 2026-01-27
2021-4504-4M-0004 | Datasheet for Hydrogen Gas Detectors | IN | Datasheet | 2025-06-30 | 2025-06-30 | 2025-08-01 | 2025-08-08 17:12 | 2025-08-08 | 2025-08-08 | 2025-11-02 |  | 2026-01-27
2021-4504-4M-0005 | Datasheet for Manual/ESD Stations | IN | Datasheet | 2025-06-30 | 2025-06-30 | 2025-08-02 | 2025-08-09 11:05 | 2025-08-09 | 2025-08-09 | 2025-11-02 |  | 2026-01-27
2021-4504-4M-0006 | Datasheet for Portable Gas Detector | IN | Datasheet | 2025-06-30 | 2025-06-30 | 2025-08-02 | 2025-08-09 11:05 | 2025-08-09 | 2025-08-09 | 2025-11-02 |  | 2026-01-27
2021-4506-4M-0001 | Datasheet for Pressure Relief Valves | IN | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-28 | 2025-09-18 10:44 | 2025-09-17 | 2025-09-22 | 2025-10-30 |  | 2026-01-16
2021-4506-4M-0002 | Datasheet for Control Valves & Regulators | IN | Datasheet | 2025-06-28 | 2025-06-28 | 2025-08-28 | 2025-09-04 16:30 | 2025-09-04 | 2025-09-04 | 2025-10-23 |  | 2026-01-05
2021-4506-4M-0003 | Datasheet for On-Off Valves (SDV, BDV, XV) | IN | Datasheet | 2025-06-28 | 2025-06-28 | 2025-08-29 | 2025-09-05 14:00 | 2025-09-05 | 2025-09-05 | 2025-09-27 |  | 2025-12-04
2021-4506-4M-0004 | Datasheet for Orifice Plate & Flanges | IN | Datasheet | 2025-07-21 | 2025-07-21 | 2025-08-08 | 2025-08-08 | 2025-09-18 | 2025-09-22 | 2025-11-04 |  | 2026-01-12
2021-4506-4M-0005 | Datasheet for Restriction Orifices | IN | Datasheet | 2025-07-21 | 2025-07-21 | 2025-09-05 | 2025-09-10 07:26 | 2025-09-18 | 2025-09-26 | 2025-11-04 |  | 2026-01-12
2021-4506-4M-0006 | Datasheet for Deluge Valve Skids | IN | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-03 | 2025-09-26 | 2025-10-03 | 2025-12-11
2021-4506-4M-0007 | Datasheet For Coriolis Flowmeter | IN | Datasheet | 2025-09-09 | 2025-09-09 | 2025-11-17 |  | 2025-12-01 |  | 2026-01-23 |  | 2026-06-03
2021-4506-4M-0008 | Datasheet for Magnetic Flowmeters | IN | Datasheet | 2025-09-09 | 2025-09-09 | 2025-11-17 |  | 2025-12-01 |  | 2026-01-23 |  | 2026-06-03
2021-4506-4M-0011 | Datasheet for Rotameters | IN | Datasheet | 2025-08-25 | 2025-08-25 | 2025-08-26 | 2025-08-26 | 2025-10-10 | 2025-10-10 | 2025-12-15 |  | 2026-02-27
2021-4506-4M-0012 | Datasheet for Level Gauge and Transmitter | IN | Datasheet | 2025-09-16 | 2025-09-16 | 2025-10-16 | 2025-10-10 14:24 | 2025-11-01 |  | 2026-01-22 |  | 2026-03-18
2021-4506-4M-0013 | Datasheet for Analyzers | IN | Datasheet | 2025-08-12 | 2025-08-12 | 2025-09-22 | 2025-09-18 17:25 | 2025-09-27 | 2025-10-03 | 2025-11-26 |  | 2026-02-27
2021-4506-4M-0014 | Datasheet for Pig Signaller | IN | Datasheet | 2025-10-30 | 2025-10-03 17:06 | 2025-11-29 | 2025-10-03 17:06 | 2025-12-15 | 2025-10-10 | 2026-03-15 |  | 2026-06-21
2021-4576-4M-0001 | Datasheet for ST-CGF PAGA | IN | Datasheet | 2025-07-03 | 2025-07-03 | 2025-08-18 | 2025-08-25 10:15 | 2025-08-25 | 2025-08-25 | 2025-10-02 | 2025-10-03 | 2025-11-25
2021-4506-4M-0016 | Data Sheet For Differential Pressure Flow Transmitters | IN | Datasheet | 2025-07-14 | 2025-07-14 | 2025-09-15 | 2025-09-19 18:16 | 2025-09-18 | 2025-09-22 | 2025-11-29 |  | 2026-02-11
2021-4506-4M-0017 | Datasheet For PT & Differential Pressure Transmitters | IN | Datasheet | 2025-08-08 | 2025-08-08 | 2025-09-17 | 2025-09-19 16:12 | 2025-09-23 | 2025-09-26 | 2025-11-20 |  | 2026-02-11
2021-4506-4M-0018 | Datasheet For Pressure & Differential Pressure Gauges | IN | Datasheet | 2025-07-14 | 2025-07-14 | 2025-08-31 | 2025-09-19 17:34 | 2025-09-18 | 2025-09-22 | 2025-11-09 |  | 2026-01-23
2021-4506-4M-0019 | Datasheet For Temperature Transmitters | IN | Datasheet | 2025-07-15 | 2025-07-15 | 2025-09-17 | 2025-09-19 16:11 | 2025-09-21 | 2025-09-22 | 2025-11-26 |  | 2026-02-11
2021-4506-4M-0020 | Datasheet For Temperature Gauges | IN | Datasheet | 2025-07-03 | 2025-07-03 | 2025-08-31 | 2025-09-19 17:30 | 2025-09-18 | 2025-09-22 | 2025-11-14 |  | 2026-01-23
2021-4506-4M-0021 | Datasheet For Radar Level Transmitters | IN | Datasheet | 2025-08-08 | 2025-08-08 | 2025-09-17 | 2025-09-19 13:55 | 2025-09-23 | 2025-09-22 | 2025-11-20 |  | 2026-02-11
2021-4506-4M-0022 | Data Sheet For Differential Pressure Level Transmitters | IN | Datasheet | 2025-08-12 | 2025-08-12 | 2025-09-15 | 2025-09-19 16:30 | 2025-09-25 | 2025-09-22 | 2025-12-04 |  | 2026-02-11
2021-4506-4M-0023 | Datasheet for Choke Valves | IN | Datasheet | 2025-09-05 | 2025-09-05 | 2025-10-05 | 2025-10-10 14:29 | 2025-10-19 |  | 2026-01-17 |  | 2026-04-25
2021-4506-4M-0025 | Datasheet for V-cone Flowmeter | IN | Datasheet | 2025-09-09 | 2025-09-09 | 2025-11-17 |  | 2025-12-01 |  | 2026-01-23 |  | 2026-06-03
2021-4506-4U-0010 | Instrument Index | IN | Register | 2025-06-28 | 2025-06-28 | 2025-08-19 | 2025-09-17 16:17 | 2025-09-19 | 2025-09-22 | 2025-11-15 |  | 2026-06-11
2021-4506-4U-0011 | Instrument I/O List (BPCS) | IN | Register | 2025-06-28 | 2025-06-28 | 2025-07-22 | 2025-09-19 18:14 | 2025-09-19 | 2025-09-22 | 2025-11-04 |  | 2026-02-03
2021-4576-4U-0010 | ST-CGF PAGA Equipment List & Weight Estimate | IN | Register | 2025-07-09 | 2025-07-09 | 2025-09-15 | 2025-09-15 10:54 | 2025-10-22 | 2025-09-15 | 2025-11-22 |  | 2026-01-26
2021-4509-4U-0011 | ST-CGF Telecom Equipment List & Weight Estimate | IN | Register | 2025-07-09 | 2025-07-09 | 2025-09-15 | 2025-09-15 10:54 | 2025-10-22 | 2025-09-15 | 2025-11-22 |  | 2026-02-16
2021-4506-4U-0012 | Instrument I/O List (SIS & FGS) | IN | Register | 2025-06-28 | 2025-06-28 | 2025-07-22 | 2025-07-22 07:44 | 2025-09-19 | 2025-09-22 | 2025-11-04 |  | 2026-02-03
2021-4506-4U-0002 | Instrument Set Points, Ranges & Alarm Settings | IN | Register | 2025-08-18 | 2025-08-18 | 2025-09-17 | 2025-09-19 18:01 | 2025-10-03 | 2025-10-03 | 2026-01-25 |  | 2026-05-25
2021-4506-4U-0003 | Instrument MTO for Tubing, fittings and valves | IN | Register | 2025-11-12 |  | 2025-11-22 |  | 2025-12-01 |  | 2026-02-26 |  | 2026-06-16
2021-4506-4U-0004 | Instrument & Telecom MTO For Tray, Ladder & Accessories | IN | Register | 2025-08-29 | 2025-08-29 | 2025-10-26 |  | 2025-11-04 |  | 2026-02-04 |  | 2026-05-26
2021-4506-4U-0005 | Instrument & Telecom MTO For Cable & Accessories | IN | Register | 2025-08-25 | 2025-08-25 | 2025-10-01 | 2025-10-03 17:54 | 2025-10-11 | 2025-10-10 | 2026-01-16 |  | 2026-05-26
2021-4506-4U-0006 | Instrument & Telecom MTO For Cable Glands & Accessories | IN | Register | 2025-09-10 | 2025-09-10 | 2025-10-10 | 2025-10-09 19:00 | 2025-10-26 | 2025-10-10 | 2026-02-12 |  | 2026-05-26
2021-4506-4U-0008 | Instrument & Telecom MTO For Steel Support | IN | Register | 2025-06-28 | 2025-06-28 | 2025-07-24 | 2025-07-24 | 2025-08-09 | 2025-08-09 | 2025-10-30 |  | 2026-04-14
2021-4506-4U-0009 | Instrument & Telecom MTO for Miscellaneous | IN | Register | 2025-07-22 | 2025-07-22 | 2025-09-15 | 2025-09-15 10:54 | 2025-09-17 | 2025-09-15 | 2025-12-17 |  | 2026-05-26
2021-4506-4U-0013 | Instrument & Telecom MTO for MCT | IN | Register | 2025-07-22 | 2025-07-22 | 2025-09-30 | 2025-10-03 15:15 | 2025-10-10 | 2025-10-10 | 2026-01-11 |  | 2026-05-26
2021-4506-4U-0014 | Instrument & Telecom MTO for Earthing Material | IN | Register | 2025-07-22 | 2025-07-22 | 2025-09-30 | 2025-10-02 08:59 | 2025-10-10 | 2025-10-10 | 2026-01-11 |  | 2026-05-26
2021-4504-4V-0001 | Bid Evaluation Criteria for Fire & Gas Detection Equipment | IN | Bid | 2025-08-20 | 2025-08-20 | 2025-09-15 | 2025-09-15 10:54 | 2025-09-17 | 2025-09-15 |  |  | 2025-10-05
2021-4504-4V-9001 | Bid Evaluation Criteria for Fire & Gas Detection Equipment (LQ & BF) | IN | Bid | 2025-09-08 | 2025-09-08 | 2025-09-16 | 2025-09-19 14:51 | 2025-09-23 | 2025-09-22 |  |  | 2025-10-09 | 2025-10-11
2021-4507-4V-0001 | Bid Evaluation Criteria for Facility Control System | IN | Bid | 2025-06-28 | 2025-06-28 | 2025-07-14 | 2025-07-14 | 2025-07-21 | 2025-08-21 |  |  | 2025-08-21 | 2025-08-21
2021-4507-4V-9001 | Bid Evaluation Criteria for Facility Control System (BF) | IN | Bid | 2025-09-08 | 2025-09-08 | 2025-09-16 | 2025-09-22 17:21 | 2025-09-23 | 2025-09-22 |  |  | 2025-10-09
2021-4506-4V-0001 | Bid Evaluation Criteria for Wellhead Control Panel | IN | Bid | 2025-06-28 | 2025-06-28 | 2025-07-19 | 2025-07-19 | 2025-07-26 | 2025-07-26 |  |  | 2025-08-16 | 2025-08-16
2021-4506-4V-0013 | Bid Evaluation Criteria for Choke Valves | IN | Bid | 2025-10-15 | 2025-10-15 | 2025-10-30 |  | 2025-11-09 |  |  |  | 2025-11-30
2021-4506-4V-0002 | Bid Evaluation Criteria for Control Valves & Regulators | IN | Bid | 2025-07-09 | 2025-07-09 | 2025-08-02 | 2025-08-02 | 2025-08-09 | 2025-08-09 |  |  | 2025-08-29 | 2025-08-29
2021-4506-4V-0003 | Bid Evaluation Criteria for Actuated Valves (PS) | IN | Bid | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-03 |  |  | 2025-07-26 | 2025-07-26
2021-4506-4V-0014 | Bid Evaluation Criteria for Actuated Valves (LS) | IN | Bid | 2025-06-28 | 2025-06-28 | 2025-07-07 | 2025-07-07 | 2025-07-14 | 2025-07-14 |  |  | 2025-08-09 | 2025-08-09
2021-4506-4V-0004 | Bid Evaluation Criteria for Safety Relief Valve | IN | Bid | 2025-08-05 | 2025-08-05 | 2025-08-29 | 2025-09-05 14:00 | 2025-09-05 | 2025-09-05 |  |  | 2025-09-20 | 2025-09-26
2021-4506-4V-9004 | Bid Evaluation Criteria for Safety Relief Valve (BF) | IN | Bid | 2025-10-08 | 2025-10-08 | 2025-10-16 | 2025-10-10 14:32 | 2025-10-23 |  |  |  | 2025-11-08
2021-4506-4V-0005 | Bid Evaluation Criteria for Flowmeters (Coriolis, Magnetic, V-cone) | IN | Bid | 2025-11-05 |  | 2025-11-20 |  | 2025-11-30 |  |  |  | 2025-12-21
2021-4506-4V-0015 | Bid Evaluation Criteria for Rotameters | IN | Bid | 2025-09-15 | 2025-09-15 | 2025-09-30 | 2025-10-03 09:21 | 2025-10-10 | 2025-10-03 |  |  | 2025-10-31
2021-4506-4V-0006 | Bid Evaluation Criteria for Orifice Plates and Flange & Restriction Orifice Plates | IN | Bid | 2025-08-06 | 2025-08-06 | 2025-08-29 | 2025-09-05 14:00 | 2025-09-05 | 2025-09-05 |  |  | 2025-09-21 | 2025-09-26
2021-4506-4V-9006 | Bid Evaluation Criteria for Orifice Plates, Flange & Restriction Orifice Plates (LQ & BF) | IN | Bid | 2025-10-20 | 2025-09-19 11:38 | 2025-10-28 | 2025-09-19 11:38 | 2025-11-04 | 2025-09-26 |  |  | 2025-11-20
2021-4506-4V-0007 | Bid Evaluation Criteria for Deluge Valve Skids | IN | Bid | 2025-06-28 | 2025-06-28 | 2025-08-08 | 2025-06-30 | 2025-07-03 | 2025-07-03 |  |  | 2025-07-23 | 2025-07-23
2021-4506-4V-0008 | Bid Evaluation Criteria for Export Gas Metering System | IN | Bid | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 |  |  | 2025-07-26 | 2025-07-26
2021-4506-4V-0010 | Bid Evaluation Criteria for Level Gauge and Transmitter | IN | Bid | 2025-10-08 | 2025-10-08 | 2025-10-23 |  | 2025-11-02 |  |  |  | 2025-11-23
2021-4509-4V-0002 | Bid Evaluation Criteria For Telecommunication & PAGA Package | IN | Bid | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-19 | 2025-07-19 |  |  | 2025-08-16 | 2025-08-16
2021-4506-4V-0016 | Bid Evaluation Criteria For Electronic Transmitters | IN | Bid | 2025-09-03 | 2025-09-03 | 2025-09-15 | 2025-09-17 14:15 | 2025-09-17 | 2025-09-17 |  |  | 2025-10-03 | 2025-10-03
2021-4506-4V-9016 | Bid Evaluation Criteria For Electronic Transmitters (LQ & BF) | IN | Bid | 2025-10-20 | 2025-09-17 14:15 | 2025-10-28 | 2025-09-17 14:15 | 2025-11-04 | 2025-09-17 |  |  | 2025-11-20 | 2025-10-03
2021-4506-4V-0017 | Bid Evaluation Criteria For Analyzers | IN | Bid | 2025-09-10 | 2025-09-10 | 2025-09-18 | 2025-09-18 23:08 | 2025-09-25 | 2025-09-26 |  |  | 2025-10-10
2021-4506-4V-0018 | Bid Evaluation Criteria For Tubing, Fitting & Valves | IN | Bid | 2025-09-08 | 2025-09-08 | 2025-09-22 | 2025-09-25 14:07 | 2025-09-29 | 2025-10-03 |  |  | 2025-10-06
2021-4506-4V-9018 | Bid Evaluation Criteria For Tubing, Fitting & Valves (LQ & BF) | IN | Bid | 2025-09-08 | 2025-09-08 | 2025-09-22 | 2025-09-25 14:13 | 2025-09-29 | 2025-10-03 |  |  | 2025-10-06
2021-4506-4V-0019 | Bid Evaluation Criteria For Pig Detector | IN | Bid | 2025-11-10 |  | 2025-11-25 |  | 2025-12-05 |  |  |  | 2025-12-26
2021-4506-4V-0021 | Bid Evaluation Criteria For Instrument Gauges | IN | Bid | 2025-08-18 | 2025-08-18 | 2025-09-15 | 2025-09-15 10:54 | 2025-09-15 | 2025-09-15 |  |  | 2025-10-03 | 2025-10-03
2021-4506-4V-0022 | Bid Evaluation Criteria For FM-200 System | IN | Bid | 2025-06-28 | 2025-06-28 | 2025-07-19 | 2025-07-19 | 2025-07-26 | 2025-07-26 |  |  | 2025-08-16 | 2025-08-16
2021-4904-4V-0001 | Bid Evaluation Criteria For Addressable Fire Alarm System | IN | Bid | 2025-09-22 | 2025-09-22 | 2025-10-16 |  | 2025-10-23 |  |  |  | 2025-11-03
2021-4504-4W-1001 | Technical Requisition for Fire & Gas Detection Equipment | IN | Procurement | 2025-07-15 | 2025-07-15 | 2025-08-29 | 2025-09-05 14:00 | 2025-09-05 | 2025-09-05 | 2025-09-19 | 2025-09-26 | 2026-02-03
2021-4504-4W-9001 | Technical Requisition for Fire & Gas Detection Equipment (BF) | IN | Procurement | 2025-07-15 | 2025-07-15 | 2025-06-30 | 2025-06-30 | 2025-09-05 | 2025-09-05 | 2025-09-19 | 2025-09-26 | 2025-12-29
2021-4507-4W-1001 | Technical Requisition for Facility Control System | IN | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-07-19 | 2025-07-19 | 2026-02-05
2021-4507-4W-9001 | Technical Requisition for Facility Control System (BF) | IN | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-03 | 2025-07-19 | 2025-07-19 | 2026-04-10
2021-4506-4W-1001 | Technical Requisition for Wellhead Control Panel | IN | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-04 | 2025-08-04 | 2025-12-15
2021-4506-4W-9001 | Technical Requisition for Choke Valves | IN | Procurement | 2025-09-16 | 2025-09-16 | 2025-10-14 | 2025-10-08 09:16 | 2025-10-21 |  | 2025-11-15 |  | 2026-04-25
2021-4506-4W-1002 | Technical Requisition for Control Valves & Regulators (GF & BF) | IN | Procurement | 2025-06-28 | 2025-06-28 | 2025-07-12 | 2025-07-12 | 2025-07-19 | 2025-07-19 | 2025-08-16 | 2025-08-16 | 2026-01-27
2021-4506-4W-1003 | Technical Requisition for Actuated Valves (PS) | IN | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-04 | 2025-07-04 | 2025-07-21 | 2025-07-21 | 2026-02-02
2021-4506-4W-1014 | Technical Requisition for Actuated Valves (LS) | IN | Procurement | 2025-06-28 | 2025-06-28 | 2025-07-07 | 2025-07-07 | 2025-07-14 | 2025-07-14 | 2025-08-04 | 2025-08-04 | 2026-02-02
2021-4506-4W-1004 | Technical Requisition for Safety Relief Valve | IN | Procurement | 2025-07-14 | 2025-07-14 | 2025-09-06 | 2025-09-08 15:44 | 2025-09-09 | 2025-09-06 | 2025-09-25 | 2025-09-26 | 2026-01-16
2021-4506-4W-9004 | Technical Requisition for Safety Relief Valve (BF) | IN | Procurement | 2025-07-14 | 2025-07-14 | 2025-11-15 | 2025-09-12 18:01 | 2025-11-18 | 2025-09-12 | 2025-12-02 |  | 2026-04-03
2021-4506-4W-1005 | Technical Requisition for Flowmeters (Coriolis, Magnetic, V-cone) | IN | Procurement | 2025-11-03 |  | 2025-11-24 |  | 2025-12-08 |  | 2026-01-02 |  | 2026-06-03
2021-4506-4W-1015 | Technical Requisition for Rotameters | IN | Procurement | 2025-08-18 | 2025-08-18 | 2025-09-08 | 2025-09-19 10:31 | 2025-09-22 | 2025-09-26 | 2025-10-17 |  | 2026-02-18
2021-4506-4W-1006 | Technical Requisition for Orifice Plates, Flange & Restriction Orifice Plates | IN | Procurement | 2025-07-14 | 2025-07-14 | 2025-08-29 | 2025-09-05 14:00 | 2025-09-05 | 2025-09-05 | 2025-09-23 | 2025-09-26 | 2026-01-12
2021-4506-4W-9006 | Technical Requisition for Orifice Plates, Flange & Restriction Orifice Plates (BF) | IN | Procurement | 2025-08-18 | 2025-08-18 | 2025-09-07 | 2025-09-12 18:01 | 2025-09-10 | 2025-09-12 | 2025-09-25 | 2025-10-03 | 2026-01-06
2021-4506-4W-1007 | Technical Requisition for Deluge Valve Skids | IN | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-03 | 2025-07-21 | 2025-07-21 | 2025-11-12
2021-4506-4W-1008 | Technical Requisition for Export Gas Metering System | IN | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-03 | 2025-07-21 | 2025-07-21 | 2025-10-16
2021-4506-4W-1010 | Technical Requisition for Level Gauge and Transmitter | IN | Procurement | 2025-09-15 | 2025-09-15 | 2025-10-06 | 2025-09-26 11:00 | 2025-10-20 |  | 2025-11-14 |  | 2026-03-18
2021-4509-4W-1002 | Technical Requisition For Telecommunication and PAGA Package (GF,LQ &BF) | IN | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-03 | 2025-07-16 | 2025-07-16 | 2026-01-08
2021-4506-4W-1016 | Technical Requisition For Electronic Transmitters | IN | Procurement | 2025-08-12 | 2025-08-12 | 2025-09-18 | 2025-09-19 16:12 | 2025-09-25 | 2025-09-26 | 2025-10-11 |  | 2026-02-11
2021-4506-4W-9016 | Technical Requisition For Electronic Transmitters (BF) | IN | Procurement | 2025-08-12 | 2025-08-12 | 2025-09-13 | 2025-09-17 14:15 | 2025-09-15 | 2025-09-17 | 2025-09-26 | 2025-10-10 | 2026-01-05
2021-4506-4W-1017 | Technical Requisition For Analyzers | IN | Procurement | 2025-08-11 | 2025-08-11 | 2025-09-03 | 2025-09-11 19:31 | 2025-09-24 | 2025-09-26 | 2025-10-10 |  | 2026-02-13
2021-4506-4W-1018 | Technical Requisition For Tubing, Fitting & Valves | IN | Procurement | 2025-09-22 | 2025-09-22 | 2025-10-13 | 2025-09-26 15:08 | 2025-10-27 |  | 2025-11-21 |  | 2026-03-25
2021-4506-4W-9018 | Technical Requisition For Tubing, Fitting & Valves (BF) | IN | Procurement | 2025-09-08 | 2025-09-08 | 2025-09-22 | 2025-09-26 15:08 | 2025-09-29 | 2025-10-03 | 2025-10-06 |  | 2026-01-30
2021-4506-4W-1019 | Technical Requisition For Pig Detector | IN | Procurement | 2025-12-08 | 2025-10-03 17:06 | 2025-12-29 | 2025-10-03 17:06 | 2026-01-12 |  | 2026-02-06 |  | 2026-06-21
2021-4506-4W-1021 | Technical Requisition For Instrument Gauges | IN | Procurement | 2025-07-22 | 2025-07-22 | 2025-09-12 | 2025-09-12 18:01 | 2025-09-15 | 2025-09-12 | 2025-09-25 | 2025-10-03 | 2026-01-23
2021-4506-4W-9021 | Technical Requisition For Instrument Gauges (LQM2) | IN | Procurement | 2025-07-22 | 2025-07-22 | 2025-09-15 | 2025-09-17 14:55 | 2026-01-09 |  | 2026-02-06 |  | 2026-04-20
2021-4506-4W-1022 | Technical Requisition For FM-200 System | IN | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-03 | 2025-07-23 | 2025-07-23 | 2025-11-26
2021-4904-4W-1001 | Technical Requisition For Addressable Fire Alarm System (LQM2) | IN | Procurement | 2025-08-22 | 2025-08-22 | 2025-12-26 |  | 2026-01-09 |  | 2026-02-06 |  | 2026-04-20
2021-4504-4W-1101 | Technical Bid Evaluation for Fire & Gas Detection Equipment | IN | Procurement | 2025-11-02 |  | 2025-12-05 |  | 2025-12-12 |  |  |  | 2025-12-26
2021-4504-4W-9101 | Technical Bid Evaluation for Fire & Gas Detection Equipment (BF) | IN | Procurement | 2025-10-16 | 2025-10-16 | 2025-11-17 |  | 2025-11-17 |  |  |  | 2025-11-24
2021-4507-4W-1101 | Technical Bid Evaluation for Facility Control System | IN | Procurement | 2025-09-09 | 2025-09-09 | 2025-10-17 |  | 2025-10-22 |  |  |  | 2025-10-30
2021-4507-4W-9101 | Technical Bid Evaluation for Facility Control System (BF) | IN | Procurement | 2026-01-20 |  | 2026-02-25 |  | 2026-03-04 |  |  |  | 2026-03-11
2021-4506-4W-1101 | Technical Bid Evaluation for Wellhead Control Panel | IN | Procurement | 2025-09-19 | 2025-09-19 | 2025-11-03 |  | 2025-11-10 |  |  |  | 2025-11-17
2021-4506-4W-9101 | Technical Bid Evaluation for Choke Valves | IN | Procurement | 2026-01-13 |  | 2026-02-27 |  | 2026-03-06 |  |  |  | 2026-03-16
2021-4506-4W-1102 | Technical Bid Evaluation for Control Valves & Regulators (GF & BF) | IN | Procurement | 2025-10-16 | 2025-10-16 | 2025-10-20 |  | 2025-11-26 |  |  |  | 2025-12-03
2021-4506-4W-1103 | Technical Bid Evaluation for Actuated Valves (PS) | IN | Procurement | 2025-10-20 |  | 2025-11-24 |  | 2025-12-01 |  |  |  | 2025-12-08
2021-4506-4W-1114 | Technical Bid Evaluation for Actuated Valves (LS) | IN | Procurement | 2025-09-30 | 2025-09-30 | 2025-10-20 |  | 2025-10-25 |  |  |  | 2025-11-01
2021-4506-4W-1104 | Technical Bid Evaluation for Safety Relief Valve | IN | Procurement | 2025-10-22 |  | 2025-11-24 |  | 2025-12-01 |  |  |  | 2025-12-15
2021-4506-4W-9104 | Technical Bid Evaluation for Safety Relief Valve (BF) | IN | Procurement | 2026-01-12 |  | 2026-02-09 |  | 2026-02-27 |  |  |  | 2026-03-10
2021-4506-4W-1105 | Technical Bid Evaluation for Flowmeters (Coriolis, Magnetic, V-cone) | IN | Procurement | 2026-03-09 |  | 2026-04-11 |  | 2026-04-18 |  |  |  | 2026-05-02
2021-4506-4W-1115 | Technical Bid Evaluation for Rotameters | IN | Procurement | 2025-11-29 |  | 2025-12-27 |  | 2026-01-03 |  |  |  | 2026-01-17
2021-4506-4W-1106 | Technical Bid Evaluation for Orifice Plates, Flange & Restriction Orifice Plates | IN | Procurement | 2025-10-23 |  | 2025-11-20 |  | 2025-11-27 |  |  |  | 2025-12-11
2021-4506-4W-9106 | Technical Bid Evaluation for Orifice Plates, Flange & Restriction Orifice Plates (BF) | IN | Procurement | 2025-10-20 |  | 2025-11-14 |  | 2025-11-20 |  |  |  | 2025-11-28
2021-4506-4W-1107 | Technical Bid Evaluation for Deluge Valve Skids | IN | Procurement | 2025-08-29 | 2025-08-29 | 2025-10-07 | 2025-10-10 18:49 | 2025-10-15 |  |  |  | 2025-10-23
2021-4506-4W-1108 | Technical Bid Evaluation for Export Gas Metering System | IN | Procurement | 2025-08-04 | 2025-08-04 | 2025-09-19 | 2025-09-25 11:06 | 2025-09-24 | 2025-10-03 |  |  | 2025-10-03 | 2025-10-16
2021-4506-4W-1110 | Technical Bid Evaluation for Level Gauge and Transmitter | IN | Procurement | 2025-12-27 |  | 2026-01-24 |  | 2026-01-31 |  |  |  | 2026-02-14
2021-4509-4W-1102 | Technical Bid Evaluation For Telecommunication and PAGA Package (GF,LQ &BF) | IN | Procurement | 2025-09-26 | 2025-09-26 | 2025-10-31 |  | 2025-11-06 |  |  |  | 2025-11-13
2021-4506-4W-1116 | Technical Bid Evaluation For Electronic Transmitters | IN | Procurement | 2025-11-22 |  | 2025-12-20 |  | 2025-12-27 |  |  |  | 2026-01-10
2021-4506-4W-9116 | Technical Bid Evaluation For Electronic Transmitters (BF) | IN | Procurement | 2025-10-19 |  | 2025-11-14 |  | 2025-11-21 |  |  |  | 2025-11-28
2021-4506-4W-1117 | Technical Bid Evaluation For Analyzers | IN | Procurement | 2025-11-19 |  | 2025-12-22 |  | 2025-12-29 |  |  |  | 2026-01-12
2021-4506-4W-1118 | Technical Bid Evaluation For Tubing, Fitting & Valves | IN | Procurement | 2026-01-03 |  | 2026-01-31 |  | 2026-02-07 |  |  |  | 2026-02-21
2021-4506-4W-9118 | Technical Bid Evaluation For Tubing, Fitting & Valves (BF) | IN | Procurement | 2025-11-14 |  | 2025-12-08 |  | 2025-12-12 |  |  |  | 2025-12-19
2021-4506-4W-1119 | Technical Bid Evaluation For Pig Detector | IN | Procurement | 2026-04-01 |  | 2026-05-25 |  | 2026-05-29 |  |  |  | 2026-06-06
2021-4506-4W-1121 | Technical Bid Evaluation For Instrument Gauges | IN | Procurement | 2025-11-03 |  | 2025-12-01 |  | 2025-12-08 |  |  |  | 2025-12-22
2021-4506-4W-9121 | Technical Bid Evaluation For Instrument Gauges (LQM2) | IN | Procurement | 2025-12-15 |  | 2026-01-09 |  | 2026-01-14 |  |  |  | 2026-01-19
2021-4506-4W-1122 | Technical Bid Evaluation For FM-200 System | IN | Procurement | 2025-08-21 | 2025-08-21 | 2025-10-10 | 2025-10-10 18:50 | 2025-10-17 |  |  |  | 2025-10-24
2021-4904-4W-1101 | Technical Bid Evaluation For Addressable Fire Alarm System (LQM2) | IN | Procurement | 2025-12-23 |  | 2026-01-23 |  | 2026-01-30 |  |  |  | 2026-02-06
2021-4504-41-0001 | ST-CGF Fire & Gas Cause & Effect Chart | IN | Drawing | 2025-08-03 | 2025-08-03 | 2025-09-24 | 2025-09-26 15:34 | 2025-10-01 | 2025-10-10 | 2025-12-15 |  | 2026-04-14
2021-4504-45-0001 | F&G Detectors Mounting Detail | IN | Drawing | 2025-06-28 | 2025-06-28 | 2025-09-18 | 2025-09-19 14:30 | 2025-09-25 | 2025-09-26 | 2026-02-03 |  | 2026-06-16
2021-4506-45-0001 | Instrument Installation Detail | IN | Drawing | 2025-06-28 | 2025-06-28 | 2025-09-22 | 2025-09-19 10:31 | 2025-09-29 | 2025-09-26 | 2026-01-27 |  | 2026-06-09
2021-4506-45-0002 | Pneumatic Hook-up | IN | Drawing | 2025-06-28 | 2025-06-28 | 2025-11-13 |  | 2025-11-25 |  | 2026-02-12 |  | 2026-06-10
2021-4506-45-0003 | Hydraulic Hook-up | IN | Drawing | 2025-06-28 | 2025-06-28 | 2025-09-15 | 2025-09-17 14:15 | 2025-09-17 | 2025-09-17 | 2026-02-12 |  | 2026-05-20
2021-4506-45-0004 | Process Hook-up | IN | Drawing | 2025-06-28 | 2025-06-28 | 2025-11-13 |  | 2025-11-25 |  | 2026-02-12 |  | 2026-06-10
2021-4506-48-0001 | Overall Control System Block Diagram | IN | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-07 | 2025-07-14 11:40 | 2025-07-14 | 2025-07-14 | 2025-12-16 |  | 2026-03-16
2021-4506-48-0002 | ST-CGF Package Interface Block Diagrams | IN | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-28 | 2025-08-04 14:01 | 2025-08-04 | 2025-08-04 | 2025-10-30 |  | 2026-02-27
2021-4507-48-0001 | ST-CGF BPCS Cable Block Diagrams | IN | Drawing | 2025-09-02 | 2025-09-02 | 2025-09-15 | 2025-09-19 15:03 | 2025-09-22 | 2025-09-26 | 2026-01-08 |  | 2026-05-19
2021-4508-48-0001 | ST-CGF SIS&FGS Cable Block Diagrams | IN | Drawing | 2025-09-02 | 2025-09-02 | 2025-09-19 | 2025-09-19 16:35 | 2025-09-26 | 2025-09-26 | 2026-01-08 |  | 2026-05-19
2021-4505-48-0001 | ST-CGF Third Party Package Cable Block Diagrams | IN | Drawing | 2025-09-02 | 2025-09-02 | 2025-09-19 | 2025-09-19 16:39 | 2025-09-29 | 2025-09-26 | 2026-02-09 |  | 2026-06-19
2021-4504-49-0001 | ST-CGF Fire & Gas Location Layout | IN | Drawing | 2025-07-28 | 2025-07-28 | 2025-09-23 | 2025-09-26 14:51 | 2025-09-28 | 2025-10-01 | 2026-01-31 |  | 2026-04-06
2021-4504-49-0005 | ST-CGF Fire & Gas 2D Mapping Detail | IN | Drawing | 2025-07-21 | 2025-07-21 | 2025-09-18 | 2025-09-26 21:33 | 2025-09-24 | 2025-10-01 | 2026-01-24 |  | 2026-03-30
2021-4506-49-0001 | ST-CGF Instrument Main Tray & Ladder Layout | IN | Drawing | 2025-07-31 | 2025-07-31 | 2025-09-19 | 2025-09-25 16:11 | 2025-09-29 | 2025-10-03 | 2026-01-27 |  | 2026-06-16
2021-4506-49-0005 | ST-CGF Instrument Cable Routing Layout | IN | Drawing | 2025-08-07 | 2025-08-07 | 2025-10-06 | 2025-10-10 15:45 | 2025-10-16 |  | 2026-02-03 |  | 2026-06-23
2021-4506-49-0009 | ST-CGF Instrument Location Layout | IN | Drawing | 2025-08-04 | 2025-08-04 | 2025-11-26 |  | 2025-12-06 |  | 2026-02-01 |  | 2026-06-21
2021-4506-49-0010 | ST-CGF Instrument Main Tubing Routing Layouts | IN | Drawing | 2025-11-16 |  | 2025-11-26 |  | 2025-12-06 |  | 2026-02-01 |  | 2026-06-21
2021-4507-42-0001 | ST-CGF Interconnection Wiring Diagrams (BPCS) | IN | Drawing | 2026-01-06 |  | 2026-01-16 |  | 2026-01-23 |  | 2026-03-04 |  | 2026-05-19
2021-4508-42-0001 | ST-CGF Interconnection Wiring Diagrams (SIS & FGS) | IN | Drawing | 2026-01-06 |  | 2026-01-16 |  | 2026-01-23 |  | 2026-03-04 |  | 2026-05-19
2021-4505-42-0001 | ST-CGF Third Party Package Interconnection Wiring Diagrams | IN | Drawing | 2026-02-09 |  | 2026-02-19 |  | 2026-02-26 |  | 2026-04-07 |  | 2026-06-19
2021-4507-43-0001 | ST-CGF Instrument Loop Diagrams (BPCS) | IN | Drawing | 2026-02-10 |  | 2026-03-05 |  | 2026-03-22 |  |  |  | 2026-06-30
2021-4508-43-0001 | ST-CGF Instrument Loop Diagrams (SIS & FGS) | IN | Drawing | 2026-02-10 |  | 2026-03-12 |  | 2026-03-22 |  |  |  | 2026-07-05
2021-4506-45-0010 | ST-CGF Instrument Level Sketches | IN | Drawing | 2025-11-07 |  | 2025-12-07 |  | 2025-12-17 |  | 2026-02-27 |  | 2026-05-16
2021-4506-48-0003 | ST-CGF Instrument and F&G Cable Schedule | IN | Drawing | 2025-08-06 | 2025-08-06 | 2025-09-26 | 2025-09-26 15:36 | 2025-10-06 | 2025-10-03 | 2025-12-27 |  | 2026-05-26
2021-4506-48-0004 | ST-CGF Instrument Tubing Schedule | IN | Drawing | 2025-08-04 | 2025-08-04 | 2025-11-20 |  | 2025-11-27 |  | 2026-02-27 |  | 2026-06-14
2021-4506-48-0005 | ST-CGF Instrument and F&G Junction Boxes Schedule | IN | Drawing | 2025-10-04 | 2025-10-04 | 2025-10-14 |  | 2025-10-24 |  | 2026-02-26 |  | 2026-06-25
2021-4506-48-0006 | ST-CGF Multi Cable Transit (MCT) schedule | IN | Drawing | 2025-07-29 | 2025-07-29 | 2025-09-26 | 2025-09-26 15:34 | 2025-10-03 | 2025-10-10 | 2026-01-09 |  | 2026-05-22
2021-4506-49-0014 | ST-CGF Instrument Equipment Room Layout | IN | Drawing | 2025-07-29 | 2025-07-29 | 2025-09-17 | 2025-09-19 08:24 | 2025-09-30 | 2025-09-19 | 2026-02-26 |  | 2026-06-16
2021-4509-49-0001 | ST-CGF Telecom and PAGA Location Layouts | IN | Drawing | 2025-07-29 | 2025-07-29 | 2025-09-17 | 2025-09-19 16:49 | 2025-09-27 | 2025-09-26 | 2026-01-19 |  | 2026-06-16
2021-4576-48-0001 | ST-CGF PAGA Cable Block Diagram | IN | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-09 | 2025-07-16 08:42 | 2025-07-16 | 2025-07-16 | 2025-12-02 |  | 2026-06-24
2021-4509-48-0004 | ST-CGF CCTV Cable Block Diagrams | IN | Block | 2025-08-18 | 2025-08-18 | 2025-09-15 | 2025-09-15 10:54 | 2025-09-29 | 2025-09-15 | 2025-12-02 |  | 2026-06-24
2021-4509-48-0005 | ST-CGF Telephone and LAN Cable Block Diagrams | IN | Block | 2025-08-13 | 2025-08-13 | 2025-09-06 | 2025-09-08 15:44 | 2025-11-08 | 2025-09-08 | 2025-12-02 |  | 2026-06-24
2021-4509-48-0006 | ST-CGF Radio Cable Block Diagrams | IN | Block | 2025-08-23 | 2025-08-23 | 2025-09-15 | 2025-09-15 10:54 | 2025-09-29 | 2025-09-15 | 2025-12-02 |  | 2026-06-24
2021-4509-49-0002 | ST-CGF Telecom and PAGA Cable Routing Layouts | IN | Drawing | 2025-08-05 | 2025-08-05 | 2025-10-02 | 2025-10-03 15:12 | 2025-10-12 |  | 2026-01-26 |  | 2026-06-23
2021-4509-42-0001 | ST-CGF Telephone and LAN Wiring Diagram | IN | Drawing | 2026-01-26 |  | 2026-02-05 |  | 2026-02-27 |  | 2026-04-16 |  | 2026-06-15
2021-4509-42-0002 | ST-CGF CCTV Wiring Diagram | IN | Drawing | 2026-01-26 |  | 2026-02-05 |  | 2026-02-27 |  | 2026-04-16 |  | 2026-06-15
2021-4509-42-0003 | ST-CGF Radio Wiring Diagram | IN | Drawing | 2026-01-26 |  | 2026-02-05 |  | 2026-02-27 |  | 2026-04-16 |  | 2026-06-15
2021-4576-42-0001 | ST-CGF PAGA Wiring Diagram | IN | Drawing | 2026-02-24 |  | 2026-03-06 |  | 2026-03-16 |  | 2026-04-30 |  | 2026-06-19
2021-4509-48-0001 | ST-CGF Telecom and PAGA Cable Schedule | IN | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-31 | 2025-07-31 | 2025-10-06 | 2025-10-10 | 2025-12-09 |  | 2026-06-14
2021-4509-48-0002 | ST-CGF Telecom and PAGA Junction Box Schedule | IN | Drawing | 2025-06-28 | 2025-06-28 | 2025-09-11 | 2025-09-18 17:18 | 2025-09-21 | 2025-09-22 | 2025-12-09 |  | 2026-06-14
2021-4509-48-0003 | ST-CGF Telecom and PAGA MCT Schedule | IN | Drawing | 2025-07-29 | 2025-07-29 | 2025-09-17 | 2025-09-26 19:09 | 2025-09-27 | 2025-09-26 | 2026-01-09 |  | 2026-05-22
2021-4509-45-0001 | ST-CGF Telecomun and PAGA Installation Detail | IN | Drawing | 2025-06-28 | 2025-06-28 | 2025-09-15 | 2025-09-19 10:32 | 2025-09-19 | 2025-09-26 | 2026-01-27 |  | 2026-06-09
2021-4505-4U-0001 | Explosion proof Register For Instrument, F&G, Telecom and PAGA Equipment | IN | Register | 2025-10-09 | 2025-10-09 | 2025-11-18 |  | 2025-12-02 |  | 2026-04-01 |  | 2026-06-30
2021-4500-1H-0001 | Mechanical Design Basis | ME | Narratives | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-03 | 2025-07-10 | 2025-07-03 | 2025-11-14 | 2025-09-30
2021-4568-1H-0002 | HVAC Basis of Design and Philosophy for ST-CGF Technical Buildings | ME | Narratives | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-03 | 2025-07-12 | 2025-07-12 | 2025-10-15 | 2025-10-16
2021-4500-1H-5003 | Material Handling Philosophy | ME | Narratives | 2025-07-20 | 2025-07-20 | 2025-06-30 | 2025-06-30 | 2025-08-08 | 2025-08-08 | 2025-09-22 | 2025-10-06 | 2025-11-11
2021-4568-1J-0001 | HVAC Calculation Note for ST-CGF Technical Buildings | ME | Calculation | 2025-06-28 | 2025-06-28 | 2025-07-05 | 2025-07-05 | 2025-07-12 | 2025-07-12 | 2025-08-21 | 2025-08-21 | 2025-11-20
2021-4568-1J-0002 | HVAC Duct Sizing and Pressure Loss Calculation ST-CGF Technical Buildings | ME | Calculation | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-31 | 2025-07-31 | 2025-10-01 | 2025-10-10 | 2025-12-05
2021-4500-1L-0001 | Specification for Package Equipment | ME | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-07-10 | 2025-07-10 | 2025-10-05
2021-4570-1L-0002 | Specification for Gas Turbine Generator | ME | Specification | 2025-06-28 | 2025-06-28 | 2025-08-04 | 2025-08-04 | 2025-07-03 | 2025-07-03 | 2025-07-10 | 2025-07-10 | 2025-10-12
2021-4525-1L-0006 | Specification for Pressure Vessels | ME | Specification | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-03 | 2025-07-03 | 2025-08-22 | 2025-08-22 | 2025-10-15
2021-4500-1L-0003 | Specification for Plate & Frame Heat Exchanger | ME | Specification | 2025-06-28 | 2025-06-28 | 2025-07-23 | 2025-07-23 | 2025-07-04 | 2025-07-04 | 2025-08-08 | 2025-08-08 | 2025-11-19
2021-4500-1L-0013 | Specification for Pedestal Crane | ME | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-18 | 2025-07-18 | 2025-07-31 | 2025-07-31 | 2025-10-27
2021-4500-1L-0004 | Specification for Submersible Pump | ME | Specification | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-07-16 | 2025-07-16 | 2025-11-07 | 2025-09-12 | 2025-12-01
2021-4500-1L-0015 | Specification for API Centrifugal Pump | ME | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-07-21 | 2025-07-21 | 2025-08-08 | 2025-08-08
2021-4500-1L-0020 | Specification for Reciprocating Pump | ME | Specification | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-03 | 2025-07-03 | 2025-08-22 | 2025-08-22 | 2025-11-01
2021-4524-1L-0004 | Specification for Gas Dehydration Package | ME | Specification | 2025-06-28 | 2025-06-28 | 2025-07-01 | 2025-07-01 | 2025-07-03 | 2025-07-03 | 2025-07-10 | 2025-07-10 | 2025-10-15
2021-4500-1L-0016 | Specification for Rotary Pump | ME | Specification | 2025-08-21 | 2025-08-21 | 2025-09-18 | 2025-09-19 08:24 | 2025-09-22 | 2025-09-19 | 2025-10-30 | 2025-10-09 | 2026-01-22
2021-4568-1L-0021 | Specification for HVAC for ST-CGF Technical Buildings | ME | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-07-12 | 2025-07-12 | 2025-10-30
2021-4542-1L-0005 | Specification for Hypochlorite Generation Package | ME | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-07-10 | 2025-07-10 | 2025-08-09 | 2025-08-09
2021-4571-1L-0022 | Specification for Emergency Diesel Generator | ME | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-10-23 | 2025-09-12 | 2025-12-25
2021-4564-1L-0007 | Specification for Instrument Air Compressor and Dryer Package | ME | Specification | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-03 | 2025-08-08 | 2025-08-08 | 2025-09-05 | 2025-09-05
2021-4550-1L-0009 | Specification for Nitrogen Generation Package | ME | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-16 | 2025-08-16 | 2025-11-01
2021-4500-1L-0023 | Specification for Non API Centrifugal Pump | ME | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-07-21 | 2025-07-21 | 2025-08-12 | 2025-08-12
2021-4500-1L-0017 | Specification for Storage Tank | ME | Specification | 2025-09-03 | 2025-09-03 | 2025-09-17 | 2025-09-26 19:04 | 2025-09-24 | 2025-10-09 | 2025-11-06 |  | 2026-02-04
2021-4542-1L-0010 | Specification for Chemical Injection Package | ME | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-22 | 2025-08-22 | 2025-11-01
2021-4500-1L-0011 | Specification for Pig Launcher | ME | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-07-10 | 2025-07-10 | 2025-10-18
2021-4526-1L-0035 | Specification for Gas Compressor Package | ME | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-07-10 | 2025-07-10 | 2025-10-27
2021-4526-1L-0012 | Specification For Printed Circuit Heat Exchanger (PCHE) | ME | Specification | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-03 | 2025-07-10 | 2025-07-10 | 2025-08-29 | 2025-08-29
2021-4526-1L-0013 | Specification for Air Cooler Heat Exchanger | ME | Specification | 2025-07-25 | 2025-07-25 | 2025-06-30 | 2025-06-30 | 2025-08-09 | 2025-08-09 | 2025-08-29 | 2025-08-29 | 2025-12-26
2021-4500-1L-0012 | Specification for Shell and Tube Heat Exchangers | ME | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-07-10 | 2025-07-10 | 2025-10-15
2021-4500-0L-0006 | Equipment Protection and Preservation Procedure Specification | ME | Specification | 2025-08-12 | 2025-08-12 | 2025-09-18 | 2025-09-12 | 2025-09-25 | 2025-09-19 | 2025-10-30 |  | 2025-11-30
2021-4541-1L-0040 | Specification for Mercury Removal Unit | ME | Specification | 2025-08-29 | 2025-08-29 | 2025-09-15 | 2025-09-05 | 2025-09-22 | 2025-09-12 | 2025-11-03 | 2025-09-30 | 2025-12-28
2021-4525-1L-0036 | User's Design Specification for Test SeparatorMBD-2701 | ME | Specification | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-07-03 | 2025-07-03 | 2025-07-10 | 2025-07-10 | 2025-10-21
2021-4525-1L-0037 | User's Design Specification for Production Separator MBD-2501 | ME | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-07-10 | 2025-07-10 | 2025-10-21
2021-4526-1L-0038 | User's Design Specification for Gas Compressor Suction Scrubber A/B MBD-2613A/B | ME | Specification | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-07-10 | 2025-07-10 | 2025-10-21
2021-4525-1M-0001 | Datasheet for Production Separator (MBD-2501) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-16 | 2025-08-16 | 2025-10-21
2021-4525-1M-0002 | Datasheet for Test Separator for CGF (MBD-2701) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-16 | 2025-08-16 | 2025-10-21
2021-4547-1M-0004 | Datasheet for Glycol Regeneration Package (ZZZ-4710) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-25 | 2025-08-25 | 2025-10-22
2021-4526-1M-0005 | Datasheet for Gas Compressor Package (CAE-2614A/B) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-08 | 2025-08-08 | 2025-10-27
2021-4525-1M-0007 | Datasheet for Compressor Discharge Cooler (HBG-2502) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-09-04 | 2025-09-04 | 2025-10-27
2021-4549-1M-0008 | Datasheet for Seawater Lift Pumps (PBE-4902A/B) | ME | Datasheet | 2025-07-07 | 2025-07-07 | 2025-06-30 | 2025-06-30 | 2025-07-26 | 2025-07-26 | 2025-08-26 | 2025-08-26 | 2025-12-08
2021-4599-1M-0010 | Datasheet for Pedestal Crane for CGF (ZZZ-9908) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-07-28 | 2025-07-28 | 2025-10-27
2021-4570-1M-0011 | Datasheet for Gas Turbine Generator (LAN 7000A/B) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-18 | 2025-07-18 | 2025-07-03 | 2025-07-03 | 2025-07-10 | 2025-07-10 | 2025-10-08
2021-4571-1M-0012 | Datasheet for Emergency Diesel Generator (LAN-7100) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-01 | 2025-07-01 | 2025-07-03 | 2025-07-03 | 2025-07-26 | 2025-07-26 | 2025-11-16
2021-4525-1M-0017 | Datasheet for Glycol Contactor (MAF-2401) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-25 | 2025-08-25 | 2025-10-22
2021-4526-1M-0021 | Datasheet for Gas Compression Suction Scrubber (MBD-2613A/B) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-16 | 2025-08-16 | 2025-10-21
2021-4526-1M-0022 | Datasheet for Gas Compression Suction Cooler (HBG-2612A/B) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-29 | 2025-08-29 | 2025-10-27
2021-4549-1M-0024 | Datasheet for Seawater Filters (MAJ-4903A/B) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-26 | 2025-07-26 | 2025-09-04 | 2025-09-04 | 2025-11-19
2021-4549-1M-0025 | Datasheet for Cooling Water Expansion Vessel (MBJ-4905) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-26 | 2025-08-26 | 2025-10-20
2021-4549-1M-0026 | Datasheet for Cooling Water Trim Filter (MAJ-4906) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-17 | 2025-07-17 | 2025-07-26 | 2025-07-26 | 2025-09-04 | 2025-09-04 | 2025-11-19
2021-4549-1M-0027 | Datasheet for Seawater/Cooling Water Heat Exchanger (HBA-4904A/B) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-12 | 2025-07-12 | 2025-11-02 | 2025-09-30 | 2025-11-26
2021-4549-1M-0028 | Datasheet for Cooling Water Circulation Pumps (PBE-4907A/B) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-17 | 2025-07-17 | 2025-07-03 | 2025-07-03 | 2025-07-12 | 2025-07-12 | 2025-10-27
2021-4543-1M-0029 | Datasheet for HP Flare Scrubber (MBF-4302) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-07-03 | 2025-07-03 | 2025-10-07 |  | 2025-10-31
2021-4543-1M-0031 | Datasheet for HP Flare Scrubber Pumps (PBE-4304A/B) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-07-12 | 2025-07-12 | 2025-10-27
2021-4562-1M-0034 | Datasheet for Hazardous Open Drain Tank (ABJ-6202) | ME | Datasheet | 2025-09-10 | 2025-09-10 | 2025-09-17 | 2025-10-03 23:03 | 2025-10-01 | 2025-10-06 | 2025-11-30 |  | 2026-02-11
2021-4562-1M-0035 | Datasheet for Hazardous Open Drain Pump (PBA-6203) | ME | Datasheet | 2025-10-11 | 2025-10-11 | 2025-10-18 |  | 2025-10-25 |  | 2025-12-14 |  | 2026-03-14
2021-4562-1M-0036 | Datasheet for Open Drain Caisson Pump (PBA-6205) | ME | Datasheet | 2025-10-11 | 2025-10-11 | 2025-10-18 |  | 2025-10-25 |  | 2025-12-14 |  | 2026-03-14
2021-4562-1M-0059 | Datasheet for Open Drain Caisson (ABH-6204) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-03 | 2025-07-21 | 2025-07-21 | 2025-10-19
2021-4561-1M-0037 | Datasheet for Closed Drain Vessel (MBF-6101) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-03 | 2025-10-07 |  | 2025-10-31
2021-4561-1M-0038 | Datasheet for Closed Drain Pumps (PBE-6103A/B) | ME | Datasheet | 2025-08-28 | 2025-08-28 | 2025-09-14 | 2025-09-18 07:15 | 2025-09-21 | 2025-09-24 | 2025-10-31 | 2025-10-14 | 2026-01-29
2021-4542-1M-0039 | Datasheet for Chemical Injection Package ZZZ-4201 | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-12 | 2025-07-12 | 2025-10-15 |  | 2025-11-08
2021-4542-1M-0058 | Datasheet for Chemical Injection Package ZZZ-4202 | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-05 | 2025-07-07 16:45 | 2025-07-12 | 2025-07-12 | 2025-10-15 |  | 2025-11-08
2021-4542-1M-0040 | Datasheet for Hypochlorite Generation Package (ZZZ-4101) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-07 | 2025-07-07 | 2025-07-03 | 2025-07-03 | 2025-07-26 | 2025-07-26 | 2025-10-16
2021-4564-1M-0041 | Datasheet for Instrument Air Compressor Package (ZZZ-6400) | ME | Datasheet | 2025-07-02 | 2025-07-02 | 2025-07-07 | 2025-07-07 | 2025-07-03 | 2025-07-03 | 2025-09-05 | 2025-09-05 | 2025-12-03
2021-4564-1M-0042 | Datasheet for Instrument Air Dryer Package (ZZZ-6405) | ME | Datasheet | 2025-07-02 | 2025-07-02 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-09-05 | 2025-09-05 | 2025-12-03
2021-4564-1M-0043 | Datasheet for Instrument Air Receiver (MBL-6410) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-25 | 2025-08-25 | 2025-10-20
2021-4564-1M-0044 | Datasheet for Utility Air Receiver (MBL-6411) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-25 | 2025-08-25 | 2025-10-20
2021-4550-1M-0045 | Datasheet for Nitrogen Generation Package (ZZZ-5000) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-10-15 |  | 2025-11-08
2021-4550-1M-0046 | Datasheet for Nitrogen Receiver (MBL-5010) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-26 | 2025-08-26 | 2025-10-20
2021-4568-1M-0047 | HVAC Equipment Datasheet for ST-CGF Technical Building | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-08-16 | 2025-08-16 | 2025-09-22 | 2025-09-08 | 2025-11-27
2021-4530-1M-0048 | Datasheet for Sales Gas Launcher (KAH-3004) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-10-14 |  | 2025-11-07
2021-4524-1M-0049 | Datasheet for Dehydrated Gas Coalescer (MAD-2415) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-08-01 | 2025-08-01 | 2025-07-03 | 2025-07-03 | 2025-08-25 | 2025-08-25 | 2025-10-22
2021-4557-1M-0053 | Datasheet for Fuel Gas Pre- Cooler (HAL-5704) | ME | Datasheet | 2025-08-01 | 2025-08-01 | 2025-06-30 | 2025-06-30 | 2025-08-09 | 2025-08-09 | 2025-10-04 | 2025-09-12 | 2026-01-02
2021-4557-1M-0055 | Datasheet for Fuel Gas Scrubber (MBF-5701) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-25 | 2025-08-25 | 2025-10-15
2021-4557-1M-0056 | Datasheet for Fuel Gas Filters (MBF-5702A/B) | ME | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-07-26 | 2025-07-26 | 2025-08-29 | 2025-08-29 | 2025-11-19
2021-4557-1M-0057 | Datasheet for Fuel Gas Superheater (HAP-5703A/B) | ME | Datasheet | 2025-07-17 | 2025-07-17 | 2025-06-30 | 2025-06-30 | 2025-07-12 | 2025-07-12 | 2025-09-19 |  | 2025-12-18
2021-4582-1M-0059 | Datasheet for Material Handling and Powered Lifting Equipment | ME | Datasheet | 2025-11-17 |  | 2025-11-24 |  | 2025-12-01 |  | 2026-01-20 |  | 2026-04-20
2021-4587-1M-0060 | Datasheet for Workshop Equipment | ME | Datasheet | 2025-11-11 |  | 2025-11-18 |  | 2025-11-25 |  | 2026-01-14 |  | 2026-04-14
2021-4582-1M-0061 | Datasheet for Jib Crane | ME | Datasheet | 2025-11-17 |  | 2025-11-24 |  | 2025-12-01 |  | 2026-01-20 |  | 2026-04-20
2021-4541-1M-0065 | Datasheet for Mercury Removal Unit | ME | Datasheet | 2025-08-29 | 2025-08-29 | 2025-09-12 | 2025-09-05 | 2025-09-15 | 2025-09-12 | 2025-11-03 | 2025-09-30 | 2025-12-28
2021-4582-1H-5001 | Material Handling Study Report for ST-CGF | ME | Report | 2025-09-14 | 2025-09-14 | 2025-09-21 | 2025-10-03 11:11 | 2025-10-09 | 2025-10-14 | 2026-01-20 |  | 2026-05-30
2021-4526-1U-0001 | ST-CGF Master Equipment List | ME | Register | 2025-06-28 | 2025-06-28 | 2025-08-28 | 2025-09-04 16:30 | 2025-09-04 | 2025-09-04 | 2026-01-15 |  | 2026-05-25
2021-4556-1U-0002 | ST-CGF Lubrication Schedule | ME | Register | 2025-07-27 | 2025-07-27 | 2025-12-16 |  | 2025-12-23 |  | 2026-02-23 |  | 2026-05-15
2021-4568-1U-0003 | HVAC Bill of Material for Duting & Bulk Material of ST-CGF Technical Building | ME | Register | 2025-07-27 | 2025-07-27 | 2025-09-13 | 2025-09-26 11:09 | 2025-09-27 | 2025-09-26 | 2025-10-22 |  | 2025-12-31
2021-4568-1U-0004 | HVAC Equipment & Instrument List for ST-CGF Technical Building | ME | Register | 2025-06-28 | 2025-06-28 | 2025-08-07 | 2025-08-07 | 2025-08-14 | 2025-08-14 | 2025-08-29 | 2025-08-29 | 2025-12-04
2021-4500-1V-0001 | Bid Evaluation Criteria for ASME U2 Stamp Pressure Vessels | ME | Bid | 2025-06-28 | 2025-06-28 | 2025-08-01 | 2025-08-01 | 2025-07-03 | 2025-07-03 |  |  | 2025-08-08 | 2025-08-08
2021-4500-1V-0002 | Bid Evaluation Criteria for ASME U Stamp Pressure Vessels | ME | Bid | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 |  |  | 2025-07-10 | 2025-07-10
2021-4500-1V-0003 | Bid Evaluation Criteria for Utility Vessels | ME | Bid | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 |  |  | 2025-08-21 | 2025-08-21
2021-4530-1V-0022 | Bid Evaluation Criteria for Pig Launcher | ME | Bid | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 |  |  | 2025-07-10 | 2025-07-10
2021-4500-1V-0023 | Bid Evaluation Criteria for Tank | ME | Bid | 2025-09-10 | 2025-09-10 | 2025-09-17 | 2025-09-18 17:36 | 2025-10-01 | 2025-09-24 |  |  | 2025-10-11 | 2025-10-02
2021-4500-1V-0024 | Bid Evaluation Criteria for Filters | ME | Bid | 2025-06-28 | 2025-06-28 | 2025-07-24 | 2025-07-24 | 2025-07-31 | 2025-07-31 |  |  | 2025-08-29 | 2025-08-29
2021-4557-1V-0005 | Bid Evaluation Criteria for Air cooler | ME | Bid | 2025-08-01 | 2025-08-01 | 2025-07-28 | 2025-07-28 | 2025-08-12 | 2025-08-12 |  |  | 2025-08-29 | 2025-08-29
2021-4547-1V-0006 | Bid Evaluation Criteria for Gas Dehydration Package | ME | Bid | 2025-06-28 | 2025-06-28 | 2025-07-18 | 2025-07-18 | 2025-07-03 | 2025-07-03 |  |  | 2025-07-10 | 2025-07-10
2021-4549-1V-0010 | Bid Evaluation Criteria for Sea Water Lift Pumps | ME | Bid | 2025-07-07 | 2025-07-07 | 2025-06-30 | 2025-06-30 | 2025-07-26 | 2025-07-26 |  |  | 2025-08-12 | 2025-08-12
2021-4564-1V-0016 | Bid Evaluation Criteria for Instrument Air Compressor and Air Dryer Package | ME | Bid | 2025-07-02 | 2025-07-02 | 2025-07-18 | 2025-07-18 | 2025-07-12 | 2025-07-12 |  |  | 2025-08-04 | 2025-08-04
2021-4542-1V-0018 | Bid Evaluation Criteria for Hypochlorite Generation Package | ME | Bid | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-07-03 | 2025-07-03 |  |  | 2025-07-10 | 2025-07-10
2021-4550-1V-0019 | Bid Evaluation Criteria for Nitrogen Generation Package | ME | Bid | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 |  |  | 2025-07-18 | 2025-07-18
2021-4542-1V-0020 | Bid Evaluation Criteria for Chemical Injection Package | ME | Bid | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-12 | 2025-07-12 |  |  | 2025-08-02 | 2025-08-02
2021-4568-1V-0021 | Bid Evaluation Criteria For HVAC Equipment Package For ST-CGF Technical Building | ME | Bid | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-07-21 | 2025-07-21 |  |  | 2025-08-21 | 2025-08-21
2021-4500-1V-0025 | Bid Evaluation Criteria for Plate and Frame Heat Exchanger | ME | Bid | 2025-06-28 | 2025-06-28 | 2025-07-18 | 2025-07-18 | 2025-07-21 | 2025-07-21 |  |  | 2025-08-08 | 2025-08-08
2021-4561-1V-0026 | Bid Evaluation Criteria for Progressive Cavity Pump | ME | Bid | 2025-08-28 | 2025-08-28 | 2025-09-14 | 2025-09-19 08:24 | 2025-09-21 | 2025-09-19 |  |  | 2025-09-28 | 2025-10-10
2021-4562-1V-0027 | Bid Evaluation Criteria for Air Operated Diaphragm Pump | ME | Bid | 2025-10-11 | 2025-10-11 | 2025-10-18 |  | 2025-10-25 |  |  |  | 2025-11-11
2021-4582-1V-0028 | Bid Evaluation Criteria for Material Handling and Powered Lifting Equipment | ME | Bid | 2025-11-24 |  | 2025-12-01 |  | 2025-12-08 |  |  |  | 2025-12-25
2021-4587-1V-0029 | Bid Evaluation Criteria for Workshop Equipment | ME | Bid | 2025-11-18 |  | 2025-11-25 |  | 2025-12-02 |  |  |  | 2025-12-19
2021-4557-1V-0030 | Bid Evaluation Criteria for Fuel Gas Superheater | ME | Bid | 2025-07-17 | 2025-07-17 | 2025-07-14 | 2025-07-14 | 2025-07-21 | 2025-07-21 |  |  | 2025-08-08 | 2025-08-08
2021-4568-1V-0031 | Bid Evaluation Criteria For HVAC Ducting & Bulk Material Package For ST-CGF Technical Building | ME | Bid | 2025-07-13 | 2025-07-13 | 2025-07-11 | 2025-07-11 | 2025-08-26 | 2025-08-26 |  |  | 2025-09-30 | 2025-09-22
2021-4582-1V-0032 | Bid Evaluation Criteria for Jib Crane | ME | Bid | 2025-11-24 |  | 2025-12-01 |  | 2025-12-08 |  |  |  | 2025-12-25
2021-4988-1V-9001 | Bid Evaluation Criteria for TEMPSC (LQ) | ME | Bid | 2025-06-28 | 2025-06-28 | 2025-11-04 |  | 2025-11-07 |  |  |  | 2025-12-02
2021-4500-1W-0001 | Technical Requisition for ASME U2 Stamp Pressure Vessels | ME | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-03 | 2025-07-10 | 2025-07-10 | 2025-11-18
2021-4500-1W-0002 | Technical Requisition for ASME U Stamp Pressure Vessels | ME | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-07-10 | 2025-07-10 | 2025-10-31
2021-4500-1W-0003 | Technical Requisition for Utility Vessels | ME | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-22 | 2025-08-22 | 2025-11-17
2021-4530-1W-0022 | Technical Requisition for Pig Launcher | ME | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-18 | 2025-08-18 | 2025-11-01
2021-4541-1W-0075 | Technical Requisition for Mercury Removal Unit | ME | Bid | 2025-09-06 | 2025-09-06 | 2025-09-09 | 2025-09-05 | 2025-09-12 | 2025-09-12 | 2025-11-01 | 2025-09-30 | 2025-12-25
2021-4541-1V-0033 | Bid Evaluation Criteria for Mercury Removal Unit | ME | Bid | 2025-09-03 | 2025-09-03 | 2025-09-19 | 2025-09-18 18:05 | 2025-09-26 | 2025-09-24 |  |  | 2025-10-20 | 2025-10-01
2021-4500-1W-0023 | Technical Requisition for Tank | ME | Procurement | 2025-09-17 | 2025-09-17 | 2025-09-24 | 2025-10-03 20:07 | 2025-10-01 | 2025-10-06 | 2025-10-18 |  | 2026-02-05
2021-4500-1W-0024 | Technical Requisition for Filters | ME | Procurement | 2025-06-28 | 2025-06-28 | 2025-07-17 | 2025-07-17 | 2025-07-26 | 2025-07-26 | 2025-11-17 |  | 2025-12-11
2021-4557-1W-0005 | Technical Requisition for Air Cooler | ME | Procurement | 2025-08-08 | 2025-08-08 | 2025-07-18 | 2025-07-18 | 2025-08-09 | 2025-08-09 | 2025-08-29 | 2025-08-29 | 2026-01-02
2021-4547-1W-0006 | Technical Requisition for Gas Dehydration Package | ME | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-07-16 | 2025-07-16 | 2026-02-06
2021-4549-1W-0009 | Technical Requisition for Sea Water Lift Pumps | ME | Procurement | 2025-07-14 | 2025-07-14 | 2025-07-23 | 2025-07-23 | 2025-07-31 | 2025-07-31 | 2025-08-25 | 2025-08-25 | 2026-01-18
2021-4564-1W-0015 | Technical Requisition for Instrument Air Compressor and Air Dryer Package | ME | Procurement | 2025-07-09 | 2025-07-09 | 2025-07-17 | 2025-07-17 | 2025-07-28 | 2025-07-28 | 2025-08-09 | 2025-08-09 | 2025-12-28
2021-4550-1W-0017 | Technical Requisition for Nitrogen Generation Package | ME | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-05 | 2025-07-05 | 2025-07-31 | 2025-07-31 | 2025-11-30
2021-4542-1W-0018 | Technical Requisition for Hypochlorite Generation Package | ME | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-07-10 | 2025-07-10 | 2025-12-17
2021-4542-1W-0019 | Technical Requisition for Chemical Injection Package | ME | Procurement | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-07-12 | 2025-07-12 | 2025-07-31 | 2025-07-31 | 2025-11-21
2021-4568-1W-0020 | Technical Requisition For HVAC Equipment Package For ST-CGF Technical Building | ME | Procurement | 2025-07-13 | 2025-07-13 | 2025-08-04 | 2025-08-04 | 2025-08-08 | 2025-08-08 | 2025-08-25 | 2025-08-25 | 2025-12-11
2021-4500-1W-0025 | Technical Requistion for Plate and Frame Heat Exchanger | ME | Procurement | 2025-07-02 | 2025-07-02 | 2025-07-16 | 2025-07-16 | 2025-07-21 | 2025-07-21 | 2025-08-08 | 2025-10-02 | 2025-12-27
2021-4561-1W-0026 | Technical Requistion for Progressive Cavity Pump | ME | Procurement | 2025-09-04 | 2025-09-04 | 2025-09-18 | 2025-09-26 21:02 | 2025-09-25 | 2025-09-30 | 2025-10-05 |  | 2026-02-03
2021-4562-1W-0027 | Technical Requistion for Air Operated Diaphragm Pump | ME | Procurement | 2025-10-18 |  | 2025-10-25 |  | 2025-11-01 |  | 2025-11-18 |  | 2026-03-03
2021-4582-1W-0028 | Technical Requistion for Material Handling and Powered Lifting Equipment | ME | Procurement | 2025-12-01 |  | 2025-12-08 |  | 2025-12-15 |  | 2026-01-01 |  | 2026-04-16
2021-4587-1W-0029 | Technical Requistion for Workshop Equipment | ME | Procurement | 2025-11-25 |  | 2025-12-02 |  | 2025-12-09 |  | 2025-12-26 |  | 2026-04-10
2021-4557-1W-0030 | Technical Requistion for Fuel Gas Superheater | ME | Procurement | 2025-07-24 | 2025-07-24 | 2025-07-11 | 2025-07-11 | 2025-07-21 | 2025-07-21 | 2025-08-08 | 2025-08-08 | 2025-12-27
2021-4568-1W-0031 | Technical Requistion For HVAC Ducting & Bulk Material Package For ST-CGF Technical Building | ME | Procurement | 2025-08-17 | 2025-08-17 | 2025-08-28 | 2025-08-28 | 2025-09-05 | 2025-09-05 | 2025-09-25 | 2025-09-26 | 2025-12-21
2021-4582-1W-0032 | Technical Requistion for Jib Crane | ME | Procurement | 2025-12-01 |  | 2025-12-08 |  | 2025-12-15 |  | 2026-01-01 |  | 2026-04-16
2021-4988-1W-9001 | Technical Requistion for TEMPSC (LQ) | ME | Procurement | 2025-06-28 | 2025-06-28 | 2025-11-04 |  | 2025-11-07 |  | 2025-12-02 |  | 2026-04-02
2021-4500-1W-0040 | Technical Bid Evaluation for ASME U2 Stamp Pressure Vessels | ME | Procurement | 2025-07-18 | 2025-07-18 | 2025-09-27 |  | 2025-10-14 |  |  |  | 2025-10-30
2021-4500-1W-0041 | Technical Bid Evaluation for ASME U Stamp Pressure Vessels | ME | Procurement | 2025-07-25 | 2025-07-25 | 2025-09-15 | 2025-09-17 14:15 | 2025-09-18 | 2025-09-17 |  |  | 2025-10-03 | 2025-10-14
2021-4500-1W-0042 | Technical Bid Evaluation for Utility Vessels | ME | Procurement | 2025-08-22 | 2025-08-22 | 2025-09-21 | 2025-09-26 17:00 | 2025-09-30 | 2025-10-02 |  |  | 2025-10-16
2021-4530-1W-0043 | Technical Bid Evaluation for Pig Launcher | ME | Procurement | 2025-08-27 | 2025-08-27 | 2025-09-17 | 2025-09-18 17:57 | 2025-09-25 | 2025-09-24 |  |  | 2025-10-15 | 2025-10-10
2021-4500-1W-0044 | Technical Bid Evaluation for Tank | ME | Procurement | 2025-12-14 |  | 2025-12-21 |  | 2026-01-02 |  |  |  | 2026-01-14
2021-4500-1W-0045 | Technical Bid Evaluation for Filters | ME | Procurement | 2025-09-21 | 2025-09-21 | 2025-10-15 |  | 2025-10-18 |  |  |  | 2025-11-01
2021-4547-1W-0047 | Technical Bid Evaluation for Air Cooler | ME | Procurement | 2025-11-09 |  | 2025-11-16 |  | 2025-11-23 |  |  |  | 2025-12-10
2021-4547-1W-0048 | Technical Bid Evaluation for Gas Dehydration Package | ME | Procurement | 2025-09-27 | 2025-09-27 | 2025-11-24 |  | 2025-11-27 |  |  |  | 2025-12-11
2021-4549-1W-0051 | Technical Bid Evaluation for Sea Water Lift Pumps | ME | Procurement | 2025-10-10 | 2025-10-10 | 2025-11-22 |  | 2025-11-25 |  |  |  | 2025-12-09
2021-4564-1W-0056 | Technical Bid Evaluation for Instrument Air Compressor and Air Dryer Package | ME | Procurement | 2025-10-10 | 2025-10-10 | 2025-11-01 |  | 2025-11-04 |  |  |  | 2025-11-18
2021-4550-1W-0057 | Technical Bid Evaluation for Nitrogen Generation Package | ME | Procurement | 2025-09-15 | 2025-09-15 | 2025-10-04 |  | 2025-10-07 |  |  |  | 2025-10-21
2021-4542-1W-0058 | Technical Bid Evaluation for Hypochlorite Generation Package | ME | Procurement | 2025-09-05 | 2025-09-05 | 2025-10-04 |  | 2025-10-07 |  |  |  | 2025-10-21
2021-4542-1W-0059 | Technical Bid Evaluation for Chemical Injection Package | ME | Procurement | 2025-09-20 | 2025-09-20 | 2025-09-27 |  | 2025-10-04 |  |  |  | 2025-10-21
2021-4568-1W-0060 | Technical Bid Evaluation for HVAC Equipment Package for ST-CGF Technical Building | ME | Procurement | 2025-10-19 |  | 2025-11-11 |  | 2025-11-14 |  |  |  | 2025-11-28
2021-4500-1W-0061 | Technical Bid Evaluation for Plate and Frame Heat Exchanger | ME | Procurement | 2025-09-28 | 2025-09-28 | 2025-10-31 |  | 2025-11-03 |  |  |  | 2025-11-17
2021-4561-1W-0062 | Technical Bid Evaluation for Progressive Cavity Pump | ME | Procurement | 2025-12-01 |  | 2025-12-08 |  | 2025-12-15 |  |  |  | 2026-01-01
2021-4562-1W-0063 | Technical Bid Evaluation for Air Operated Diaphragm Pump | ME | Procurement | 2026-01-09 |  | 2026-01-16 |  | 2026-01-23 |  |  |  | 2026-02-09
2021-4582-1W-0064 | Technical Bid Evaluation for Material Handling and Powered Lifting Equipment | ME | Procurement | 2026-02-22 |  | 2026-03-01 |  | 2026-03-08 |  |  |  | 2026-03-25
2021-4587-1W-0065 | Technical Bid Evaluation for Workshop Equipment | ME | Procurement | 2026-02-16 |  | 2026-02-23 |  | 2026-03-02 |  |  |  | 2026-03-19
2021-4557-1W-0066 | Technical Bid Evaluation for Fuel Gas Superheater | ME | Procurement | 2025-11-04 |  | 2025-11-11 |  | 2025-11-18 |  |  |  | 2025-12-05
2021-4568-1W-0067 | Technical Bid Evaluation for HVAC Ducting & Bulk Material Package for ST-CGF Technical Building | ME | Procurement | 2025-10-29 |  | 2025-11-05 |  | 2025-11-12 |  |  |  | 2025-11-29
2021-4582-1W-0068 | Technical Bid Evaluation for Jib Crane | ME | Procurement | 2026-02-22 |  | 2026-03-01 |  | 2026-03-08 |  |  |  | 2026-03-25
2021-4541-1W-0076 | Technical Bid Evaluation for Mercury Removal Unit | ME | Procurement | 2025-12-16 |  | 2025-12-23 |  | 2025-12-30 |  |  |  | 2026-01-14
2021-4988-1W-9002 | Technical Bid Evaluation for TEMPSC (LQ) | ME | Procurement | 2025-08-29 | 2025-08-29 | 2026-02-28 |  | 2026-03-03 |  |  |  | 2026-03-22
2021-4500-1W-0074 | Startup & Operating Manual for CGF inclusive of modifications on PIP-WHPC-LQ platform | ME | Procurement | 2026-01-18 |  | 2026-01-25 |  | 2026-02-01 |  |  |  | 2026-02-22
2021-4568-16-0001 | HVAC Symbols & Legends | ME | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-23 | 2025-08-23 | 2025-11-25
2021-4568-16-0002 | HVAC Standard Details | ME | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-23 | 2025-07-23 | 2025-07-03 | 2025-07-03 | 2025-08-23 | 2025-08-23 | 2025-11-25
2021-4568-16-0003 | HVAC Ducting & Instrument Diagram for ST-CGF Technical Building | ME | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-08 | 2025-08-08 | 2025-08-14 | 2025-08-14 | 2025-08-29 | 2025-08-29 | 2025-12-02
2021-4568-16-0004 | HVAC Equipment & Ducting Layout for ST-CGF Technical Building | ME | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-14 | 2025-08-21 08:23 | 2025-08-21 | 2025-08-21 | 2025-10-30 |  | 2025-12-17
2021-4500-17-5001 | Material Handling Layout for ST-CGF | ME | Drawing | 2025-09-14 | 2025-09-14 | 2025-09-21 | 2025-10-03 11:11 | 2025-10-09 | 2025-10-10 | 2026-01-20 |  | 2026-04-21
2021-4568-16-0005 | HVAC Ducting Support Layout for ST-CGF Technical Building | ME | Drawing | 2026-05-01 |  | 2026-05-31 |  | 2026-06-30 |  | 2026-08-14 |  | 2026-09-28
2021-4500-17-5002 | ST-CGF Mechanical Workshop Layout | ME | Drawing | 2025-09-14 | 2025-09-14 | 2025-09-21 | 2025-10-10 15:34 | 2025-10-09 | 2025-10-14 | 2026-05-31 |  | 2026-08-30
2021-4568-16-0006 | HVAC Typical of Duct Penetration Drawing | ME | Drawing | 2025-06-29 | 2025-06-29 | 2025-07-11 | 2025-07-11 | 2025-08-29 | 2025-08-29 | 2025-11-15 |  | 2026-01-14
2021-4568-1V-9021 | Bid Evaluation Criteria For HVAC Equipment Package for ST-LQ Living Quarter Module #2 | ME | Bid | 2025-09-15 | 2025-09-15 | 2025-10-15 |  | 2025-10-30 |  |  |  | 2025-11-24
2021-4568-1V-9031 | Bid Evaluation Criteria For HVAC Ducting, Piping & Bulk Material Package for ST-LQ Living Quarter Module #2 | ME | Bid | 2025-10-15 | 2025-10-15 | 2025-11-14 |  | 2025-11-29 |  |  |  | 2026-01-08
2021-4568-1W-9020 | Technical Requistion For HVAC Equipment Package for ST-LQ Living Quarter Module #2 | ME | Procurement | 2025-09-25 | 2025-09-25 | 2025-10-25 |  | 2025-11-09 |  | 2025-11-24 |  | 2026-04-10
2021-4568-1W-9031 | Technical Requistion For HVAC Ducting, Piping & Bulk Material Package for ST-LQ Living Quarter Module #2 | ME | Procurement | 2025-11-09 |  | 2025-12-09 |  | 2025-12-24 |  | 2026-01-08 |  | 2026-04-29
2021-4568-1W-9060 | Technical Bid Evaluation for HVAC Equipment Package for ST-LQ Living Quarter Module #2 | ME | Procurement | 2026-01-30 |  | 2026-02-13 |  | 2026-02-20 |  | 2026-02-27 |  | 2026-03-06
2021-4568-1W-9067 | Technical Bid Evaluation for HVAC Ducting, Piping & Bulk Material Package for ST-LQ Living Quarter Module #2 | ME | Procurement | 2026-02-20 |  | 2026-03-06 |  | 2026-03-13 |  | 2026-03-20 |  | 2026-03-27
2021-4500-1P-5001 | 3D Model Implementation & Model Review Procedure | PI | Narratives | 2025-06-28 | 2025-06-28 | 2025-08-13 | 2025-06-30 | 2025-07-12 | 2025-07-12 | 2025-12-03 | 2025-10-01 | 2026-01-29
2021-4500-1H-5004 | Equipment Layout Philosophy & Narrative Report for ST-CGF | PI | Narratives | 2025-06-28 | 2025-06-28 | 2025-10-12 |  | 2025-10-15 |  | 2026-01-17 |  | 2026-06-09
2021-4500-1H-5001 | Pipe Stress Analysis Philosophy | PI | Narratives | 2025-06-28 | 2025-06-28 | 2025-08-27 | 2025-08-27 | 2025-07-02 | 2025-07-02 | 2025-10-25 |  | 2026-01-05
2021-4500-1H-5002 | Piping Standard Details | PI | Narratives | 2025-06-28 | 2025-06-28 | 2025-07-12 | 2025-07-19 10:51 | 2025-07-19 | 2025-07-19 | 2025-09-26 |  | 2026-01-15
2021-4500-1L-5001 | Piping Design Basis | PI | Narratives | 2025-06-28 | 2025-06-28 | 2025-08-08 | 2025-08-08 | 2025-07-21 | 2025-10-06 | 2025-10-03 |  | 2025-12-16
2021-4500-13-5001 | Pipe Support Standards | PI | Narratives | 2025-06-28 | 2025-06-28 | 2025-08-23 | 2025-08-23 | 2025-07-23 | 2025-07-23 | 2025-09-15 | 2025-09-15 | 2025-12-16
2021-4500-1J-5001 | Pipe Wall Thickness Calculation for ST-CGF, ST-PIP, ST-LQ and WHP-C | PI | Calculation | 2025-06-28 | 2025-06-28 | 2025-08-27 | 2025-08-27 | 2025-07-02 | 2025-07-02 | 2025-08-29 | 2025-08-29 | 2026-01-06
2021-4500-1R-5011 | Pipe Stress Analysis Report for ST-CGF - PRODUCTION FLOWLINES AND MANIFOLDS | PI | Calculation | 2025-06-28 | 2025-06-28 | 2025-08-13 | 2025-09-06 08:41 | 2025-10-07 | 2025-10-09 | 2025-11-28 |  | 2026-04-14
2021-4500-1R-5012 | Pipe Stress Analysis Report for ST-CGF - PRODUCTION GAS TO GAS COMPRESSOR SUCTION COOLERS AND SCRUBBERS | PI | Calculation | 2025-06-28 | 2025-06-28 | 2025-09-08 | 2025-09-10 17:04 | 2025-10-14 |  | 2025-12-05 |  | 2026-04-21
2021-4500-1R-5013 | Pipe Stress Analysis Report for ST-CGF - GAS COMPRESSORS SYSTEM | PI | Calculation | 2025-06-28 | 2025-06-28 | 2025-08-27 | 2025-09-06 08:42 | 2025-10-28 |  | 2025-12-19 |  | 2026-05-05
2021-4500-1R-5014 | Pipe Stress Analysis Report for ST-CGF - PRODUCTION GAS FROM COMPRESSOR DISCHARGE COOLER TO SALES GAS METERING SKID | PI | Calculation | 2025-06-28 | 2025-06-28 | 2025-10-14 | 2025-09-13 10:28 | 2025-10-21 |  | 2025-12-12 |  | 2026-04-28
2021-4500-1R-5015 | Pipe Stress Analysis Report for ST-CGF - SALES GAS PIG LAUNCHER SYSTEM | PI | Calculation | 2025-06-28 | 2025-06-28 | 2025-08-13 | 2025-08-13 07:23 | 2025-10-14 |  | 2025-12-05 |  | 2026-04-21
2021-4500-1R-5016 | Pipe Stress Analysis Report for ST-CGF - PRODUCTION LIQUID TO ST-PIP | PI | Calculation | 2025-06-28 | 2025-06-28 | 2025-08-23 | 2025-08-23 10:19 | 2025-10-07 | 2025-10-13 | 2025-11-28 |  | 2026-04-14
2021-4500-1R-5017 | Pipe Stress Analysis Report for ST-CGF - TEST FLUID TO PRODUCTION SEPARATOR | PI | Calculation | 2025-06-28 | 2025-06-28 | 2025-09-04 | 2025-09-04 07:31 | 2025-11-04 | 2025-10-10 | 2025-12-26 |  | 2026-05-12
2021-4500-1R-5018 | Pipe Stress Analysis Report for ST-CGF - HP FLARE SYSTEM | PI | Calculation | 2025-06-28 | 2025-06-28 | 2025-08-13 | 2025-08-13 07:23 | 2025-10-21 |  | 2025-12-12 |  | 2026-04-28
2021-4500-1R-5019 | Pipe Stress Analysis Report for ST-CGF - LP FLARE SYSTEM | PI | Calculation | 2025-06-28 | 2025-06-28 | 2025-08-13 | 2025-08-13 07:23 | 2025-10-28 |  | 2025-12-19 |  | 2026-05-05
2021-4500-1R-5020 | Pipe Stress Analysis Report for ST-CGF - PRODUCTION LIQUID TO ST-PIP | PI | Calculation | 2025-06-28 | 2025-06-28 | 2025-09-04 | 2025-09-04 16:49 | 2025-11-11 |  | 2026-01-02 |  | 2026-05-19
2021-4500-1R-5021 | Pipe Stress Analysis Report for ST-CGF - HP FLARE SCRUBBER PUMPS SYSTEM | PI | Calculation | 2025-06-28 | 2025-06-28 | 2025-08-18 | 2025-08-18 10:34 | 2025-11-04 |  | 2025-12-26 |  | 2026-05-12
2021-4500-1R-5022 | Pipe Stress Analysis Report for ST-CGF - CLOSED DRAIN PUMPS SYSTEM | PI | Calculation | 2025-06-28 | 2025-06-28 | 2025-08-27 | 2025-08-27 08:56 | 2025-11-11 |  | 2026-01-02 |  | 2026-05-19
2021-4500-1R-5023 | Pipe Stress Analysis Report for ST-CGF - System 13 | PI | Calculation | 2025-07-01 | 2025-07-01 | 2025-09-04 | 2025-09-04 07:31 | 2025-11-18 |  | 2026-01-09 |  | 2026-05-26
2021-4500-1R-5024 | Pipe Stress Analysis Report for ST-CGF - System 14 | PI | Calculation | 2025-07-01 | 2025-07-01 | 2025-08-20 | 2025-08-20 09:17 | 2025-11-18 |  | 2026-01-09 |  | 2026-05-26
2021-4500-1R-5025 | Pipe Stress Analysis Report for ST-CGF - System 15 | PI | Calculation | 2025-07-01 | 2025-07-01 | 2025-11-15 |  | 2025-11-18 |  | 2026-01-09 |  | 2026-05-26
2021-4500-1L-5004 | Valve Specification & Material Requirements | PI | Specification | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-08-26 | 2025-08-26 | 2026-01-20
2021-4500-1L-5005 | Piping Material Class Specification | PI | Specification | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-08-30 | 2025-08-30 | 2026-01-20
2021-4500-1L-5006 | Piping Fabrication Specification for ST-CGF, ST-PIP, ST-LQ and WHP-C | PI | Specification | 2025-06-28 | 2025-06-28 | 2025-08-01 | 2025-08-07 17:00 | 2025-08-08 | 2025-08-08 | 2025-09-23 | 2025-10-10 | 2026-01-20
2021-4500-1M-5001 | Datasheet for Manual Valves & Integral SBB & DBB | PI | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-17 | 2025-07-17 | 2025-07-02 | 2025-07-02 | 2025-08-22 | 2025-08-22 | 2026-01-13
2021-4500-1M-5002 | Datasheet for Strainers (Y Strainer, Basket Strainer, Cone Strainer) for STT Phase 2B | PI | Datasheet | 2025-08-18 | 2025-08-18 | 2025-10-18 |  | 2025-12-10 |  | 2026-01-12 |  | 2026-04-02
2021-4500-1M-5003 | Datasheet for Flexible Hose & Quick Coupling for STT Phase 2B | PI | Datasheet | 2025-09-20 | 2025-09-20 | 2025-12-05 |  | 2026-01-10 |  | 2026-02-06 |  | 2026-04-15
2021-4500-1M-5004 | Datasheet for Flame Arrestor for STT Phase 2B | PI | Datasheet | 2025-09-20 | 2025-09-20 | 2025-11-20 |  | 2025-12-20 |  | 2026-01-15 |  | 2026-04-01
2021-4500-1M-5005 | Datasheet for Valve Interlock for STT Phase 2B | PI | Datasheet | 2025-12-02 |  | 2026-01-06 |  | 2026-01-16 |  | 2026-02-27 |  | 2026-05-16
2021-4500-1M-5006 | Datasheet for Sample Connection & Chemical Injection for STT Phase 2B | PI | Datasheet | 2025-06-28 | 2025-06-28 | 2025-09-15 | 2025-09-25 15:04 | 2025-10-20 | 2025-10-10 | 2025-12-01 |  | 2026-02-20
2021-4500-1M-5007 | Datasheet for Corrosion Probe/Coupon for STT Phase 2B | PI | Datasheet | 2025-06-28 | 2025-06-28 | 2025-09-15 | 2025-09-25 15:04 | 2025-10-20 | 2025-10-10 | 2025-12-01 |  | 2026-02-20
2021-4500-1M-5008 | Datasheet for API Flanges for STT Phase 2B | PI | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-21 | 2025-07-21 | 2025-07-28 | 2025-07-28 | 2025-10-14 | 2025-09-17 | 2026-01-27
2021-4500-1M-5009 | Datasheet for Target Tee for STT Phase 2B | PI | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-31 | 2025-07-25 | 2025-08-01 | 2025-08-01 | 2025-10-14 | 2025-09-10 | 2026-01-27
2021-4500-1M-5010 | Datasheet for Bug Screen / Bird Screen for STT Phase 2B | PI | Datasheet | 2025-11-25 |  | 2025-12-30 |  | 2026-01-20 |  | 2026-02-03 |  | 2026-06-02
2021-4500-1M-5011 | Datasheet for Non Slam Check Valve for STT Phase 2B | PI | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-09-05 | 2025-09-05 | 2026-01-27
2021-4500-1M-5012 | Datasheet for Lateral Tee & Lateral Olet for STT Phase 2B | PI | Datasheet | 2025-08-30 | 2025-08-30 | 2025-07-28 | 2025-08-04 14:01 | 2025-08-04 | 2025-08-04 | 2025-11-10 |  | 2026-01-15
2021-4500-1M-5014 | Datasheet for Spring Support | PI | Datasheet | 2025-11-25 |  | 2025-12-15 |  | 2026-01-02 |  | 2026-01-20 |  | 2026-04-02
2021-4500-1M-5019 | Datasheet for Barred Tree for STT Phase 2B | PI | Datasheet | 2025-06-28 | 2025-06-28 | 2025-09-05 | 2025-09-05 07:16 | 2025-10-14 | 2025-10-10 | 2025-11-10 |  | 2026-01-15
2021-4500-1M-5020 | Datasheet for Kamos or Equivalent Testing Method for STT Phase 2B | PI | Datasheet | 2025-11-11 |  | 2025-12-16 |  | 2026-01-15 |  | 2026-02-27 |  | 2026-06-01
2021-4500-1M-5021 | Datasheet for Drain Trap for STT Phase 2B | PI | Datasheet | 2025-11-18 |  | 2025-11-18 |  | 2025-12-10 |  | 2026-01-12 |  | 2026-04-02
2021-4500-1M-5023 | Datasheet for Insulating Kit for STT Phase 2B | PI | Datasheet | 2025-11-11 |  | 2025-12-16 |  | 2026-01-15 |  | 2026-02-27 |  | 2026-06-01
2021-4500-1M-5032 | Datasheet for Flange Protectors | PI | Datasheet | 2025-12-01 |  | 2025-12-08 |  | 2025-12-15 |  | 2026-01-04 |  | 2026-02-03
2021-4500-1R-5003 | 3D Model Clash Check Report for CGF and bridge | PI | Report | 2025-12-30 |  | 2026-01-20 | [5 empty] | 2026-01-30
2021-4500-1R-5004 | 30% 3D Model Review Close-Out Report for STT Phase 2B | PI | Report | 2025-09-25 | 2025-09-25 | 2025-10-10 | [5 empty] | 2025-10-20
2021-4500-1R-5005 | 60% 3D Model Review Close-Out Report for STT Phase 2B | PI | Report | 2026-02-05 |  | 2026-02-13 | [5 empty] | 2026-03-12
2021-4500-1R-5006 | 90% 3D Model Review Close-Out Report for STT Phase 2B | PI | Report | 2026-05-28 |  | 2026-06-09 | [5 empty] | 2026-06-23
2021-4500-1U-5003 | Stress Critical Line List for ST-CGF and Bridge | PI | Register | 2025-06-28 | 2025-06-28 | 2025-09-10 | 2025-09-15 10:52 | 2025-10-10 | 2025-09-24 | 2026-01-23 |  | 2026-06-23
2021-4500-1U-5004 | Tie-in List for ST-CGF ST-PIP Bridge | PI | Register | 2025-12-23 |  | 2025-12-30 |  | 2026-01-20 |  | 2026-02-10 |  | 2026-06-02
2021-4500-1U-5005 | Specialty Item List & MTO for ST-CGF | PI | Register | 2025-06-28 | 2025-06-28 | 2025-10-30 | 2025-10-02 08:36 | 2025-11-06 | 2025-10-02 | 2026-02-03 |  | 2026-06-02
2021-4500-1U-5001 | Piping & Bulk MTO for ST-CGF and Bridge | PI | Register | 2025-07-05 | 2025-07-05 | 2025-12-27 |  | 2025-12-30 |  | 2026-01-23 |  | 2026-06-25
2021-4500-1U-5002 | Manual Valve List For CGF and Bridge | PI | Register | 2025-08-24 | 2025-08-24 | 2025-10-01 |  | 2025-10-08 |  | 2026-02-10 |  | 2026-06-02
2021-4500-1U-5006 | Piping and Equipmentt Insulation MTO For ST CGF and Bridge | PI | Register | 2026-02-07 |  | 2026-03-15 |  | 2026-04-05 |  | 2026-05-19 |  | 2026-07-03
2021-4500-1U-5007 | Pipe Support MTO For ST- CGF and Bridge | PI | Register | 2025-06-28 | 2025-06-28 | 2025-08-14 | 2025-08-21 11:35 | 2025-08-21 | 2025-08-21 | 2026-06-01 |  | 2026-06-25
2021-4500-1V-4001 | Bid Evaluation Criteria for Manual Valves | PI | Bid | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 |  |  | 2025-07-14 | 2025-07-14
2021-4500-1V-4003 | Bid Evaluation Criteria for Mechanical Valve Interlock | PI | Bid | 2025-12-02 |  | 2026-01-06 |  | 2026-01-20 |  |  |  | 2026-03-05
2021-4500-1V-4005 | Bid Evaluation Criteria for Flexible Hose and Quick Coupling | PI | Bid | 2025-12-06 |  | 2025-12-20 |  | 2026-01-12 |  |  |  | 2026-02-12
2021-4500-1V-4006 | Bid Evaluation Criteria for Access Fitting (Chemical Injection Quill, Sample Connection, Corrosion Coupon, Corrosion Probe) | PI | Bid | 2025-06-28 | 2025-06-28 | 2025-10-08 | 2025-10-03 07:29 | 2025-10-25 | 2025-10-10 |  |  | 2025-12-20
2021-4500-1V-4007 | Bid Evaluation Criteria for Flame Arrestor | PI | Bid | 2025-12-10 | 2025-10-03 16:57 | 2025-12-20 | 2025-10-03 16:57 | 2026-01-18 | 2025-10-09 |  |  | 2026-02-17
2021-4500-1V-4008 | Bid Evaluation Criteria for Strainer (Y Strainer, Basket Strainer, Cone Strainer) | PI | Bid | 2025-10-20 | 2025-10-03 17:00 | 2025-12-15 | 2025-10-03 17:00 | 2025-12-25 | 2025-10-09 |  |  | 2026-01-14
2021-4500-1V-4009 | Bid Evaluation Criteria for Barred Tee, Target Tee, Lateral Tee and Lateral Olet | PI | Bid | 2025-07-15 | 2025-07-15 | 2025-10-09 | 2025-10-03 16:59 | 2025-11-24 |  |  |  | 2025-12-08
2021-4500-1V-4010 | Bid Evaluation Criteria for Spring Support | PI | Bid | 2025-12-15 |  | 2025-12-22 |  | 2026-01-10 |  |  |  | 2026-01-30
2021-4500-1V-4012 | Bid Evaluation Criteria for Steel Piping bulk (Including CuNi and API 10K Flange) | PI | Bid | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-12 | 2025-07-12 |  |  | 2025-09-06 | 2025-09-10
2021-4500-1V-4013 | Bid Evaluation Criteria for GRE Piping | PI | Bid | 2025-07-15 | 2025-07-15 | 2025-06-29 | 2025-06-29 | 2025-08-26 | 2025-08-26 |  |  | 2025-09-15 | 2025-09-25 08:02
2021-4500-1V-4014 | Bid Evaluation Criteria for CPVC Piping | PI | Bid | 2025-10-02 | 2025-10-02 | 2025-11-02 |  | 2025-12-02 |  |  |  | 2025-12-20
2021-4500-1V-4015 | Bid Evaluation Criteria for Piping and Equipment Insulation | PI | Bid | 2026-03-15 |  | 2026-04-20 |  | 2026-05-10 |  |  |  | 2026-06-02
2021-4500-1V-4016 | Bid Evaluation Criteria for Piping supports | PI | Bid | 2025-07-15 | 2025-07-15 | 2025-08-07 | 2025-08-14 14:19 | 2025-08-14 | 2025-08-14 |  |  | 2025-09-30 | 2025-09-22
2021-4500-1V-4017 | Bid Evaluation Criteria for Gasket, Insulation Gasket and Kamos Gasket | PI | Bid | 2025-08-15 | 2025-08-15 | 2025-10-10 | 2025-10-03 17:03 | 2025-11-20 | 2025-10-09 |  |  | 2025-12-26
2021-4500-1V-4018 | Bid Evaluation Criteria for Bolts & Nuts | PI | Bid | 2025-10-15 | 2025-10-15 | 2025-11-15 |  | 2026-01-02 |  |  |  | 2026-01-20
2021-4500-1W-1001 | Technical Requisition for Manual Valves (PS) | PI | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-09-05 | 2025-09-05 | 2025-12-03
2021-4500-1W-1002 | Technical Requisition for Manual Valves (LS) | PI | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-07-14 | 2025-07-14 | 2025-11-18
2021-4500-1W-1003 | Technical Requisition for Mechanical Valve Interlock | PI | Procurement | 2025-12-02 |  | 2026-01-06 |  | 2026-01-20 |  | 2026-03-05 |  | 2026-06-24
2021-4500-1W-1005 | Technical Requisition for Flexible Hose and Quick Coupling | PI | Procurement | 2025-12-06 |  | 2025-12-20 |  | 2026-01-12 |  | 2026-02-12 |  | 2026-06-15
2021-4500-1W-1006 | Technical RequisitionforAccess Fitting (Chemical Injection Quill, Sample Connection, Corrosion Coupon, Corrosion Probe) | PI | Procurement | 2025-06-28 | 2025-06-28 | 2025-10-08 | 2025-10-01 09:16 | 2025-10-25 | 2025-10-10 | 2025-12-20 |  | 2026-04-15
2021-4500-1W-1007 | Technical Requisition for Flame Arrestor | PI | Procurement | 2025-12-10 |  | 2025-12-20 |  | 2026-01-18 |  | 2026-02-27 |  | 2026-05-18
2021-4500-1W-1008 | Technical Requisition for Strainers & Drain Traps | PI | Procurement | 2025-10-20 |  | 2025-12-15 |  | 2025-12-25 |  | 2026-01-14 |  | 2026-05-14
2021-4500-1W-1009 | Technical Requisition for Barred Tee and Lateral Tee | PI | Procurement | 2025-07-29 | 2025-07-29 | 2025-10-28 |  | 2025-11-24 |  | 2025-12-15 |  | 2026-04-12
2021-4500-1W-1010 | Technical Requisition for Spring Support | PI | Procurement | 2025-12-15 |  | 2025-12-22 |  | 2026-01-10 |  | 2026-01-30 |  | 2026-05-22
2021-4500-1W-1012 | Technical Requisition for Steel Piping bulk (Including Target Tee, Lateral Olet, CuNi and API 10K Flange) | PI | Procurement | 2025-06-28 | 2025-06-28 | 2025-07-19 | 2025-07-19 | 2025-07-26 | 2025-07-26 | 2025-10-18 | 2025-09-10 | 2025-11-11
2021-4500-1W-1013 | Technical Requisition for FRP Piping | PI | Procurement | 2025-07-15 | 2025-07-15 | 2025-08-19 | 2025-08-19 | 2025-08-26 | 2025-08-26 | 2025-09-15 | 2025-09-17 | 2026-01-10
2021-4500-1W-1014 | Technical Requisition for CPVC Piping | PI | Procurement | 2025-10-02 | 2025-10-02 | 2025-11-02 |  | 2025-12-02 |  | 2025-12-20 |  | 2026-04-27
2021-4500-1W-1015 | Technical Requisition for Piping and Equipment Insulation | PI | Procurement | 2026-03-15 |  | 2026-04-20 |  | 2026-05-10 |  | 2026-06-02 |  | 2026-10-01
2021-4500-1W-1016 | Technical Requisition for Piping supports | PI | Procurement | 2025-07-15 | 2025-07-15 | 2025-08-14 | 2025-08-14 | 2025-08-21 | 2025-08-21 | 2025-11-24 | 2025-09-19 | 2025-12-18
2021-4500-1W-1017 | Technical Requisition for Gasket, Insulation Gasket and Kamos Gasket | PI | Procurement | 2025-08-15 | 2025-08-15 | 2025-11-27 |  | 2025-12-15 |  | 2025-12-26 |  | 2026-04-26
2021-4500-1W-1018 | Technical Requisition for Bolts & Nuts | PI | Procurement | 2025-10-15 | 2025-10-15 | 2025-11-15 |  | 2026-01-02 |  | 2026-01-20 |  | 2026-05-24
2021-4500-1W-2001 | Technical Bid Evaluation for Manual Valves (PS) | PI | Procurement | 2025-08-20 | 2025-08-20 | 2025-12-05 |  | 2025-12-12 |  |  |  | 2026-01-12
2021-4500-1W-2002 | Technical Bid Evaluation for Manual Valves (LS) | PI | Procurement | 2025-08-17 | 2025-08-17 | 2025-10-10 | 2025-10-10 18:13 | 2025-10-17 | 2025-10-10 |  |  | 2025-11-11
2021-4500-1W-2003 | Technical Bid Evaluation for Mechanical Valve Interlock | PI | Procurement | 2026-04-06 |  | 2026-05-02 |  | 2026-05-06 |  |  |  | 2026-05-20
2021-4500-1W-2005 | Technical Bid Evaluation for Flexible Hose and Quick Coupling | PI | Procurement | 2026-03-28 |  | 2026-04-23 |  | 2026-04-27 |  |  |  | 2026-05-11
2021-4500-1W-2006 | Technical Bid Evaluation for Access Fitting (Chemical Injection Quill, Sample Connection, Corrosion Coupon, Corrosion Probe) | PI | Procurement | 2026-01-26 |  | 2026-02-21 |  | 2026-02-25 |  |  |  | 2026-03-11
2021-4500-1W-2007 | Technical Bid Evaluation for Flame Arrestor | PI | Procurement | 2026-02-28 |  | 2026-03-26 |  | 2026-03-30 |  |  |  | 2026-04-13
2021-4500-1W-2008 | Technical Bid Evaluation for Strainers & Drain Traps | PI | Procurement | 2026-02-24 |  | 2026-03-22 |  | 2026-03-26 |  |  |  | 2026-04-09
2021-4500-1W-2009 | Technical Bid Evaluation for Barred Tee and Lateral Tee | PI | Procurement | 2026-01-23 |  | 2026-02-23 |  | 2026-02-27 |  |  |  | 2026-03-13
2021-4500-1W-2010 | Technical Bid Evaluation for Spring Support | PI | Procurement | 2026-03-04 |  | 2026-03-28 |  | 2026-04-01 |  |  |  | 2026-04-15
2021-4500-1W-2012 | Technical Bid Evaluation for Steel Piping bulk (Including Target Tee, Lateral Olet, CuNi and API 10K Flange)) | PI | Procurement | 2025-08-24 | 2025-08-24 | 2025-10-28 |  | 2025-11-12 |  |  |  | 2025-11-23
2021-4500-1W-2013 | Technical Bid Evaluation for FRP Piping | PI | Procurement | 2025-10-23 |  | 2025-11-18 |  | 2025-11-22 |  |  |  | 2025-12-06
2021-4500-1W-2014 | Technical Bid Evaluation for CPVC Piping | PI | Procurement | 2026-02-07 |  | 2026-03-12 |  | 2026-03-16 |  |  |  | 2026-03-30
2021-4500-1W-2015 | Technical Bid Evaluation for Piping and Equipment Insulation | PI | Procurement | 2026-07-14 |  | 2026-08-07 |  | 2026-08-11 |  |  |  | 2026-08-25
2021-4500-1W-2016 | Technical Bid Evaluation for Piping supports | PI | Procurement | 2025-09-30 | 2025-09-30 | 2025-10-24 |  | 2025-10-28 |  |  |  | 2025-11-11
2021-4500-1W-2017 | Technical Bid Evaluation for Gasket, Insulation Gasket and Kamos Gasket | PI | Procurement | 2026-02-06 |  | 2026-03-04 |  | 2026-03-08 |  |  |  | 2026-03-22
2021-4500-1W-2018 | Technical Bid Evaluation for Bolts & Nuts | PI | Procurement | 2026-03-06 |  | 2026-03-30 |  | 2026-04-03 |  |  |  | 2026-04-17
2021-4500-09-5001 | Field Layout - Complex Layout | PI | Drawing | 2025-06-28 | 2025-06-28 | 2025-09-05 | 2025-09-12 15:52 | 2025-09-10 | 2025-09-12 | 2026-01-17 |  | 2026-06-09
2021-4500-00-5001 | ST-CGF Equipment Layout - Drawing Index | PI | Drawing | 2025-06-28 | 2025-06-28 | 2025-09-05 | 2025-09-12 15:52 | 2025-09-10 | 2025-09-12 | 2026-01-17 |  | 2026-06-09
2021-4500-07-5001 | ST-CGF Equipment Layout - Maindeck | PI | Drawing | 2025-06-28 | 2025-06-28 | 2025-09-07 | 2025-09-12 15:52 | 2025-09-10 | 2025-09-12 | 2026-01-17 |  | 2026-06-09
2021-4500-07-5002 | ST-CGF Equipment Layout - Intermediate Deck | PI | Drawing | 2025-06-28 | 2025-06-28 | 2025-09-05 | 2025-09-12 15:52 | 2025-09-10 | 2025-09-12 | 2026-01-17 |  | 2026-06-09
2021-4500-07-5003 | ST-CGF Equipment Layout - E-House | PI | Drawing | 2025-06-28 | 2025-06-28 | 2025-09-05 | 2025-09-12 15:52 | 2025-09-10 | 2025-09-12 | 2026-01-17 |  | 2026-06-09
2021-4500-07-5004 | ST-CGF Equipment Layout - Cellar Deck | PI | Drawing | 2025-06-28 | 2025-06-28 | 2025-09-07 | 2025-09-12 15:52 | 2025-09-10 | 2025-09-12 | 2026-01-17 |  | 2026-06-09
2021-4500-07-5005 | ST-CGF Equipment Layout - Sub Cellar Deck | PI | Drawing | 2025-06-28 | 2025-06-28 | 2025-09-07 | 2025-09-12 15:52 | 2025-09-10 | 2025-09-12 | 2026-01-17 |  | 2026-06-09
2021-4500-07-5006 | ST-CGF Equipment Layout - Top of Jacket Walkway | PI | Drawing | 2025-06-28 | 2025-06-28 | 2025-09-07 | 2025-09-12 15:52 | 2025-09-10 | 2025-09-12 | 2026-01-17 |  | 2026-06-09
2021-4500-07-5007 | ST-CGF Equipment Layout - Elevation Looking East | PI | Drawing | 2025-06-28 | 2025-06-28 | 2025-09-05 | 2025-09-12 15:52 | 2025-09-10 | 2025-09-12 | 2026-01-17 |  | 2026-06-09
2021-4500-07-5008 | ST-CGF Equipment Layout - Elevation Looking South | PI | Drawing | 2025-06-28 | 2025-06-28 | 2025-09-05 | 2025-09-12 15:52 | 2025-09-10 | 2025-09-12 | 2026-01-17 |  | 2026-06-09
2021-4500-07-5009 | ST-CGF Equipment Layout - Elevation Looking North | PI | Drawing | 2025-06-28 | 2025-06-28 | 2025-09-05 | 2025-09-12 15:52 | 2025-09-10 | 2025-09-12 | 2026-01-17 |  | 2026-06-09
2021-4500-07-5010 | ST-CGF Equipment Layout - Elevation Looking West | PI | Drawing | 2025-06-28 | 2025-06-28 | 2025-09-05 | 2025-09-12 15:52 | 2025-09-10 | 2025-09-12 | 2026-01-17 |  | 2026-06-09
2021-4500-11-1001 | STT-CGF Special Pipe Supports Detailed Drawings & Index | PI | Drawing | 2026-03-10 |  | 2026-04-21 | [5 empty] | 2026-06-30
2021-4500-11-1002 | STT-CGF Standard Pipe Support detailed Drawings & Index | PI | Drawing | 2026-03-10 |  | 2026-04-21 | [5 empty] | 2026-06-30
2021-4500-11-1003 | STT-CGF Piping Isometrics Drawings & Index | PI | Drawing | 2026-03-10 |  | 2026-04-21 | [5 empty] | 2026-06-16
2021-4500-11-8900 | ST-CGF Piping GA Drawing Index | PI | Drawing | 2026-03-10 |  | 2026-04-21 | [5 empty] | 2026-06-23
2021-4500-12-8901 | ST-CGF Piping GA Drawing Key Plan | PI | Drawing | 2026-03-10 |  | 2026-04-21 | [5 empty] | 2026-06-23
2021-4500-12-8902 | ST-CGF Piping GA Compressor Service Platform-Upper | PI | Drawing | 2026-03-10 |  | 2026-04-21 | [5 empty] | 2026-06-23
2021-4500-12-8903 | ST-CGF Piping GA Compressor Service Platform-Lower | PI | Drawing | 2026-03-10 |  | 2026-04-21 | [5 empty] | 2026-06-23
2021-4500-12-8904 | ST-CGF Piping GA other Service Platforms on Maindeck | PI | Drawing | 2026-03-10 |  | 2026-04-21 | [5 empty] | 2026-06-23
2021-4500-12-8905 | ST-CGF Piping GA Main Deck Upper Level | PI | Drawing | 2026-03-10 |  | 2026-04-21 | [5 empty] | 2026-06-23
2021-4500-12-8906 | ST-CGF Piping GA Main Deck Lower Level | PI | Drawing | 2026-03-10 |  | 2026-04-21 | [5 empty] | 2026-06-23
2021-4500-12-8907 | ST-CGF Piping GA Intermediate Deck Upper Level | PI | Drawing | 2026-03-10 |  | 2026-04-21 | [5 empty] | 2026-06-23
2021-4500-12-8908 | ST-CGF Piping GA Intermediate Deck Lower Level | PI | Drawing | 2026-03-10 |  | 2026-04-21 | [5 empty] | 2026-06-23
2021-4500-12-8909 | ST-CGF Piping GA at E-house | PI | Drawing | 2026-03-10 |  | 2026-04-21 | [5 empty] | 2026-06-23
2021-4500-12-8910 | ST-CGF Piping GA Cellar Deck Upper Level | PI | Drawing | 2026-03-10 |  | 2026-04-21 | [5 empty] | 2026-06-23
2021-4500-12-8911 | ST-CGF Piping GA Cellar Deck Lower Level | PI | Drawing | 2026-03-10 |  | 2026-04-21 | [5 empty] | 2026-06-23
2021-4500-12-8912 | ST-CGF Piping GA Sub-Cellar Deck Upper Level | PI | Drawing | 2026-03-10 |  | 2026-04-21 | [5 empty] | 2026-06-23
2021-4500-12-8913 | ST-CGF Piping GA Sub-Cellar Deck Lower Level | PI | Drawing | 2026-03-10 |  | 2026-04-21 | [5 empty] | 2026-06-23
2021-4500-12-8914 | ST-CGF Piping GA Top Of Jacket Upper Level | PI | Drawing | 2026-03-10 |  | 2026-04-21 | [5 empty] | 2026-06-23
2021-4500-12-8915 | ST-CGF Piping GA Top Of Jacket Lower Level | PI | Drawing | 2026-03-10 |  | 2026-04-21 | [5 empty] | 2026-06-23
2021-4500-9H-0001 | Process Design Criteria | PR | Narratives | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-10-24 |  | 2026-02-13
2021-4500-9H-0007 | Process Design Basis | PR | Narratives | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-03 | 2025-07-03 | 2025-09-26 | 2025-10-03 | 2026-03-11
2021-4500-9H-0002 | Process Control, Operating, Startup & Shutdown Philosophy | PR | Narratives | 2025-06-28 | 2025-06-28 | 2025-07-08 | 2025-07-08 | 2025-09-05 | 2025-09-05 | 2025-12-16 |  | 2026-05-05
2021-4500-9H-0004 | Valving and Isolation Philsophy | PR | Narratives | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-07-21 | 2025-07-21 | 2025-11-04 |  | 2026-03-27
2021-4500-9H-0003 | Relief & Blowdown Philosophy | PR | Narratives | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-04 | 2025-07-04 | 2025-12-09 |  | 2026-04-28
2021-4500-9H-0006 | Startup & Operating Manual for CGF inclusive of modifications on PIP-WHPC-LQ platform | PR | Narratives | 2025-06-28 | 2025-06-28 | 2026-06-16 |  | 2026-06-30 |  | 2026-07-28 |  | 2026-09-09
2021-4500-9H-0005 | Drainage Philosophy | PR | Narratives | 2025-06-28 | 2025-06-28 | 2025-08-26 | 2025-08-26 | 2025-07-04 | 2025-07-04 | 2025-11-07 |  | 2026-03-20
2021-4500-9J-0001 | Process Simulation Report | PR | Calculation | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-03 | 2025-08-28 | 2025-08-28 | 2026-03-18
2021-4500-9J-0003 | Process Calculations Report | PR | Calculation | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-03 | 2025-11-11 |  | 2026-04-23
2021-4500-9J-0006 | Utility Sizing Calculation Report | PR | Calculation | 2025-06-28 | 2025-06-28 | 2025-07-21 | 2025-09-12 18:01 | 2025-09-09 | 2025-09-12 | 2025-11-20 |  | 2026-04-29
2021-4500-9J-0004 | Process Line Sizing Calculations Report | PR | Calculation | 2025-06-28 | 2025-06-28 | 2025-08-15 | 2025-08-22 18:55 | 2025-08-22 | 2025-08-22 | 2025-10-23 |  | 2026-04-15
2021-4500-9J-0005 | Relief, Blowdown and low temperature study report | PR | Calculation | 2025-06-28 | 2025-06-28 | 2025-09-15 | 2025-09-19 13:37 | 2025-09-22 | 2025-09-30 | 2026-02-10 |  | 2026-06-16
2021-4500-9J-0007 | Flare Network Report | PR | Calculation | 2025-06-28 | 2025-06-28 | 2025-09-19 | 2025-09-26 10:18 | 2025-09-30 | 2025-10-13 | 2026-02-17 |  | 2026-06-23
2021-4500-9J-0008 | Control valve Process Calculation | PR | Calculation | 2025-06-28 | 2025-06-28 | 2025-08-28 | 2025-09-04 16:30 | 2025-09-04 | 2025-09-04 | 2025-09-22 |  | 2025-10-14
2021-4500-9J-0009 | Acoustic Induced Vibration (AIV) study | PR | Calculation | 2025-07-08 | 2025-07-08 | 2025-09-19 |  | 2025-10-03 |  | 2026-03-10 |  | 2026-07-28
2021-4500-9J-0010 | Flow Induced Vibration (FIV) study | PR | Calculation | 2025-07-08 | 2025-07-08 | 2025-09-17 | 2025-10-03 09:18 | 2025-09-29 | 2025-10-10 | 2026-03-03 |  | 2026-07-21
2021-4500-9J-0012 | Operating and Commissioning Manual -System Production Wellheads, Manifolds and Test Separator | PR | Calculation | 2026-05-19 |  | 2026-06-09 |  | 2026-06-23 |  | 2026-07-21 |  | 2026-08-18
2021-4500-9J-0013 | System Design & Operating Manual -Gas Compression System | PR | Calculation | 2026-05-19 |  | 2026-06-09 |  | 2026-06-23 |  | 2026-07-21 |  | 2026-08-18
2021-4500-9J-0014 | System Design & Operating Manual - Gas Cooling System | PR | Calculation | 2026-05-19 |  | 2026-06-09 |  | 2026-06-23 |  | 2026-07-21 |  | 2026-08-18
2021-4500-9J-0015 | System Design & Operating Manual - Gas Dehydration System | PR | Calculation | 2026-05-19 |  | 2026-06-09 |  | 2026-06-23 |  | 2026-07-21 |  | 2026-08-18
2021-4500-9J-0016 | System Design & Operating Manual -Export Line & Launcher System | PR | Calculation | 2026-05-19 |  | 2026-06-09 |  | 2026-06-23 |  | 2026-07-21 |  | 2026-08-18
2021-4500-9J-0017 | System Design & Operating Manual - Chemical Injection System | PR | Calculation | 2026-05-19 |  | 2026-06-09 |  | 2026-06-23 |  | 2026-07-21 |  | 2026-08-18
2021-4500-9J-0018 | System Design & Operating Manual - Flare System | PR | Calculation | 2026-05-19 |  | 2026-06-09 |  | 2026-06-23 |  | 2026-07-21 |  | 2026-08-18
2021-4500-9J-0019 | System Design & Operating Manual - Fuel Gas System | PR | Calculation | 2026-05-19 |  | 2026-06-09 |  | 2026-06-23 |  | 2026-07-21 |  | 2026-08-18
2021-4500-9J-0020 | System Design & Operating Manual - Closed & Open Drain System | PR | Calculation | 2026-05-19 |  | 2026-06-09 |  | 2026-06-23 |  | 2026-07-21 |  | 2026-08-18
2021-4500-9J-0021 | System Design & Operating Manual - IA and UA System | PR | Calculation | 2026-05-19 |  | 2026-06-09 |  | 2026-06-23 |  | 2026-07-21 |  | 2026-08-18
2021-4500-9J-0022 | System Design & Operating Manual - Nitrogen system | PR | Calculation | 2026-05-19 |  | 2026-06-09 |  | 2026-06-23 |  | 2026-07-21 |  | 2026-08-18
2021-4500-9J-0023 | System Design & Operating Manual - Seawater/ Cooling water system | PR | Calculation | 2026-05-19 |  | 2026-06-09 |  | 2026-06-23 |  | 2026-07-21 |  | 2026-08-18
2021-4500-9J-0024 | System Design & Operating Manual - MRU System | PR | Calculation | 2026-05-19 |  | 2026-06-09 |  | 2026-06-23 |  | 2026-07-21 |  | 2026-08-18
2021-4500-9M-0001 | Environmental Conditions & Utility Available Datasheet | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-09 | 2025-07-09 | 2025-07-03 | 2025-07-03 | 2025-09-19 | 2025-09-24 | 2026-03-06
2021-4525-9M-0002 | Process Datasheet for Test Separator | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-09 | 2025-07-09 | 2025-07-03 | 2025-07-03 | 2025-08-08 | 2025-08-08 | 2026-04-02
2021-4525-9M-0003 | Process Datasheet for Production Separator | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-09 | 2025-07-09 | 2025-07-03 | 2025-07-03 | 2025-08-08 | 2025-08-08 | 2026-04-06
2021-4526-9M-0005 | Process Datasheet for Gas Inlet Scrubber | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-08-08 | 2025-08-08 | 2026-04-10
2021-4543-9M-0010 | Process Datasheet for HP Flare Scrubber | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-09-15 | 2025-10-03 16:59 | 2025-10-01 | 2025-10-13 | 2026-02-17 |  | 2026-06-23
2021-4561-9M-0011 | Process Datasheet for Closed Drain Vessel | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-09-17 | 2025-10-03 16:59 | 2025-10-01 | 2025-10-13 | 2026-02-17 |  | 2026-06-23
2021-4549-9M-0012 | Process Datasheet for Cooling Water Expansion Vessel | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-06 | 2025-07-06 | 2025-08-22 | 2025-08-22 | 2025-11-27 |  | 2026-05-06
2021-4564-9M-0013 | Process Datasheet for Utility Air Receiver | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-28 | 2025-08-04 14:01 | 2025-08-04 | 2025-09-30 | 2025-11-29 |  | 2026-05-08
2021-4550-9M-0014 | Process Datasheet for Instrument Air Receiver | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-28 | 2025-08-04 14:01 | 2025-08-04 | 2025-09-30 | 2025-11-29 |  | 2026-05-08
2021-4550-9M-0015 | Process Datasheet for Nitrogen Receiver | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-04 | 2025-09-30 | 2025-12-01 |  | 2026-05-10
2021-4530-9M-0083 | Process Datasheet for Sales Gas Launcher | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-03 | 2025-07-03 | 2025-10-17 |  | 2026-03-20
2021-4562-9M-0020 | Process Datasheet for Hazardous Open Drain Tank | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-09 | 2025-07-09 | 2025-07-04 | 2025-07-04 | 2025-11-29 |  | 2026-05-08
2021-4549-9M-0021 | Process Datasheet for Seawater Lift Caisson | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-08-16 | 2025-08-16 | 2025-08-22 | 2025-08-22 | 2025-11-28 |  | 2026-05-08
2021-4562-9M-0083 | Process Datasheet for Open Drain Caisson | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-26 | 2025-08-26 | 2025-11-25 |  | 2026-05-04
2021-4543-9M-0033 | Process Datasheet for HP Flare Scrubber Pump | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-09-17 | 2025-10-03 16:59 | 2025-10-06 | 2025-10-10 | 2026-02-19 |  | 2026-06-25
2021-4561-9M-0034 | Process Datasheet for Closed Drain Pump | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-09-19 | 2025-09-26 10:51 | 2025-10-06 | 2025-10-10 | 2026-02-19 |  | 2026-06-25
2021-4562-9M-0035 | Process Datasheet for Hazardous Open Drain Pump | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-03 | 2025-12-01 |  | 2026-05-10
2021-4562-9M-0036 | Process Datasheet for Open Drain Caisson Pump | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-09-04 | 2025-09-04 | 2025-11-27 |  | 2026-05-06
2021-4549-9M-0037 | Process Datasheet for Seawater Lift Pump | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-08-22 | 2025-08-22 | 2025-11-30 |  | 2026-05-10
2021-4549-9M-0038 | Process Datasheet for Cooling Water Circulation Pump | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-08-23 | 2025-08-23 | 2025-12-02 |  | 2026-05-11
2021-4525-9M-0040 | Process Datasheet for Compressor Discharge Cooler | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-08-04 | 2025-08-04 | 2025-11-18 |  | 2026-04-30
2021-4526-9M-0041 | Process Datasheet for Gas Compressor Suction Cooler | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-08-04 | 2025-08-04 | 2025-11-18 |  | 2026-04-30
2021-4561-9M-0045 | Process Datasheet for Closed Drain Vessel Heater | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-09-17 | 2025-10-03 16:59 | 2025-10-01 | 2025-10-10 | 2026-02-17 |  | 2026-06-23
2021-4543-9M-0046 | Process Datasheet for HP Flare Scrubber Heater | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-09-15 | 2025-10-03 16:59 | 2025-10-01 | 2025-10-10 | 2026-02-17 |  | 2026-06-23
2021-4549-9M-0048 | Process Datasheet for Seawater / Cooling Water Exchanger | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-08-22 | 2025-08-22 | 2025-11-30 |  | 2026-05-09
2021-4557-9M-0049 | Process Datasheet for Fuel Gas Pre-Cooler | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-07-03 | 2025-07-03 | 2025-11-22 | 2025-09-06 | 2026-05-04
2021-4557-9M-0050 | Process Datasheet for Fuel Gas Scrubber | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-06 | 2025-07-06 | 2025-08-14 | 2025-08-14 | 2025-11-24 |  | 2026-05-06
2021-4557-9M-0051 | Process Datasheet for Fuel Gas Filter | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-06 | 2025-07-06 | 2025-07-03 | 2025-07-03 | 2025-11-24 |  | 2026-05-06
2021-4557-9M-0052 | Process Datasheet for Fuel Gas Superheater | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-07-03 | 2025-07-03 | 2025-11-24 |  | 2026-05-06
2021-4549-9M-0053 | Process Datasheet for Seawater Filter Package | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-03 | 2025-07-03 | 2025-12-02 |  | 2026-05-12
2021-4549-9M-0054 | Process Datasheet for Cooling Water Filter | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-04 | 2025-07-04 | 2025-07-03 | 2025-07-03 | 2025-12-02 |  | 2026-05-11
2021-4526-9M-0060 | Process Datasheet for Gas Compressor | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-03 | 2025-07-31 | 2025-07-31 | 2026-04-09
2021-4525-9M-0070 | Process Datasheet for Gas Dehydration Unit | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-03 | 2025-08-12 | 2025-08-12 | 2025-10-31 |  | 2026-04-14
2021-4541-9M-0071 | Process Datasheet for Gas Mercury Adsorption Package | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-07-04 | 2025-07-04 | 2025-08-12 | 2025-08-12 | 2025-10-31 |  | 2026-04-14
2021-4541-9M-0072 | Process Datasheet for Hypochlorite Generation Package | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-08-05 | 2025-08-05 | 2025-07-31 | 2025-07-31 | 2025-11-27 |  | 2026-05-05
2021-4557-9M-0074 | Process Datasheet for Chemical Injection Package | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-08-29 | 2025-09-05 18:31 | 2025-09-05 | 2025-09-05 | 2025-11-23 |  | 2026-05-04
2021-4564-9M-0076 | Process Datasheet for Instrument Air compressor and Instrument Air Dryer Package | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-08-16 | 2025-08-16 | 2025-07-23 | 2025-09-30 | 2025-11-22 |  | 2026-05-06
2021-4550-9M-0077 | Process Datasheet for Nitrogen Generator Package | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-12 | 2025-09-30 | 2025-11-21 |  | 2026-05-04
2021-4500-9M-0080 | Process Datasheet for Control Valve | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-09-04 | 2025-09-04 | 2025-09-26 |  | 2026-04-01
2021-4500-9M-0081 | Process Datasheet for Relief Valves | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-09-16 | 2025-09-18 17:13 | 2025-09-26 | 2025-10-03 | 2025-12-04 |  | 2026-05-13
2021-4530-9M-0082 | Process Datasheet for Sales Gas Metering | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-03 | 2025-07-03 | 2025-08-08 | 2025-08-08 | 2026-04-14
2021-4562-9M-0047 | PROCESS DATASHEET FOR HAZARDOUS OPEN DRAIN TANK HEATER | PR | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-04 | 2025-07-04 | 2025-11-29 |  | 2026-05-08
2021-4500-9U-0001 | Process Line List for CGF | PR | Register | 2025-06-28 | 2025-06-28 | 2025-09-15 | 2025-09-15 11:09 | 2025-09-17 | 2025-09-15 | 2026-01-24 |  | 2026-05-26
2021-4500-00-0001 | Drawing Index | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4500-01-0001-1 | P&ID Symbols Abbreviations & Legend Typical P&ID Piping Arrangements Details | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-31 | 2025-07-31 | 2026-01-05 |  | 2026-05-12
2021-4500-01-0001-2 | P&ID Symbols Abbreviations & Legend Typical P&ID Piping Arrangements Details | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-31 | 2025-07-31 | 2026-01-05 |  | 2026-05-12
2021-4500-01-0001-3 | P&ID Symbols Abbreviations & Legend Typical P&ID Piping Arrangements Details | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-31 | 2025-07-31 | 2026-01-05 |  | 2026-05-12
2021-4500-01-0001-4 | P&ID Symbols Abbreviations & Legend Typical P&ID Piping Arrangements Details | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-31 | 2025-07-31 | 2026-01-05 |  | 2026-05-12
2021-4500-01-0001-5 | P&ID Symbols Abbreviations & Legend Typical P&ID Piping Arrangements Details | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-31 | 2025-07-31 | 2026-01-05 |  | 2026-05-12
2021-4500-01-0001-6 | P&ID Symbols Abbreviations & Legend Typical P&ID Piping Arrangements Details | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-31 | 2025-07-31 | 2026-01-05 |  | 2026-05-12
2021-4500-01-0001-7 | P&ID Symbols Abbreviations & Legend Typical P&ID Piping Arrangements Details | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-07-31 | 2025-07-31 | 2026-01-05 |  | 2026-05-12
2021-4500-01-0001-8 | P&ID Symbols Abbreviations & Legend Typical P&ID Piping Arrangements Details | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-31 | 2025-07-31 | 2026-01-05 |  | 2026-05-12
2021-4500-01-0001-9 | P&ID Symbols Abbreviations & Legend Typical P&ID Piping Arrangements Details | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-31 | 2025-07-31 | 2026-01-05 |  | 2026-05-12
2021-4500-03-0101 | Heat and Material Balance Case 1 - Early Year without CGF Production | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-03 | 2025-07-03 | 2025-08-08 | 2025-08-08 | 2026-03-18
2021-4500-03-0102 | Heat and Material Balance Case 2 - Early Year with CGF Production | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-03 | 2025-07-03 | 2025-08-08 | 2025-08-08 | 2026-03-18
2021-4500-03-0103 | Heat and Material Balance Case 3 - Maximum Condensate Production | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-03 | 2025-07-03 | 2025-08-08 | 2025-08-08 | 2026-03-18
2021-4500-03-0104 | Heat and Material Balance Case 4 - Late Year with WHP-C and PIP in HP Mode | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-03 | 2025-07-03 | 2025-08-08 | 2025-08-08 | 2026-03-18
2021-4500-03-0105 | Heat and Material Balance Case 5 - Late Year with WHP-C and PIP in LP Mode | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-07-03 | 2025-07-03 | 2025-08-08 | 2025-08-08 | 2026-03-18
2021-4528-03-0201 | Process Flow Diagram Wellhead, Flowlines, Headers and Test Separator | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-07-03 | 2025-07-03 | 2025-09-10 | 2025-09-08 | 2026-04-28
2021-4525-03-0202 | Process Flow Diagram Gas And Liquid Separation System | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-07-03 | 2025-07-03 | 2025-09-10 | 2025-09-08 | 2026-04-28
2021-4526-03-0203 | Process Flow Diagram Gas Compression System | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-07-03 | 2025-07-03 | 2025-09-10 | 2025-09-08 | 2026-04-28
2021-4525-03-0204 | Process Flow Diagram Mercury Adsorption Unit | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-07-03 | 2025-07-03 | 2025-09-10 | 2025-09-08 | 2026-04-28
2021-4524-03-0205 | Process Flow Diagram Gas Dehydration And Glycol Regeneration System | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-07-03 | 2025-07-03 | 2025-09-10 | 2025-09-08 | 2026-04-28
2021-4530-03-0208 | Process Flow Diagram Metering Launcher And Export | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-07-03 | 2025-07-03 | 2025-09-10 | 2025-09-08 | 2026-04-28
2021-4542-03-0220 | Utility Flow Diagram Chemical Injection System | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-09-10 10:34 | 2025-11-15 | 2025-09-10 | 2025-12-09 |  | 2026-04-28
2021-4543-03-0221 | Utility Flow Diagram HP/LP Flare System | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-09-10 10:34 | 2025-11-15 | 2025-09-10 | 2025-12-09 |  | 2026-04-28
2021-4549-03-0222 | Utility Flow Diagram Seawater / Cooling Water System | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-09-10 10:34 | 2025-11-15 | 2025-09-10 | 2025-12-09 |  | 2026-04-28
2021-4561-03-0223 | Utility Flow Diagram Open and Closed Drain System | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-09-10 10:34 | 2025-11-15 | 2025-09-10 | 2025-12-09 |  | 2026-04-28
2021-4564-03-0224 | Utility Flow Diagram Instrument / Utility And Nitrogen System | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-09-10 10:34 | 2025-11-15 | 2025-09-10 | 2025-12-09 |  | 2026-04-28
2021-4570-03-0225 | Utility Flow Diagram Power Generation System | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-09-10 10:34 | 2025-11-15 | 2025-09-10 | 2025-12-09 |  | 2026-04-28
2021-4557-03-0226 | Utility Flow Diagram Fuel Gas System | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-09-10 10:34 | 2025-11-15 | 2025-09-10 | 2025-12-09 |  | 2026-04-28
2021-4520-01-0201 | Piping and Instrumentation Diagram Production Header | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4520-01-0202 | Piping and Instrumentation Diagram Test Header | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4524-01-0201 | Piping and Instrumentation Diagram Glycol Contactor | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4524-01-0202 | Piping and Instrumentation Diagram Dehydrated Gas Coalescer | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4525-01-0201 | Piping and Instrumentation Diagram Production Separator | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4525-01-0205 | Piping and Instrumentation Diagram Mercury Adsorption Package (Sheet 1) | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4525-01-0206 | Piping and Instrumentation Diagram Mercury Adsorption Package (Sheet 2) | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4526-01-0201 | Piping and Instumentation Diagram Gas Inlet Cooler A | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4526-01-0202 | Piping and Instrumentation Diagram Gas Compressor Suction Scrubber A | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4526-01-0203 | Piping and Instrumentation Diagram Gas Compressor A | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4526-01-0204 | Piping and Instrumentation Diagram Gas Compressor Gas Turbine A | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4526-01-0205 | Piping and Instrumentation Diagram Gas Inlet Cooler B | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4526-01-0206 | Piping and Instrumentation Diagram Gas Compressor Suction Scrubber B | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4526-01-0207 | Piping and Instrumentation Diagram Gas Compressor B | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4526-01-0208 | Piping and Instrumentation Diagram Gas Compressor Gas Turbine B | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4527-01-0201 | Piping and Instrumentation Diagram Test Separator | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4528-01-0201-01 | Piping and Instrumentation Diagram Production Wellheads QAY-2882 | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4552-01-0201 | Piping and Instrumentation Diagram Wellhead Control Panel and HPU | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4530-01-0201 | Piping and Instrumentation Diagram Sales Gas Metering | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4530-01-0202 | Piping and Instrumentation Diagram Sales Gas Launcher | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4541-01-0201 | Piping and Instrumentation Diagram Hypochlorite Generator Package | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4542-01-0201 | Piping and Instrumentation Diagram Chemical Injection Package (Sheet 1) | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4542-01-0202 | Piping and Instumentation Diagram Chemical Injection Package (Sheet 2) | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4542-01-0203 | Piping and Instrumentation Diagram Chemical Injection Package (sheet 3) | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4543-01-0201 | Piping and Instrumentation Diagram HP Flare Scrubber and Heater | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4543-01-0203 | Piping and Instrumentation Diagram HP Flare Scrubber Pumps | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4543-01-0251 | Piping and Instrumentation Diagram HP Flare Header | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4544-01-0251 | Piping and Instrumentation Diagram LP Flare Header | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4547-01-0201 | Piping and Instrumentation Diagram Glycol Regeneration Package Glycol Flash Vessel and Filters | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4547-01-0202 | Piping and Instrumentation Diagram Glycol Regeneration Package Glycol Reboiler | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4547-01-0203 | Piping and Instrumentation Diagram Glycol Regeneration Package Glycol Surge Drum and Pumps | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4547-01-0204 | Piping and Instrumentation Diagram Glycol Regeneration Package Chemical Injection | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4549-01-0201 | Piping and Instrumentation Diagram Cooling Water Circulation Pump and Filter | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4549-01-0202 | Piping and Instrumentation Diagram Cooling Water Expansion Vessel | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4549-01-0203 | Piping and Instrumentation Diagram Seawater/Cooling Water Exchanger | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4549-01-0204 | Piping and Instrumentation Diagram Seawater Filter Package | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4549-01-0205 | Piping and Instrumentation Diagram Seawater Lift Pump & Caisson | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4549-01-0206 | Piping and Instrumentation Diagram Overboard Dump Caisson | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4549-01-0251 | Piping and Instrumentation Diagram Cooling Water Header | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4550-01-0251 | Piping and Instrumentation Diagram Nitrogen Distribution Header | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4557-01-0201 | Piping and Instrumentation Diagram Fuel Gas Scrubber | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4557-01-0202 | Piping and Instrumentation Diagram Fuel Gas Filter | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4557-01-0203 | Piping and Instrumentation Diagram Fuel Gas Superheater | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4560-01-0251 | Piping and Instrumentation Diagram Non-Hazardous Open Drain Header | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4561-01-0201 | Piping and Instrumentation Diagram Closed Drain Vessel & Heater | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4561-01-0202 | Piping and Instrumentation Diagram Closed Drain Pumps | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4561-01-0251 | Piping and Instrumentation Diagram Closed Drain Header | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4562-01-0201 | Piping and Instumentation Diagram Hazardous Open Drain Tank Heater and Pump | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4562-01-0202 | Piping and Instrumentation Diagram Hazardous Open Drain Caisson and Pump | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4562-01-0251 | Piping and Instrumentation Diagram Hazardous Open Drain Header | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4564-01-0201 | Piping and Instrumentation Diagram Instrument Air Compressor Package | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4564-01-0202 | Piping and Instrumentation Diagram Instrument Air Dryer Package | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4564-01-0203 | Piping and Instrumentation Diagram Instrument Air Receiver | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4550-01-0201 | Piping and Instrumentation Diagram Nitrogen Generator and Receiver | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4564-01-0204 | Piping and Instrumentation Diagram Utility Air Receiver | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4564-01-0251 | Piping and Instrumentation Diagram Utility Air Distribution Header | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4564-01-0261 | Piping and Instrumentation Diagram Instrument Air Distribution Header | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4566-01-0251 | Piping and Instrumentation Diagram Utility Water and Service Water Distribution Header | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4570-01-0201 | Piping and Instumentation Diagram Gas Turbine Generator Packages | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-09 | 2025-07-09 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4571-01-0201 | Piping and Instrumentation Diagram Emergency Diesel Generator | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-07 | 2025-07-07 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4597-01-0201 | Piping and Instrumentation Diagram Bridge (ST-CGF and ST-PIP) | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4506-47-0501 | Shutdown Hierarchy Summary | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-09-04 | 2025-09-04 | 2026-01-17 |  | 2026-05-05
2021-4506-41-0502 | Process Cause and Effect Diagram | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-09-15 | 2025-09-15 11:09 | 2025-09-18 | 2025-09-15 | 2026-01-24 |  | 2026-05-12
2021-4506-41-0503 | SAFE Chart | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-26 | 2025-07-26 13:44 | 2025-09-16 | 2025-09-22 | 2026-01-31 |  | 2026-05-12
2021-4528-04-0601 | Safety Flow Diagram Wellhead Flowline Headers and Test Separator | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-09-05 | 2025-09-05 | 2026-01-17 |  | 2026-05-19
2021-4525-04-0602 | Safety Flow Diagram Gas And Liquid Separation System | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-09-05 | 2025-09-05 | 2026-01-17 |  | 2026-05-19
2021-4526-04-0603 | Safety Flow Diagram Gas Compression | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-09-05 | 2025-09-05 | 2026-01-17 |  | 2026-05-19
2021-4525-04-0604 | Safety Flow Diagram Mercury Adsorption Unit | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-09-05 | 2025-09-05 | 2026-01-17 |  | 2026-05-19
2021-4524-04-0605 | Safety Flow Diagram Gas Dehydration And Glycol Regeneration System | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-09-05 | 2025-09-05 | 2026-01-17 |  | 2026-05-19
2021-4530-04-0608 | Safety Flow Diagram Metering Launcher And Export | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-09-05 | 2025-09-05 | 2026-01-17 |  | 2026-05-19
2021-4542-04-0621 | Safety Flow Diagram Chemical Injection System | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-09-05 | 2025-09-05 | 2026-01-17 |  | 2026-05-19
2021-4543-04-0622 | Safety Flow Diagram HP/LP Flare System | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-09-05 | 2025-09-05 | 2026-01-17 |  | 2026-05-19
2021-4549-04-0623 | Safety Flow Diagram Seawater / Cooling Water System | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-09-05 | 2025-09-05 | 2026-01-17 |  | 2026-05-19
2021-4561-04-0624 | Safety Flow Diagram Open and Closed Drain System | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-11 | 2025-07-11 | 2025-09-05 | 2025-09-05 | 2026-01-17 |  | 2026-05-19
2021-4564-04-0625 | Safety Flow Diagram Instrument / Utility And Nitrogen System | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-07-23 | 2025-07-23 | 2025-09-05 | 2025-09-05 | 2026-01-17 |  | 2026-05-19
2021-4570-04-0626 | Safety Flow Diagram Power Generation System | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-29 | 2025-09-05 18:31 | 2025-09-05 | 2025-09-05 | 2026-01-17 |  | 2026-05-19
2021-4557-04-0627 | Safety Flow Diagram Fuel Gas System | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-29 | 2025-09-05 16:13 | 2025-09-05 | 2025-09-05 | 2026-01-17 |  | 2026-05-19
2021-4528-05-0201 | Material Selection Diagram Wellhead, Flowlines, Headers and Test Separator | MAT | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-13 | 2025-09-17 14:19 | 2025-09-28 | 2025-09-17 | 2025-12-24 |  | 2026-05-12
2021-4525-05-0202 | Material Selection Diagram Gas And Liquid Separation System | MAT | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-13 | 2025-09-17 14:19 | 2025-09-28 | 2025-09-17 | 2025-12-24 |  | 2026-05-12
2021-4526-05-0203 | Material Selection Diagram Gas Compression System | MAT | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-13 | 2025-09-17 14:19 | 2025-09-28 | 2025-09-17 | 2025-12-24 |  | 2026-05-12
2021-4525-05-0204 | Material Selection Diagram Mercury Adsorption Unit | MAT | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-13 | 2025-09-17 14:19 | 2025-09-28 | 2025-09-17 | 2025-12-24 |  | 2026-05-12
2021-4524-05-0205 | Material Selection Diagram Gas Dehydration And Glycol Regeneration System | MAT | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-13 | 2025-09-17 14:15 | 2025-09-28 | 2025-09-17 | 2025-12-24 |  | 2026-05-12
2021-4530-05-0208 | Material Selection Diagram Metering Launcher And Export | MAT | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-13 | 2025-09-17 14:19 | 2025-09-28 | 2025-09-17 | 2025-12-24 |  | 2026-05-12
2021-4542-05-0220 | Material Selection Diagram Chemical Injection System | MAT | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-13 | 2025-09-17 16:57 | 2025-09-28 | 2025-09-17 | 2025-12-24 |  | 2026-05-12
2021-4543-05-0221 | Material Selection Diagram HP/LP Flare System | MAT | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-13 | 2025-09-17 16:57 | 2025-09-28 | 2025-09-17 | 2025-12-24 |  | 2026-05-12
2021-4549-05-0222 | Material Selection Diagram Seawater / Cooling Water System | MAT | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-13 | 2025-09-17 16:57 | 2025-09-28 | 2025-09-17 | 2025-12-24 |  | 2026-05-12
2021-4561-05-0223 | Material Selection Diagram Open and Closed Drain System | MAT | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-13 | 2025-09-17 16:57 | 2025-09-28 | 2025-09-17 | 2025-12-24 |  | 2026-05-12
2021-4564-05-0224 | Material Selection Diagram Instrument / Utility And Nitrogen System | MAT | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-13 | 2025-09-17 16:57 | 2025-09-26 | 2025-09-17 | 2025-12-24 |  | 2026-05-12
2021-4570-05-0225 | Material Selection Diagram Power Generation System | MAT | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-13 | 2025-09-17 16:57 | 2025-09-28 | 2025-09-17 | 2025-12-24 |  | 2026-05-12
2021-4557-05-0226 | Material Selection Diagram Fuel Gas System | MAT | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-13 | 2025-09-17 16:57 | 2025-09-28 | 2025-09-17 | 2025-12-24 |  | 2026-05-12
2021-4500-1L-5002 | Painting and Coating Specification | MAT | Specification | 2025-06-28 | 2025-06-28 | 2025-07-19 | 2025-07-19 | 2025-07-26 | 2025-07-26 | 2025-10-16 | 2025-09-12 | 2026-03-20
2021-4500-1L-5003 | Insulation & Personnel Protection Specification | MAT | Specification | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-10-16 |  | 2026-03-20
2021-4500-1L-5007 | Specification for Thermally Sprayed Aluminum Coatings | MAT | Specification | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-09-26 | 2025-10-09 | 2026-03-18
2021-4500-1L-5008 | Baseline Corrosion Survey Specifciation (new) | MAT | Specification | 2025-08-14 | 2025-08-14 | 2025-10-28 |  | 2025-11-10 |  | 2026-02-18 |  | 2026-04-24
2021-4500-5H-0001 | HSE Philosophy & Basis of Design | TS | Narratives | 2025-06-28 | 2025-06-28 | 2025-07-12 | 2025-07-19 10:51 | 2025-07-19 | 2025-07-19 | 2025-12-15 |  | 2026-05-14
2021-4500-5H-0002 | Hazardous Area Schedule & Report | TS | Narratives | 2025-06-28 | 2025-06-28 | 2025-07-07 | 2025-07-07 10:10 | 2025-09-20 | 2025-09-24 | 2026-01-31 |  | 2026-06-05
2021-4580-5J-0001 | ST-CGF Fire Water Demand Calculation Note | TS | Calculation | 2025-06-28 | 2025-06-28 | 2025-07-18 | 2025-07-18 07:47 | 2025-09-30 | 2025-10-01 | 2026-02-05 |  | 2026-06-16
2021-4580-5J-0002 | ST-CGF Fire Water System Hydraulic Analysis | TS | Calculation | 2026-01-12 |  | 2026-03-03 |  | 2026-03-13 |  | 2026-06-26 |  | 2026-07-27
2021-4580-5J-0003 | ST-CGF Deluge Nozzle Arrangment and System Calculation Report | TS | Calculation | 2025-06-28 | 2025-06-28 | 2025-08-04 | 2025-08-04 07:27 | 2025-10-14 |  | 2026-02-12 |  | 2026-06-30
2021-4500-5K-0006 | ST-CGF HAZOP Close-Out Report | TS | Special Studies | 2025-12-08 |  | 2026-02-06 |  | 2026-02-27 |  |  |  | 2026-06-12
2021-4500-5K-0007 | ST-CGF HAZID Close-out Report | TS | Special Studies | 2025-10-20 |  | 2026-01-28 |  | 2026-02-11 |  |  |  | 2026-06-18
2021-4500-5K-0004 | ST-CGF HAZOP Study Report | TS | Special Studies | 2025-10-29 |  | 2025-12-08 |  | 2025-12-22 |  | 2026-01-21 |  | 2026-02-20
2021-4500-5K-0005 | ST-CGF HAZID Study Report | TS | Special Studies | 2025-10-01 | 2025-10-01 | 2025-10-20 |  | 2025-10-27 |  | 2025-11-26 |  | 2025-12-26
2021-4500-5K-0026 | ST-CGF SIL Classification report | TS | Special Studies | 2025-10-29 |  | 2025-12-15 |  | 2025-12-29 |  | 2026-01-28 |  | 2026-02-27
2021-4500-5K-0002 | ST-CGF SIL Verification report | TS | Special Studies | 2025-12-28 |  | 2026-02-26 |  | 2026-03-12 |  | 2026-05-11 |  | 2026-07-10
2021-4500-5K-0003 | ST-CGF Noise Study Report | TS | Special Studies | 2025-12-01 |  | 2026-01-28 |  | 2026-02-11 |  | 2026-04-22 |  | 2026-07-13
2021-4500-5K-0022 | ST-CGF Simultaneous Operations and Matrix of Permitted Operations (SIMOPS & MOPO) Study | TS | Special Studies | 2026-03-02 |  | 2026-03-23 |  | 2026-03-30 |  | 2026-04-29 |  | 2026-05-29
2021-4500-5K-0023 | ST-CGF Safety Critical Elements and Performance Standards | TS | Special Studies | 2025-12-01 |  | 2026-02-14 |  | 2026-03-07 |  | 2026-05-16 |  | 2026-07-15
2021-4500-5K-0024 | Su Tu Trang Phase 2 Design Safety Case Studies Report ( For complex platforms including ST-CGF, ST-PIP, WHP-C and ST- LQ) | TS | Special Studies | 2025-12-01 |  | 2026-03-22 |  | 2026-04-04 |  | 2026-05-27 |  | 2026-08-26
2021-4500-5K-0025 | ST-CGF SIL Close-out Report | TS | Special Studies | 2025-12-15 |  | 2026-02-13 |  | 2026-02-27 |  |  |  | 2026-05-28
2021-4581-5L-0001 | Firefighting Equipment Specification & Datasheet | TS | Specification | 2025-07-15 | 2025-07-15 | 2025-08-15 | 2025-08-22 19:11 | 2025-08-22 | 2025-08-22 | 2025-12-19 |  | 2026-07-15
2021-4585-5L-0001 | Life Saving & Safety Equipment Specifications & Datasheets | TS | Specification | 2025-07-15 | 2025-07-15 | 2025-08-15 | 2025-08-15 | 2025-08-22 | 2025-08-22 | 2025-12-19 |  | 2026-07-15
2021-4584-5L-0001 | FM-200 System Specification & Datasheet | IN | Specification | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-03 | 2025-08-22 | 2025-08-22 | 2025-11-25
2021-4590-5L-0001 | Passive Fire Protection Specification | TS | Specification | 2026-01-15 |  | 2026-02-05 |  | 2026-02-26 |  | 2026-03-28 |  | 2026-07-16
2021-4585-5L-0002 | Safety Signs Specification | TS | Specification | 2025-07-01 | 2025-07-01 | 2025-08-15 | 2025-08-22 19:11 | 2025-08-22 | 2025-08-22 | 2026-01-19 |  | 2026-07-15
2021-4500-5K-0018 | HSE Issues Register | TS | Register | 2026-01-07 |  | 2026-04-07 |  | 2026-04-28 |  |  |  | 2026-09-04
2021-4581-5U-0001 | ST-CGF Firefighting, Life Saving & Safety Equipment List | TS | Register | 2025-09-15 | 2025-09-15 | 2025-09-22 | 2025-09-24 15:44 | 2025-10-08 | 2025-10-02 | 2026-01-31 |  | 2026-07-14
2021-4580-5U-0001 | ST-CGF Firewater System Line List | TS | Register | 2025-08-07 | 2025-08-07 | 2025-10-28 |  | 2025-11-04 |  | 2026-03-05 |  | 2026-07-14
2021-4500-5K-0001 | SoW for HAZID, HAZOP & SIL Classification Study | TS | Contractors | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-03 |  |  | 2025-07-14 | 2025-07-14
2021-4500-5K-0014 | SoW for Safety Studies | TS | Contractors | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-03 |  |  | 2025-08-08 | 2025-08-08
2021-4581-5W-0001 | Technical Requisition for Fire Fighting Equipment | TS | Procurement | 2025-12-06 |  | 2025-12-21 |  | 2025-12-31 |  | 2026-01-31 |  | 2026-06-09
2021-4585-5W-0001 | Technical Requisition for Life Saving Equipment | TS | Procurement | 2025-12-06 |  | 2025-12-21 |  | 2025-12-31 |  | 2026-01-31 |  | 2026-06-09
2021-4585-5W-0002 | Technical Requisition for Safety Sign | TS | Procurement | 2026-02-14 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-04-11 |  | 2026-08-18
2021-4500-5W-0001 | Technical Bid Evaluation for HAZID, HAZOP & SIL Clasification Study | TS | Procurement | 2025-07-01 | 2025-07-01 | 2025-08-22 | 2025-08-22 | 2025-08-29 | 2025-08-29 |  |  | 2025-09-25 | 2025-09-10
2021-4500-5W-0002 | Technical Bid Evaluation for Safety Studies | TS | Procurement | 2025-08-15 | 2025-08-15 | 2025-10-17 |  | 2025-10-24 |  |  |  | 2025-11-14
2021-4581-5W-0002 | Technical Bid Evaluation for Fire Fighting Equipment | TS | Procurement | 2026-03-14 |  | 2026-04-23 |  | 2026-04-28 |  |  |  | 2026-05-15
2021-4585-5W-0003 | Technical Bid Evaluation for Life Saving Equipment | TS | Procurement | 2026-03-14 |  | 2026-04-23 |  | 2026-04-28 |  |  |  | 2026-05-15
2021-4585-5W-0004 | Technical Bid Evaluation for Safety Sign | TS | Procurement | 2026-05-23 |  | 2026-07-02 |  | 2026-07-07 |  |  |  | 2026-07-24
2021-4581-5V-0001 | Bid Evaluation Criteria for Fire Fighting Equipment | TS | Bid | 2025-12-06 |  | 2025-12-21 |  | 2025-12-31 |  |  |  | 2026-01-31
2021-4585-5V-0002 | Bid Evaluation Criteria for Life Saving Equipment | TS | Bid | 2025-12-06 |  | 2025-12-21 |  | 2025-12-31 |  |  |  | 2026-01-31
2021-4585-5V-0003 | Bid Evaluation Criteria for Safety Sign | TS | Bid | 2026-02-14 |  | 2026-03-01 |  | 2026-03-11 |  |  |  | 2026-04-11
2021-4580-03-0001 | Utility Flow Diagram Firewater System | TS | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-15 | 2025-08-15 13:34 | 2025-09-30 | 2025-09-26 | 2026-02-05 |  | 2026-06-16
2021-4580-05-0004 | ST-CGF P&ID Firewater Ringmain Distribution | TS | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-20 | 2025-09-10 07:25 | 2025-10-14 | 2025-10-14 | 2026-02-12 |  | 2026-06-30
2021-4580-05-0005 | P&ID Deluge System for ST-CGF and Bridge | TS | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-20 | 2025-08-20 11:05 | 2025-10-14 | 2025-10-14 | 2026-02-12 |  | 2026-06-30
2021-4585-07-0001 | Fire Fighting, Safety Equipment & Escape Route Layout index | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-15 | 2025-09-19 09:58 | 2025-09-24 | 2025-09-25 | 2026-01-31 |  | 2026-06-30
2021-4585-07-0002 | Fire Fighting, Safety Equipment & Escape Route Layout Maindeck | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-15 | 2025-09-19 10:04 | 2025-09-24 | 2025-09-25 | 2026-01-31 |  | 2026-06-30
2021-4585-07-0003 | Fire Fighting, Safety Equipment & Escape Route Layout Intermediate Deck | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-15 | 2025-09-19 10:08 | 2025-09-24 | 2025-09-25 | 2026-01-31 |  | 2026-06-30
2021-4585-07-0004 | Fire Fighting, Safety Equipment & Escape Route Layout E-House | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-15 | 2025-09-19 10:16 | 2025-09-24 | 2025-09-25 | 2026-01-31 |  | 2026-06-30
2021-4585-07-0005 | Fire Fighting, Safety Equipment & Escape Route Layout Cellar Deck | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-15 | 2025-09-19 10:11 | 2025-09-24 | 2025-09-25 | 2026-01-31 |  | 2026-06-30
2021-4585-07-0006 | Fire Fighting, Safety Equipment & Escape Route Layout - Sub Cellar Deck | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-15 | 2025-09-19 10:13 | 2025-09-24 | 2025-09-25 | 2026-01-31 |  | 2026-06-30
2021-4585-07-0007 | Fire Fighting, Safety Equipment & Escape Route Layout - Top of Jacket Walkway | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-15 | 2025-09-19 09:56 | 2025-09-24 | 2025-09-25 | 2026-01-31 |  | 2026-06-30
2021-4585-07-0008 | Safety Sign Layout Drawing Index | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-29 | 2025-10-03 14:05 | 2025-10-08 | 2025-10-09 | 2026-03-09 |  | 2026-07-14
2021-4585-07-0011 | Safety Sign Layout E-House | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-29 | 2025-10-03 14:08 | 2025-10-08 | 2025-10-09 | 2026-03-09 |  | 2026-07-14
2021-4585-07-0012 | Safety Sign Layout Cellar Deck | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-29 | 2025-10-03 14:09 | 2025-10-08 | 2025-10-09 | 2026-03-09 |  | 2026-07-14
2021-4585-07-0009 | Safety Sign Layout Main Deck | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-29 | 2025-10-03 14:06 | 2025-10-08 | 2025-10-09 | 2026-03-09 |  | 2026-07-14
2021-4585-07-0013 | Safety Sign Layout Sub Cellar Deck | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-29 | 2025-10-03 14:11 | 2025-10-08 | 2025-10-09 | 2026-03-09 |  | 2026-07-14
2021-4585-07-0014 | Safety Sign Layout Top of Jacket Walkway | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-29 | 2025-10-03 14:12 | 2025-10-08 | 2025-10-09 | 2026-03-09 |  | 2026-07-14
2021-4585-07-0010 | Safety Sign Layout Intermediate Deck | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-29 | 2025-10-03 14:06 | 2025-10-08 | 2025-10-09 | 2026-03-09 |  | 2026-07-14
2021-4585-31-0001 | Hazardous Area Classification Layout Drawing Index | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-22 | 2025-09-26 11:37 | 2025-10-01 | 2025-09-26 | 2026-03-02 |  | 2026-07-07
2021-4585-31-0002 | Hazardous Area Classification Layout Maindeck | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-22 | 2025-09-26 11:37 | 2025-10-01 | 2025-09-26 | 2026-03-02 |  | 2026-07-07
2021-4585-31-0003 | Hazardous Area Classification Layout Intermediate Deck | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-22 | 2025-09-26 11:37 | 2025-10-01 | 2025-09-26 | 2026-03-02 |  | 2026-07-07
2021-4585-31-0004 | Hazardous Area Classification Layout E-House | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-22 | 2025-09-26 11:37 | 2025-10-01 | 2025-09-26 | 2026-03-02 |  | 2026-07-07
2021-4585-31-0005 | Hazardous Area Classification Layout Cellar Deck | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-22 | 2025-09-26 11:37 | 2025-10-01 | 2025-09-26 | 2026-03-02 |  | 2026-07-07
2021-4585-31-0006 | Hazardous Area Classification Layout Sub Cellar Deck | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-22 | 2025-09-26 11:37 | 2025-10-01 | 2025-09-26 | 2026-03-02 |  | 2026-07-07
2021-4585-31-0007 | Hazardous Area Classification Layout Top of Jacket Walkaway | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-22 | 2025-09-26 11:37 | 2025-10-01 | 2025-09-26 | 2026-03-02 |  | 2026-07-07
2021-4585-31-0010 | Hazardous Area Classification Layout Elevation Looking North | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-22 | 2025-09-26 11:37 | 2025-10-01 | 2025-09-26 | 2026-03-02 |  | 2026-07-07
2021-4585-31-0009 | Hazardous Area Classification Layout Elevation Looking South | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-22 | 2025-09-26 11:37 | 2025-10-01 | 2025-09-26 | 2026-03-02 |  | 2026-07-07
2021-4585-31-0008 | Hazardous Area Classification Layout Elevation Looking East | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-22 | 2025-09-26 11:37 | 2025-10-01 | 2025-09-26 | 2026-03-02 |  | 2026-07-07
2021-4585-31-0011 | Hazardous Area Classification Layout Elevation Looking West | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-22 | 2025-09-26 11:37 | 2025-10-01 | 2025-09-26 | 2026-03-02 |  | 2026-07-07
2021-4585-31-0012 | Hazardous Area Classification Layout Maindeck (SIMOPS) | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-22 | 2025-09-26 11:37 | 2025-10-01 | 2025-09-26 | 2026-03-02 |  | 2026-07-07
2021-4585-31-0013 | Hazardous Area Classification Layout Intermediate Deck (SIMOPS) | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-22 | 2025-09-26 11:37 | 2025-10-01 | 2025-09-26 | 2026-03-02 |  | 2026-07-07
2021-4585-31-0014 | Hazardous Area Classification Layout E-House (SIMOPS) | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-22 | 2025-09-26 11:37 | 2025-10-01 | 2025-09-26 | 2026-03-02 |  | 2026-07-07
2021-4585-31-0015 | Hazardous Area Classification Layout Cellar Deck (SIMOPS) | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-22 | 2025-09-26 11:37 | 2025-10-01 | 2025-09-26 | 2026-03-02 |  | 2026-07-07
2021-4585-31-0016 | Hazardous Area Classification Layout Sub Cellar Deck (SIMOPS) | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-22 | 2025-09-26 11:37 | 2025-10-01 | 2025-09-26 | 2026-03-02 |  | 2026-07-07
2021-4585-31-0017 | Hazardous Area Classification Layout Top of Jacket Walkaway (SIMOPS) | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-22 | 2025-09-26 11:37 | 2025-10-01 | 2025-09-26 | 2026-03-02 |  | 2026-07-07
2021-4585-31-0020 | Hazardous Area Classification Layout Elevation Looking North (SIMOPS) | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-22 | 2025-09-26 11:37 | 2025-10-01 | 2025-09-26 | 2026-03-02 |  | 2026-07-07
2021-4585-31-0019 | Hazardous Area Classification Layout Elevation Looking South (SIMOPS) | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-22 | 2025-09-26 11:37 | 2025-10-01 | 2025-09-26 | 2026-03-02 |  | 2026-07-07
2021-4585-31-0018 | Hazardous Area Classification Layout Elevation Looking East (SIMOPS) | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-22 | 2025-09-26 11:37 | 2025-10-01 | 2025-09-26 | 2026-03-02 |  | 2026-07-07
2021-4585-31-0021 | Hazardous Area Classification Layout Elevation Looking West (SIMOPS) | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-22 | 2025-09-26 11:37 | 2025-10-01 | 2025-09-26 | 2026-03-02 |  | 2026-07-07
2021-4585-50-0001 | Fire Zone Layout Drawing Index | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-15 | 2025-09-19 08:53 | 2025-09-22 | 2025-09-24 | 2026-01-31 |  | 2026-06-16
2021-4585-50-0002 | Fire Zone Layout Main Deck | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-15 | 2025-09-19 09:44 | 2025-09-22 | 2025-09-24 | 2026-01-31 |  | 2026-06-16
2021-4585-50-0003 | Fire Zone Layout Intermediate Deck | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-15 | 2025-09-19 09:44 | 2025-09-22 | 2025-09-24 | 2026-01-31 |  | 2026-06-16
2021-4585-50-0004 | Fire Zone Layout E-House | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-15 | 2025-09-19 09:44 | 2025-09-22 | 2025-09-24 | 2026-01-31 |  | 2026-06-16
2021-4585-50-0005 | Fire Zone Layout Cellar Deck | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-15 | 2025-09-19 09:44 | 2025-09-22 | 2025-09-24 | 2026-01-31 |  | 2026-06-16
2021-4585-50-0006 | Fire Zone Layout Sub Cellar Deck | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-15 | 2025-09-19 09:44 | 2025-09-22 | 2025-09-24 | 2026-01-31 |  | 2026-06-16
2021-4585-50-0007 | Fire Zone Layout Top of Jacket Walkaway | TS | Drawing | 2025-07-01 | 2025-07-01 | 2025-09-15 | 2025-09-19 09:44 | 2025-09-22 | 2025-09-24 | 2026-01-31 |  | 2026-06-16
2021-4981-5W-0001 | Technical Requisition for Fire Fighting Equipment (LQM2) | TS | Procurement | 2025-12-05 |  | 2025-12-19 |  | 2025-12-29 |  | 2026-01-28 |  | 2026-06-07
2021-4981-5V-0001 | Bid Evaluation Criteria for Fire Fighting Equipment (LQ &BF) | TS | Bid | 2025-12-05 |  | 2025-12-19 |  | 2025-12-29 |  |  |  | 2026-01-28
2021-4981-5W-0002 | Technical Bid Evaluation for Fire Fighting Equipment (LQ &BF) | TS | Procurement | 2026-03-15 |  | 2026-04-24 |  | 2026-04-29 |  |  |  | 2026-05-13
2021-4985-5W-0001 | Technical Requisition for Life Saving Equipment (LQM2) | TS | Procurement | 2025-12-05 |  | 2025-12-19 |  | 2025-12-29 |  | 2026-01-28 |  | 2026-06-07
2021-4985-5V-0001 | Bid Evaluation Criteria for Life Saving Equipment (LQ &BF) | TS | Bid | 2025-12-05 |  | 2025-12-19 |  | 2025-12-29 |  |  |  | 2026-01-28
2021-4985-5W-0002 | Technical Bid Evaluation for Life Saving Equipment (LQ &BF) | TS | Procurement | 2026-03-15 |  | 2026-04-24 |  | 2026-04-29 |  |  |  | 2026-05-13
2021-4985-5W-0003 | Technical Requisition for Safety Sign Equipment (LQM2) | TS | Procurement | 2026-02-13 |  | 2026-02-27 |  | 2026-03-09 |  | 2026-04-08 |  | 2026-08-16
2021-4985-5V-0002 | Bid Evaluation Criteria for Safety Sign Equipment (LQ &BF) | TS | Bid | 2026-02-13 |  | 2026-02-27 |  | 2026-03-09 |  |  |  | 2026-04-08
2021-4985-5W-0004 | Technical Bid Evaluation for Safety Sign Equipment (LQ &BF) | TS | Procurement | 2026-05-24 |  | 2026-07-03 |  | 2026-07-08 |  |  |  | 2026-07-22
2021-4500-5K-0020 | HAZOP Report for Vendor Package | TS | Special Studies | 2026-02-05 |  | 2026-02-26 |  | 2026-03-05 |  | 2026-06-03 |  | 2026-07-13
2021-4500-5K-0021 | HAZOP Close-Out Report for Vendor Package | TS | Special Studies | 2026-02-26 |  | 2026-04-27 |  | 2026-05-11 |  |  |  | 2026-09-11
2021-4500-5K-0017 | Hazards & Effects Register | TS | Special Studies | 2025-12-01 |  | 2026-01-15 |  | 2026-01-29 |  | 2026-03-30 |  | 2026-05-29
2021-4500-5K-0008 | Assumptions Register | TS | Special Studies | 2025-12-01 |  | 2025-12-31 |  | 2026-01-14 |  | 2026-02-28 |  | 2026-08-30
2021-4500-5K-0009 | Fire & Explosion Risk Analysis (FERA) | TS | Special Studies | 2025-12-01 |  | 2026-01-15 |  | 2026-02-05 |  | 2026-03-07 |  | 2026-07-09
2021-4500-5K-0010 | Non-Hydrocarbon Risk Assessment (NHRA) | TS | Special Studies | 2025-12-01 |  | 2026-01-07 |  | 2026-01-21 |  | 2026-04-15 |  | 2026-07-15
2021-4500-5K-0012 | Escape, Muster, Evacuation & Rescue Analysis (EMERA) | TS | Special Studies | 2025-12-01 |  | 2026-02-05 |  | 2026-02-26 |  | 2026-03-28 |  | 2026-07-30
2021-4586-5K-0001 | Quantitative Risk Assessment (QRA) | TS | Special Studies | 2025-12-01 |  | 2026-03-01 |  | 2026-03-14 |  | 2026-05-06 |  | 2026-08-05
2021-4591-6H-1002 | ST-CGF Topside Structural Basis of Design | ST | Narratives | 2025-07-10 | 2025-07-10 | 2025-08-14 | 2025-08-21 07:55 | 2025-08-21 | 2025-08-21 | 2025-09-30 |  | 2025-10-24
2021-4591-6J-1031 | ST-CGF Topside Computer Model & Load Formulation | ST | Calculation | 2025-06-28 | 2025-06-28 | 2025-09-15 | 2025-09-18 16:09 | 2025-09-29 | 2025-09-26 | 2026-02-16 |  | 2026-06-25
2021-4591-6J-1032 | ST-CGF Topside Yard Jack-up Analysis | ST | Calculation | 2025-08-10 | 2025-08-10 | 2025-12-12 |  | 2025-12-23 |  | 2026-04-06 |  | 2026-06-05
2021-4591-6J-1033 | ST-CGF Topsides Loadout Analysis | ST | Calculation | 2025-08-10 | 2025-08-10 | 2025-11-09 |  | 2025-11-13 |  | 2026-04-06 |  | 2026-06-05
2021-4591-6J-1035 | ST-CGF Topside Transportation Analysis | ST | Calculation | 2025-08-10 | 2025-08-10 | 2025-11-09 |  | 2025-11-19 |  | 2026-04-15 |  | 2026-06-14
2021-4591-6J-1039 | ST-CGF Topside Mating Analysis | ST | Calculation | 2025-08-10 | 2025-08-10 | 2025-10-05 |  | 2025-12-23 |  | 2026-04-15 |  | 2026-06-14
2021-4591-6J-1040 | ST-CGF Topside Inplace Analysis | ST | Calculation | 2025-08-10 | 2025-08-10 | 2025-10-03 | 2025-10-08 09:48 | 2025-10-17 |  | 2026-03-31 |  | 2026-05-30
2021-4591-6J-1041 | ST-CGF Topside Blast Analysis | ST | Calculation | 2025-12-15 |  | 2026-01-24 |  | 2026-02-03 |  | 2026-04-30 |  | 2026-06-29
2021-4591-6J-1042 | ST-CGF Topside Dropped Object Analysis | ST | Calculation | 2026-01-07 |  | 2026-02-06 |  | 2026-02-15 |  | 2026-05-07 |  | 2026-07-06
2021-4591-6J-1044 | ST-CGF Topside Miscellaneous Design Calculation | ST | Calculation | 2025-08-18 | 2025-08-18 | 2026-02-13 |  | 2026-02-20 |  | 2026-04-14 |  | 2026-06-13
2021-4591-6J-1045 | ST-CGF Topsides Vibration Analysis | ST | Calculation | 2025-11-10 |  | 2025-12-22 |  | 2025-12-30 |  | 2026-05-30 |  | 2026-06-29
2021-4591-6J-1043 | ST-CGF Topsides Blast Wall Design Report | ST | Calculation | 2025-12-15 |  | 2026-01-24 |  | 2026-02-03 |  | 2026-05-07 |  | 2026-07-06
2021-4591-6J-1046 | ST-CGF Topsides Main Truss Joint Design Report | ST | Calculation | 2025-10-10 | 2025-10-10 | 2025-12-05 |  | 2025-12-23 |  | 2026-05-22 |  | 2026-07-02
2021-4591-6J-1047 | ST CGF Topsides Outfittings Design Report - Equipments Support Structure | ST | Calculation | 2025-10-18 |  | 2026-02-20 |  | 2026-02-28 |  | 2026-06-06 |  | 2026-07-06
2021-4591-6J-1048 | ST-CGF Topsides Major Pipe Support And Piperack Design Report | ST | Calculation | 2025-09-30 | 2025-09-30 | 2025-11-14 |  | 2025-11-28 |  | 2026-03-28 |  | 2026-06-26
2021-4591-6J-1049 | DSF Loadout Structural Analysis | ST | Calculation | 2025-09-04 | 2025-09-04 | 2025-10-03 |  | 2025-11-16 |  | 2026-01-15 |  | 2026-05-15
2021-4591-6J-1050 | DSF Transportation Structural Analysis | ST | Calculation | 2025-09-04 | 2025-09-04 | 2025-11-03 |  | 2025-11-16 |  | 2026-01-15 |  | 2026-05-15
2021-4591-6J-1051 | DSF Floatover Structural Analysis | ST | Calculation | 2025-09-04 | 2025-09-04 | 2025-10-03 |  | 2025-11-16 |  | 2026-01-15 |  | 2026-05-15
2021-4591-0Q-1072 | ST-CGF Topside Weight Control Report | ST | Calculation | 2025-06-28 | 2025-06-28 | 2025-08-19 | 2025-08-26 15:55 | 2025-08-26 | 2025-09-30 | 2026-03-27 |  | 2026-07-02
2021-4591-6U-1083 | ST-CGF Topside Primary Steel Material Take-Off | ST | Calculation | 2025-06-28 | 2025-06-28 | 2025-09-05 | 2025-09-19 13:40 | 2025-12-22 | 2025-09-22 | 2026-01-15 |  | 2026-03-15
2021-4591-6U-1084 | ST-CGF Topside Secondary Steel Material Take-Off | ST | Calculation | 2025-07-06 | 2025-07-06 | 2025-09-05 | 2025-09-16 15:45 | 2026-01-03 | 2025-09-25 | 2026-01-27 |  | 2026-05-15
2021-4591-6L-1101 | Specification for Structural Materials | ST | Specification | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-02 | 2025-07-02 | 2025-07-26 | 2025-07-26 | 2025-08-16 | 2025-08-16
2021-4590-6L-1102 | Specification for Fire Rated Blast Walls | ST | Specification | 2025-10-03 | 2025-10-03 | 2025-10-27 |  | 2025-11-13 |  | 2025-12-03 |  | 2026-01-02
2021-4591-6L-1103 | Specification for Structural Skids for Packaged Equipment | ST | Specification | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-31 | 2025-07-31 | 2025-09-13 | 2025-09-15 | 2025-10-07 | 2025-10-09
2021-4591-6L-1104 | Specification for Load-out, Transportation & Installation | ST | Specification | 2025-06-28 | 2025-06-28 | 2025-08-09 | 2025-08-16 14:04 | 2025-08-16 | 2025-08-16 | 2025-09-20 | 2025-10-01 | 2025-10-14
2021-4500-6L-1105 | Specification for Weight Control | ST | Specification | 2025-06-28 | 2025-06-28 | 2025-07-19 | 2025-07-19 | 2025-07-26 | 2025-07-26 | 2025-09-08 | 2025-09-08 | 2025-10-02 | 2025-10-13
2021-4591-6L-1109 | Specification for Structural Fabrication & Welding | ST | Specification | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-07-26 | 2025-07-26 | 2025-08-16 | 2025-08-16
2021-4502-6L-1116 | Specification for Architectural Materials and Furnitures | ST | Specification | 2025-06-28 | 2025-06-28 | 2025-08-08 | 2025-08-08 | 2025-08-04 | 2025-08-04 | 2025-08-21 | 2025-08-21 | 2025-09-17 | 2025-09-17
2021-4589-6V-1123 | Bid Evaluation Criteria for ST-CGF Jacket Structural Anode | ST | Bid | 2025-06-28 | 2025-06-28 | 2025-08-08 | 2025-08-08 | 2025-07-04 | 2025-07-04 |  |  | 2025-08-14 | 2025-08-14
2021-4589-6V-1124 | Bid Evaluation Criteria for ST-CGF Jacket Barge Bumper | ST | Bid | 2025-10-10 | 2025-10-10 | 2025-10-24 |  | 2025-10-29 |  |  |  | 2025-11-19
2021-4589-6V-1125 | Bid Evaluation Criteria for ST-CGF Timber for Launch Runner, & Crane Boom Rest | ST | Bid | 2025-06-28 | 2025-06-28 | 2025-07-07 | 2025-07-07 | 2025-07-14 | 2025-07-14 |  |  | 2025-08-16 | 2025-08-16
2021-4589-6V-1126 | Bid Evaluation Criteria for ST-CGF Jacket Flooding Fitting & Valve Assembly | ST | Bid | 2025-09-05 | 2025-09-05 | 2025-09-19 | 2025-09-26 17:37 | 2025-09-24 | 2025-09-30 |  |  | 2025-10-15
2021-4589-6V-1127 | Bid Evaluation Criteria for ST-CGF Jacket Diaphragm Closure | ST | Bid | 2025-08-01 | 2025-08-01 | 2025-09-04 | 2025-08-14 | 2025-08-21 | 2025-08-21 |  |  | 2025-09-14 | 2025-09-15 11:13
2021-4589-6V-1128 | Bid Evaluation Criteria for ST-CGF Jacket Miscellaneous | ST | Bid | 2025-09-05 | 2025-09-05 | 2025-09-19 | 2025-09-25 14:41 | 2025-09-24 | 2025-09-25 |  |  | 2025-10-15
2021-4589-6V-1129 | Bid Evaluation Criteria for ST-CGF Grating | ST | Bid | 2025-11-25 |  | 2025-12-09 |  | 2025-12-14 |  |  |  | 2026-01-04
2021-4589-6V-1136 | Bid Evaluation Criteria for ST-CGF Jacket Sway Fenders | ST | Bid | 2025-07-14 | 2025-07-14 | 2025-08-09 | 2025-08-09 | 2025-08-16 | 2025-08-16 |  |  | 2025-08-28 | 2025-08-28
2021-4591-6V-1131 | Bid Evaluation Criteria for ST-CGF Topside Float-over Hardware | ST | Bid | 2025-11-05 |  | 2025-11-19 |  | 2025-11-24 |  |  |  | 2025-12-15
2021-4591-6V-1136 | Bid Evaluation Criteria for ST-CGF Secondary & Tertiary Structural Steel | ST | Bid | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 |  |  | 2025-08-11 | 2025-08-11
2021-4591-6V-1137 | Bid Evaluation Criteria for ST-CGF Topside Miscellaneous | ST | Bid | 2025-12-30 |  | 2026-01-13 |  | 2026-01-18 |  |  |  | 2026-02-08
2021-4591-6V-1138 | Bid Evaluation Criteria for ST-CGF Topside Architectural | ST | Bid | 2025-08-14 | 2025-08-14 | 2025-09-13 | 2025-09-19 07:44 | 2025-09-20 | 2025-09-25 |  |  | 2025-10-14 | 2025-10-09
2021-4591-6V-9001 | Bid Evaluation Criteria for Brownfield structural Steel | ST | Bid | 2025-08-14 | 2025-08-14 | 2025-09-13 |  | 2025-09-20 |  |  |  | 2025-09-30
2021-4589-6W-0002 | Technical Requisition for ST-CGF Jacket Structural Anode | ST | Procurement | 2025-06-28 | 2025-06-28 | 2025-08-15 | 2025-08-15 | 2025-07-02 | 2025-07-02 | 2025-07-16 | 2025-07-16 | 2025-10-28
2021-4589-6W-0003 | Technical Requisition for ST-CGF Jacket Barge Bumper | ST | Procurement | 2025-10-08 | 2025-10-08 | 2025-10-16 |  | 2025-10-27 |  | 2025-11-17 |  | 2026-03-06
2021-4589-6W-0004 | Technical Requisition for ST-CGF Timber for Launch Runner & Crane Boom Rest | ST | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-07-19 | 2025-07-19 | 2025-10-28
2021-4589-6W-0005 | Technical Requisition for ST-CGF Jacket Flooding Fitting & Valve Assembly | ST | Procurement | 2025-08-23 | 2025-08-23 | 2025-09-16 | 2025-09-26 13:23 | 2025-09-23 | 2025-09-26 | 2025-10-07 |  | 2026-01-17
2021-4589-6W-0006 | Technical Requisition for ST-CGF Jacket Miscellaneous | ST | Procurement | 2025-08-23 | 2025-08-23 | 2025-10-06 | 2025-09-25 14:41 | 2025-10-13 | 2025-09-25 | 2025-10-20 |  | 2026-01-17
2021-4591-6W-0001 | Technical Requisition for Topside and Jacket Grating | ST | Procurement | 2025-11-23 | 2025-09-18 17:13 | 2025-12-07 | 2025-09-18 17:13 | 2025-12-12 |  | 2026-01-02 |  | 2026-05-02
2021-4589-6W-0007 | Technical Requisition for ST-CGF Jacket Sway Fenders | ST | Procurement | 2025-07-23 | 2025-07-23 | 2025-08-05 | 2025-08-05 | 2025-08-16 | 2025-08-16 | 2025-08-28 | 2025-08-28 | 2026-04-24
2021-4589-6W-0008 | Technical Requisition for ST-CGF Jacket Diaphragm Closure | ST | Procurement | 2025-07-18 | 2025-07-18 | 2025-08-27 | 2025-08-27 | 2025-08-21 | 2025-08-21 | 2025-11-19 | 2025-09-16 | 2025-12-13
2021-4591-6W-0002 | Technical Requisition for ST-CGF Secondary & Tertiary Structural Steel | ST | Procurement | 2025-06-28 | 2025-06-28 | 2025-08-09 | 2025-08-09 | 2025-08-11 | 2025-07-03 | 2025-08-11 | 2025-08-11 | 2025-09-26
2021-4591-6W-0003 | Technical Requisition for ST-CGF Topside Miscellaneous | ST | Procurement | 2026-01-05 |  | 2026-01-19 |  | 2026-01-24 |  | 2026-02-14 |  | 2026-06-01
2021-4591-6W-0004 | Technical Requisition for ST-CGF Topside Float-over Hardware | ST | Procurement | 2025-11-08 |  | 2025-11-22 |  | 2025-11-27 |  | 2025-12-11 |  | 2026-04-13
2021-4592-6W-0001 | Technical Requisition for ST-CGF Topside Architectural | ST | Procurement | 2025-08-20 | 2025-08-20 | 2025-09-13 | 2025-09-19 08:24 | 2025-09-24 | 2025-09-19 | 2025-10-08 | 2025-10-06 | 2026-01-20
2021-4589-6W-0102 | Technical Bid Evaluation for ST-CGF Jacket Structural Anode | ST | Procurement | 2025-09-13 | 2025-09-13 | 2025-10-04 | 2025-10-09 | 2025-10-07 | 2025-10-16 |  |  | 2025-10-18
2021-4589-6W-0103 | Technical Bid Evaluation for ST-CGF Jacket Barge Bumper | ST | Procurement | 2025-12-21 |  | 2026-01-29 |  | 2026-02-06 |  |  |  | 2026-02-22
2021-4589-6W-0104 | Technical Bid Evaluation for ST-CGF Timber for Launch Runner & Crane Boom Rest | ST | Procurement | 2025-08-03 | 2025-08-03 | 2025-09-20 | 2025-09-19 16:44 | 2025-09-30 | 2025-10-10 |  |  | 2025-10-18 | 2025-10-16
2021-4589-6W-0105 | Technical Bid Evaluation for ST-CGF Jacket Flooding Fitting & Valve Assembly | ST | Procurement | 2025-11-04 |  | 2025-12-02 |  | 2025-12-05 |  |  |  | 2025-12-17
2021-4589-6W-0106 | Technical Bid Evaluation for ST-CGF Jacket Miscellaneous | ST | Procurement | 2025-11-04 |  | 2025-12-02 |  | 2025-12-05 |  |  |  | 2025-12-17
2021-4591-6W-0101 | Technical Bid Evaluation for Topside and Jacket Grating | ST | Procurement | 2026-02-08 |  | 2026-03-08 |  | 2026-03-13 |  |  |  | 2026-04-03
2021-4589-6W-0107 | Technical Bid Evaluation for ST-CGF Jacket Sway Fenders | ST | Procurement | 2025-10-13 | 2025-10-13 | 2025-11-10 |  | 2025-11-18 |  |  |  | 2025-12-02
2021-4589-6W-0108 | Technical Bid Evaluation for ST-CGF Jacket Diaphragm Closure | ST | Procurement | 2025-10-04 | 2025-10-04 | 2025-11-01 |  | 2025-11-05 |  |  |  | 2025-11-15
2021-4591-6W-0102 | Technical Bid Evaluation for ST-CGF Secondary & Tertiary Structural Steel | ST | Procurement | 2025-07-21 | 2025-07-21 | 2025-08-06 | 2025-08-06 | 2025-08-23 | 2025-08-23 |  |  | 2025-09-30 | 2025-09-15
2021-4591-6W-0103 | Technical Bid Evaluation for ST-CGF Topside Miscellaneous | ST | Procurement | 2026-03-19 |  | 2026-04-16 |  | 2026-04-19 |  |  |  | 2026-05-01
2021-4591-6W-0104 | Technical Bid Evaluation for ST-CGF Topside Float-over Hardware | ST | Procurement | 2026-01-14 | 2025-09-26 | 2026-02-23 | 2025-09-26 | 2026-02-28 |  |  |  | 2026-03-12
2021-4592-6W-0101 | Technical Bid Evaluation for ST-CGF Topsides Architectural for E-houses | ST | Procurement | 2025-10-30 |  | 2025-12-09 |  | 2025-12-12 |  |  |  | 2025-12-27
2021-4591-60-0001 | ST-CGF Topside Drawing Index - Sht 01 & Sht 04 | ST | Drawing | 2025-07-03 | 2025-07-03 | 2025-11-30 |  | 2025-12-13 |  |  |  | 2026-06-29
2021-4591-61-0001 | ST-CGF Topside General Notes - Sht 01 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-08-08 | 2025-08-08 | 2025-11-06 |  | 2025-12-06
2021-4591-61-0002 | ST-CGF Topside General Notes - Sht 02 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-11-06 |  | 2025-12-06
2021-4591-61-0003 | ST-CGF Jack-up Rig Location & Cantilever Limit | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-08 | 2025-08-08 | 2025-08-21 | 2025-08-21 | 2025-11-06 |  | 2025-12-06
2021-4591-61-0009 | ST-CGF Topsides Deck Floor Loading Maps Sht 01 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-08-16 | 2025-08-16 | 2025-11-06 |  | 2025-12-06
2021-4591-61-0010 | ST-CGF Topsides Deck Floor Loading Maps Sht 02 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-08-16 | 2025-08-16 | 2025-11-06 |  | 2025-12-06
2021-4591-61-0006 | ST-CGF Topside Typical Welding Details - Sht 01 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-08-14 | 2025-08-14 | 2025-11-06 |  | 2025-12-06
2021-4591-61-0007 | ST-CGF Topside Typical Welding Details - Sht 02 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-06-30 | 2025-06-30 | 2025-08-14 | 2025-08-14 | 2025-11-06 |  | 2025-12-06
2021-4591-61-0008 | ST-CGF Topside Typical Welding Details - Sht 03 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-08 | 2025-08-08 | 2025-08-14 | 2025-08-14 | 2025-11-06 |  | 2025-12-06
2021-4591-61-0011 | ST-CGF Topside Typical Joint Connection Details - Sht 01 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-11-06 |  | 2025-12-06
2021-4591-61-0012 | ST-CGF Topside Typical Joint Connection Details - Sht 02 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-05 | 2025-08-05 | 2025-08-08 | 2025-08-08 | 2025-11-06 |  | 2025-12-06
2021-4591-61-0013 | ST-CGF Topside Typical Joint Connection Details - Sht 03 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-05 | 2025-08-05 | 2025-08-08 | 2025-08-08 | 2025-11-06 |  | 2025-12-06
2021-4591-61-0014 | ST-CGF Topside Typical Joint Connection Details - Sht 04 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-05 | 2025-08-05 | 2025-08-08 | 2025-08-08 | 2025-11-06 |  | 2025-12-06
2021-4591-61-0015 | ST-CGF Topside Typical Joint Connection Details - Sht 05 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-05 | 2025-08-05 | 2025-08-08 | 2025-08-08 | 2025-11-06 |  | 2025-12-06
2021-4591-61-0016 | ST-CGF Topside Typical Joint Connection Details - Sht 06 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-05 | 2025-08-05 | 2025-08-08 | 2025-08-08 | 2025-11-06 |  | 2025-12-06
2021-4591-61-0017 | ST-CGF Topside Typical Joint Connection Details - Sht 07 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-05 | 2025-08-05 | 2025-08-08 | 2025-08-08 | 2025-11-06 |  | 2025-12-06
2021-4591-61-0023 | ST-CGF Topside Typical Stiffener Details | ST | Drawing | 2025-07-14 | 2025-07-14 | 2025-08-07 | 2025-08-14 16:50 | 2025-08-14 | 2025-08-14 | 2025-11-21 |  | 2025-12-21
2021-4591-61-0024 | ST-CGF Topside Typical Gusset Plate Details | ST | Drawing | 2025-07-14 | 2025-07-14 | 2025-08-22 | 2025-08-22 | 2025-08-09 | 2025-08-09 | 2025-11-21 |  | 2025-12-21
2021-4591-61-0031 | ST-CGF Topside Standard Stairway Details - Sht 01 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-22 | 2025-08-22 | 2025-08-14 | 2025-08-14 | 2025-11-21 |  | 2025-12-21
2021-4591-61-0032 | ST-CGF Topside Standard Stairway Details - Sht 02 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-22 | 2025-08-22 | 2025-08-14 | 2025-08-14 | 2025-11-21 |  | 2025-12-21
2021-4591-61-0033 | ST-CGF Topside Standard Ladder Details - Sht 01 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-25 | 2025-08-25 | 2025-08-14 | 2025-08-14 | 2025-11-21 |  | 2025-12-21
2021-4591-61-0034 | ST-CGF Topside Standard Ladder Details - Sht 02 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-25 | 2025-08-25 | 2025-08-14 | 2025-08-14 | 2025-11-21 |  | 2025-12-21
2021-4591-61-0035 | ST-CGF Topside Standard Handrail Details - Sht 01 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-25 | 2025-08-25 | 2025-08-08 | 2025-08-08 | 2025-11-21 |  | 2025-12-21
2021-4591-61-0036 | ST-CGF Topside Standard Handrail Details - Sht 02 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-26 | 2025-08-26 | 2025-08-08 | 2025-08-08 | 2025-11-21 |  | 2025-12-21
2021-4591-61-0037 | ST-CGF Topside Standard Handrail Details - Sht 03 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-26 | 2025-08-26 | 2025-08-08 | 2025-08-08 | 2025-11-21 |  | 2025-12-21
2021-4591-61-0038 | ST-CGF Topside Standard Self Closing gate Details | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-26 | 2025-08-26 | 2025-08-12 | 2025-08-12 | 2025-11-21 |  | 2025-12-21
2021-4591-61-0039 | ST-CGF Topside Typical Plating Details | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-26 | 2025-08-26 | 2025-08-14 | 2025-08-14 | 2025-11-21 |  | 2025-12-21
2021-4591-61-0040 | ST-CGF Topside Typical Grating Details | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-07 | 2025-08-14 16:50 | 2025-08-14 | 2025-08-14 | 2025-11-21 |  | 2025-12-21
2021-4591-61-0041 | ST-CGF Topside Typical Deck Penetration Details - Sht 01 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-05 | 2025-08-11 17:32 | 2025-08-12 | 2025-08-12 | 2025-11-21 |  | 2025-12-21
2021-4591-61-0042 | ST-CGF Topside Typical Deck Penetration Details - Sht 02 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-04 | 2025-08-11 17:29 | 2025-08-11 | 2025-08-11 | 2025-11-21 |  | 2025-12-21
2021-4591-61-0043 | ST-CGF Topside Typical Drain Box Details | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-04 | 2025-08-11 17:29 | 2025-08-11 | 2025-08-11 | 2025-11-21 |  | 2025-12-21
2021-4591-61-0044 | ST-CGF Topside Typical Hatch Cover Layout & Details - Sht 01 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-26 | 2025-08-26 | 2025-08-09 | 2025-08-09 | 2025-11-21 |  | 2025-12-21
2021-4591-61-0045 | ST-CGF Topside Typical Hatch Cover Layout & Details - Sht 02 | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-26 | 2025-08-26 | 2025-08-09 | 2025-08-09 | 2025-11-21 |  | 2025-12-21
2021-4591-61-0046 | ST-CGF Topside Typical Liquid Seal Details | ST | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-26 | 2025-08-26 | 2025-08-09 | 2025-08-09 | 2025-11-21 |  | 2025-12-21
2021-4591-62-0001 | ST-CGF Topside Perspective View | ST | Drawing | 2025-11-15 |  | 2025-12-25 |  | 2026-01-15 |  | 2026-04-15 |  | 2026-05-15
2021-4591-62-0002-01 | ST-CGF Topside Elevation Truss Rows - 1 | ST | Drawing | 2025-07-31 | 2025-07-31 | 2025-08-22 | 2025-09-18 15:14 | 2025-11-06 |  | 2026-02-09 |  | 2026-03-23
2021-4591-62-0002-02 | ST-CGF Topside Elevation Truss Rows - 2 | ST | Drawing | 2025-07-31 | 2025-07-31 | 2025-08-22 | 2025-09-18 15:14 | 2025-11-06 |  | 2026-02-09 |  | 2026-03-23
2021-4591-62-0002-03 | ST-CGF Topside Elevation Truss Rows - 3 | ST | Drawing | 2025-07-31 | 2025-07-31 | 2025-08-22 | 2025-09-18 15:14 | 2025-11-06 |  | 2026-02-09 |  | 2026-03-23
2021-4591-62-0002-04 | ST-CGF Topside Elevation Truss Rows - 4 | ST | Drawing | 2025-07-31 | 2025-07-31 | 2025-08-25 | 2025-09-18 15:14 | 2025-11-06 |  | 2026-02-09 |  | 2026-03-23
2021-4591-62-0002-05 | ST-CGF Topside Elevation Truss Rows - 5 | ST | Drawing | 2025-07-31 | 2025-07-31 | 2025-08-25 | 2025-09-18 15:14 | 2025-11-06 |  | 2026-02-09 |  | 2026-03-23
2021-4591-62-0002-06 | ST-CGF Topside Elevation Truss Rows - 6 | ST | Drawing | 2025-07-31 | 2025-07-31 | 2025-08-25 | 2025-09-18 15:14 | 2025-11-06 |  | 2026-02-09 |  | 2026-03-23
2021-4591-62-0002-07 | ST-CGF Topside Elevation Truss Rows - 3.1 | ST | Drawing | 2025-07-31 | 2025-07-31 | 2025-08-26 | 2025-09-18 15:14 | 2025-11-06 |  | 2026-02-09 |  | 2026-03-23
2021-4591-62-0002-08 | ST-CGF Topside Elevation Truss Rows - A | ST | Drawing | 2025-07-31 | 2025-07-31 | 2025-08-26 | 2025-09-18 15:14 | 2025-11-06 |  | 2026-02-09 |  | 2026-03-23
2021-4591-62-0002-09 | ST-CGF Topside Elevation Truss Rows - B | ST | Drawing | 2025-07-31 | 2025-07-31 | 2025-08-26 | 2025-09-18 15:14 | 2025-11-06 |  | 2026-02-09 |  | 2026-03-23
2021-4591-62-0002-10 | ST-CGF Topside Elevation Truss Rows - C | ST | Drawing | 2025-07-31 | 2025-07-31 | 2025-08-26 | 2025-09-18 15:14 | 2025-11-06 |  | 2026-02-09 |  | 2026-03-23
2021-4591-62-0003-01 | ST-CGF Topside Sectional Views - SHT 01 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-12-25 |  | 2026-01-06 |  | 2026-02-09 |  | 2026-03-23
2021-4591-62-0003-02 | ST-CGF Topside Sectional Views - SHT 02 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-12-25 |  | 2026-01-06 |  | 2026-02-09 |  | 2026-03-23
2021-4591-62-0003-03 | ST-CGF Topside Sectional Views - SHT 03 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-12-25 |  | 2026-01-06 |  | 2026-02-09 |  | 2026-03-23
2021-4591-62-0003-04 | ST-CGF Topside Sectional Views - SHT 04 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-12-25 |  | 2026-01-06 |  | 2026-02-09 |  | 2026-03-23
2021-4591-62-0011 | ST-CGF Topside Primary Steel Framing Plans - Main Deck | ST | Drawing | 2025-07-25 | 2025-07-25 | 2025-08-26 | 2025-09-18 15:14 | 2025-10-28 |  | 2026-01-31 |  | 2026-03-21
2021-4591-62-0012 | ST-CGF Topside Primary Steel Framing Plan - Intermediate Deck | ST | Drawing | 2025-07-25 | 2025-07-25 | 2025-09-17 | 2025-09-18 15:14 | 2025-10-28 |  | 2026-01-31 |  | 2026-03-21
2021-4591-62-0013 | ST-CGF Topside Primary Steel Framing Plan - Cellar Deck | ST | Drawing | 2025-07-25 | 2025-07-25 | 2025-08-20 | 2025-09-18 15:14 | 2025-11-06 |  | 2026-01-20 |  | 2026-02-09
2021-4591-62-0024-01 | ST-CGF Topside Crane Boom Rest Layout & Details - Sht 01 | ST | Drawing | 2026-01-15 |  | 2026-03-05 |  | 2026-03-17 |  |  |  | 2026-07-09
2021-4591-62-0024-02 | ST-CGF Topside Crane Boom Rest Layout & Details - Sht 02 | ST | Drawing | 2026-01-15 |  | 2026-03-05 |  | 2026-03-17 |  |  |  | 2026-07-09
2021-4591-62-0024-03 | ST-CGF Topside Crane Boom Rest Layout & Details - Sht 03 | ST | Drawing | 2026-01-15 |  | 2026-03-05 |  | 2026-03-17 |  |  |  | 2026-07-09
2021-4591-62-0031-01 | ST-CGF Topside Primary Joint Details Truss Row 1- SHT 01 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-09-05 | 2025-09-17 07:44 | 2025-11-23 |  | 2026-01-16 |  | 2026-03-15
2021-4591-62-0031-02 | ST-CGF Topside Primary Joint Details Truss Row 1- SHT 02 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-09-18 | 2025-09-17 08:18 | 2025-11-23 |  | 2026-01-16 |  | 2026-03-15
2021-4591-62-0031-03 | ST-CGF Topside Primary Joint Details Truss Row 1- SHT 03 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-09-18 | 2025-09-17 08:27 | 2025-10-23 |  | 2026-01-16 |  | 2026-03-01
2021-4591-62-0032-01 | ST-CGF Topside Primary Joint Details Truss Row 2- SHT 01 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-09-25 | 2025-09-17 08:38 | 2025-11-23 |  | 2026-01-16 |  | 2026-03-15
2021-4591-62-0032-02 | ST-CGF Topside Primary Joint Details Truss Row 2- SHT 02 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-09-25 | 2025-09-17 08:59 | 2025-11-23 |  | 2026-01-16 |  | 2026-03-15
2021-4591-62-0032-03 | ST-CGF Topside Primary Joint Details Truss Row 2- SHT 03 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-09-25 | 2025-09-18 16:27 | 2025-11-23 |  | 2026-01-16 |  | 2026-03-15
2021-4591-62-0032-04 | ST-CGF Topside Primary Joint Details Truss Row 2- SHT 04 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-10-10 | 2025-09-26 10:00 | 2025-11-15 |  | 2026-01-16 |  | 2026-03-01
2021-4591-62-0032-05 | ST-CGF Topside Primary Joint Details Truss Row 2- SHT 05 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-10-10 | 2025-10-03 09:37 | 2025-11-15 |  | 2026-01-16 |  | 2026-03-01
2021-4591-62-0032-06 | ST-CGF Topside Primary Joint Details Truss Row 2- SHT 06 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-10-10 | 2025-10-01 15:22 | 2025-11-15 |  | 2026-01-16 |  | 2026-03-01
2021-4591-62-0033-01 | ST-CGF Topside Primary Joint Details Truss Row 3- SHT 01 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-10-25 | 2025-09-26 14:19 | 2025-11-23 |  | 2026-01-16 |  | 2026-03-17
2021-4591-62-0033-02 | ST-CGF Topside Primary Joint Details Truss Row 3- SHT 02 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-10-25 | 2025-10-01 15:57 | 2025-11-23 |  | 2026-01-16 |  | 2026-03-17
2021-4591-62-0033-03 | ST-CGF Topside Primary Joint Details Truss Row 3- SHT 03 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-10-25 | 2025-10-01 16:07 | 2025-11-23 |  | 2026-01-16 |  | 2026-03-17
2021-4591-62-0033-04 | ST-CGF Topside Primary Joint Details Truss Row 3- SHT 04 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-10-25 | 2025-10-01 16:13 | 2025-11-23 |  | 2026-01-16 |  | 2026-03-17
2021-4591-62-0033-05 | ST-CGF Topside Primary Joint Details Truss Row 3- SHT 05 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-10-10 | 2025-10-01 17:43 | 2025-11-15 |  | 2026-01-16 |  | 2026-02-10
2021-4591-62-0034-01 | ST-CGF Topside Primary Joint Details Truss Row 4- SHT 01 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-11-25 | 2025-09-26 07:54 | 2025-12-23 |  | 2026-01-16 |  | 2026-03-17
2021-4591-62-0034-02 | ST-CGF Topside Primary Joint Details Truss Row 4- SHT 02 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-11-25 | 2025-09-26 08:06 | 2025-12-23 |  | 2026-01-16 |  | 2026-03-17
2021-4591-62-0034-03 | ST-CGF Topside Primary Joint Details Truss Row 4- SHT 03 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-11-25 | 2025-09-26 08:25 | 2025-12-23 |  | 2026-01-16 |  | 2026-03-17
2021-4591-62-0034-04 | ST-CGF Topside Primary Joint Details Truss Row 4- SHT 04 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-11-25 | 2025-09-26 16:16 | 2025-12-23 |  | 2026-01-16 |  | 2026-03-17
2021-4591-62-0035-01 | ST-CGF Topside Primary Joint Details Truss Row 5- SHT 01 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-11-25 | 2025-10-01 16:45 | 2025-12-23 |  | 2026-01-16 |  | 2026-03-19
2021-4591-62-0035-02 | ST-CGF Topside Primary Joint Details Truss Row 5- SHT 02 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-11-25 | 2025-10-01 16:54 | 2025-12-23 |  | 2026-01-16 |  | 2026-03-19
2021-4591-62-0035-03 | ST-CGF Topside Primary Joint Details Truss Row 5- SHT 03 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-11-25 | 2025-10-02 08:50 | 2025-12-23 |  | 2026-01-16 |  | 2026-03-19
2021-4591-62-0035-04 | ST-CGF Topside Primary Joint Details Truss Row 5- SHT 04 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-11-25 | 2025-10-03 14:15 | 2025-12-23 |  | 2026-01-16 |  | 2026-03-19
2021-4591-62-0035-05 | ST-CGF Topside Primary Joint Details Truss Row 5- SHT 05 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-10-13 | 2025-10-06 09:25 | 2025-11-15 |  | 2026-01-16 |  | 2026-02-10
2021-4591-62-0035-06 | ST-CGF Topside Primary Joint Details Truss Row 5- SHT 06 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-10-13 | 2025-10-06 09:25 | 2025-11-15 |  | 2026-01-16 |  | 2026-02-15
2021-4591-62-0035-07 | ST-CGF Topside Primary Joint Details Truss Row 5- SHT 07 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-10-13 | 2025-10-08 09:39 | 2025-11-15 |  | 2026-01-16 |  | 2026-02-15
2021-4591-62-0036-01 | ST-CGF Topside Primary Joint Details Truss Row 6- SHT 01 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-11-27 | 2025-09-26 16:55 | 2025-12-25 |  | 2026-01-16 |  | 2026-03-19
2021-4591-62-0036-02 | ST-CGF Topside Primary Joint Details Truss Row 6- SHT 02 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-11-27 | 2025-10-10 14:22 | 2025-12-25 |  | 2026-01-16 |  | 2026-03-19
2021-4591-62-0036-03 | ST-CGF Topside Primary Joint Details Truss Row 6- SHT 03 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-11-27 | 2025-10-10 16:16 | 2025-12-25 |  | 2026-01-16 |  | 2026-03-19
2021-4591-62-0036-04 | ST-CGF Topside Primary Joint Details Truss Row 6- SHT 04 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-11-27 | 2025-10-02 09:11 | 2025-12-25 |  | 2026-01-16 |  | 2026-02-15
2021-4591-62-0037-01 | ST-CGF Topside Primary Joint Details Truss Row 3.1- SHT 01 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-11-27 | 2025-10-08 11:07 | 2025-12-25 |  | 2026-01-16 |  | 2026-03-21
2021-4591-62-0037-02 | ST-CGF Topside Primary Joint Details Truss Row 3.1- SHT 02 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-11-27 | 2025-10-10 08:36 | 2025-12-25 |  | 2026-01-16 |  | 2026-03-21
2021-4591-62-0037-03 | ST-CGF Topside Primary Joint Details Truss Row 3.1- SHT 03 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-11-27 | 2025-10-10 08:43 | 2025-12-25 |  | 2026-01-16 |  | 2026-03-21
2021-4591-62-0037-04 | ST-CGF Topside Primary Joint Details Truss Row 3.1- SHT 04 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-11-27 | 2025-10-09 10:45 | 2025-12-25 |  | 2026-01-16 |  | 2026-03-28
2021-4591-62-0038-01 | ST-CGF Topside Primary Joint Details Truss A- SHT 01 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-12-04 | 2025-10-08 10:21 | 2025-12-25 |  | 2026-01-16 |  | 2026-03-28
2021-4591-62-0038-02 | ST-CGF Topside Primary Joint Details Truss A- SHT 02 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-12-04 | 2025-10-10 17:13 | 2025-12-25 |  | 2026-01-16 |  | 2026-03-28
2021-4591-62-0038-03 | ST-CGF Topside Primary Joint Details Truss A- SHT 03 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-12-04 | 2025-10-10 17:13 | 2025-12-25 |  | 2026-01-16 |  | 2026-03-28
2021-4591-62-0039-01 | ST-CGF Topside Primary Joint Details Truss B- SHT 01 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-12-04 | 2025-10-09 13:21 | 2025-12-25 |  | 2026-01-16 |  | 2026-03-28
2021-4591-62-0039-02 | ST-CGF Topside Primary Joint Details Truss B- SHT 02 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-12-04 | 2025-10-10 08:01 | 2025-12-25 |  | 2026-01-16 |  | 2026-03-28
2021-4591-62-0040-01 | ST-CGF Topside Primary Joint Details Truss C- SHT 01 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-12-04 | 2025-10-10 09:33 | 2025-12-25 |  | 2026-01-16 |  | 2026-03-28
2021-4591-62-0040-02 | ST-CGF Topside Primary Joint Details Truss C- SHT 02 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-12-04 | 2025-10-10 09:33 | 2025-12-25 |  | 2026-01-16 |  | 2026-03-28
2021-4591-62-0040-03 | ST-CGF Topside Primary Joint Details Truss C- SHT 03 | ST | Drawing | 2025-08-18 | 2025-08-18 | 2025-12-04 |  | 2025-12-25 |  | 2026-01-16 |  | 2026-03-28
2021-4591-63-0001 | ST-CGF Topside Secondary Steel Framing Plans - Main Deck | ST | Drawing | 2025-12-16 |  | 2026-02-25 |  | 2026-03-15 |  |  |  | 2026-06-15
2021-4591-63-0002 | ST-CGF Topside Secondary Steel Framing Plans - Intermediate Deck | ST | Drawing | 2025-11-15 |  | 2026-01-25 |  | 2026-03-15 |  |  |  | 2026-05-15
2021-4591-63-0003 | ST-CGF Topside Secondary Steel Framing Plans - Cellar Deck | ST | Drawing | 2025-10-16 | 2025-10-16 | 2025-12-25 |  | 2026-01-23 |  |  |  | 2026-04-15
2021-4591-63-0004 | ST-CGF Topside Secondary Steel Framing Plans - Sub-Cellar Deck | ST | Drawing | 2026-01-15 |  | 2026-03-05 |  | 2026-03-17 |  |  |  | 2026-07-09
2021-4591-63-0005 | ST-CGF Topside Flooring & Handrail Layouts - Main Deck | ST | Drawing | 2026-01-15 |  | 2026-03-05 |  | 2026-03-17 |  |  |  | 2026-07-09
2021-4591-63-0006 | ST-CGF Topside Flooring & Handrail Layouts - Intermediate Deck | ST | Drawing | 2026-01-15 |  | 2026-03-05 |  | 2026-03-17 |  |  |  | 2026-07-09
2021-4591-63-0007 | ST-CGF Topside Flooring & Handrail Layouts - Cellar Deck | ST | Drawing | 2026-01-15 |  | 2026-02-24 |  | 2026-03-17 |  |  |  | 2026-07-15
2021-4591-63-0008 | ST-CGF Topside Flooring & Handrail Layouts - Sub-Cellar Deck | ST | Drawing | 2026-01-15 |  | 2026-02-24 |  | 2026-03-17 |  |  |  | 2026-07-15
2021-4591-63-0010 | ST-CGF Topside Fire & Blast Wall Plan, Elevation View, Section & Details | ST | Drawing | 2026-01-17 |  | 2026-02-07 |  | 2026-03-14 |  | 2026-04-01 |  | 2026-05-01
2021-4591-63-0011-01 | ST-CGF Topside Stairway Layout & Sections - SHT 01 | ST | Drawing | 2026-02-14 |  | 2026-03-26 |  | 2026-04-16 |  |  |  | 2026-07-15
2021-4591-63-0011-02 | ST-CGF Topside Stairway Layout & Sections - SHT 02 | ST | Drawing | 2026-02-14 |  | 2026-03-26 |  | 2026-04-16 |  |  |  | 2026-07-15
2021-4591-63-0011-03 | ST-CGF Topside Stairway Layout & Sections - SHT 03 | ST | Drawing | 2026-02-14 |  | 2026-03-26 |  | 2026-04-16 |  |  |  | 2026-07-15
2021-4591-63-0011-04 | ST-CGF Topside Stairway Layout & Sections - SHT 04 | ST | Drawing | 2026-02-14 |  | 2026-03-26 |  | 2026-04-16 |  |  |  | 2026-07-15
2021-4591-63-0011-05 | ST-CGF Topside Stairway Layout & Sections - SHT 05 | ST | Drawing | 2026-02-14 |  | 2026-03-26 |  | 2026-04-16 |  |  |  | 2026-07-15
2021-4591-63-0011-06 | ST-CGF Topside Stairway Layout & Sections - SHT 06 | ST | Drawing | 2026-02-14 |  | 2026-03-26 |  | 2026-04-16 |  |  |  | 2026-07-15
2021-4591-63-0011-07 | ST-CGF Topside Stairway Layout & Sections - SHT 07 | ST | Drawing | 2026-02-14 |  | 2026-03-26 |  | 2026-04-16 |  |  |  | 2026-07-15
2021-4591-63-0013 | ST-CGF Topside Platform Identification Sign | ST | Drawing | 2026-03-06 |  | 2026-04-05 |  | 2026-04-26 |  |  |  | 2026-07-15
2021-4591-63-0014 | ST-CGF Topside Lifting Lugs Layout and Details | ST | Drawing | 2026-02-04 |  | 2026-03-12 |  | 2026-04-06 |  |  |  | 2026-06-15
2021-4591-63-0015 | ST-CGF Topside Monorail Layout and Details | ST | Drawing | 2026-02-04 |  | 2026-03-12 |  | 2026-04-06 |  |  |  | 2026-06-15
2021-4592-90-0001 | ST-CGF Topside E-House - Architectural Drawing Index | ST | Drawing | 2025-08-13 | 2025-08-13 | 2025-12-05 |  | 2025-12-15 |  | 2026-05-11 |  | 2026-06-10
2021-4592-91-0001 | ST-CGF Topside E-House - Architectural 1st Floor Layout Plan | ST | Drawing | 2025-07-19 | 2025-07-19 | 2025-12-05 |  | 2025-12-15 |  | 2026-03-22 |  | 2026-06-05
2021-4592-91-0002 | ST-CGF Topside E-House - Architectural 2nd Floor Layout Plan | ST | Drawing | 2025-07-19 | 2025-07-19 | 2025-12-05 |  | 2025-12-15 |  | 2026-03-22 |  | 2026-06-05
2021-4592-91-0003 | ST-CGF Topside E-House - Architectural Roof Layout Plan | ST | Drawing | 2025-07-19 | 2025-07-19 | 2025-12-05 |  | 2025-12-15 |  | 2026-03-22 |  | 2026-06-05
2021-4592-91-0004 | ST-CGF Topside E-House - Elevation Looking East | ST | Drawing | 2025-07-19 | 2025-07-19 | 2025-12-05 |  | 2025-12-15 |  | 2026-03-22 |  | 2026-06-05
2021-4592-91-0005 | ST-CGF Topside E-House - Elevation Looking North | ST | Drawing | 2025-07-19 | 2025-07-19 | 2025-12-05 |  | 2025-12-15 |  |  |  | 2026-06-05
2021-4592-91-0006 | ST-CGF Topside E-House - Elevation Looking South | ST | Drawing | 2025-08-03 | 2025-08-03 | 2025-11-17 |  | 2025-12-17 |  |  |  | 2026-06-15
2021-4592-91-0007 | ST-CGF Topside E-House - Elevation Looking West | ST | Drawing | 2025-08-03 | 2025-08-03 | 2025-11-17 |  | 2025-12-17 |  |  |  | 2026-06-15
2021-4592-91-0008 | ST-CGF Topside E-House - Longitudinal Section | ST | Drawing | 2025-08-03 | 2025-08-03 | 2025-11-17 |  | 2025-12-17 |  |  |  | 2026-06-15
2021-4592-91-0009 | ST-CGF Topside E-House - Cross Section | ST | Drawing | 2025-08-03 | 2025-08-03 | 2025-11-17 |  | 2025-12-17 |  |  |  | 2026-06-15
2021-4592-91-0010 | ST-CGF Topside E-House - Fire Rated Insulation Plan - 1st Floor | ST | Drawing | 2025-08-03 | 2025-08-03 | 2025-12-05 |  | 2025-12-20 |  |  |  | 2026-06-15
2021-4592-91-0011 | ST-CGF Topside E-House - Fire Rated Insulation Plan - 2nd Floor | ST | Drawing | 2025-08-03 | 2025-08-03 | 2025-12-05 |  | 2025-12-20 |  |  |  | 2026-06-15
2021-4592-91-0012 | ST-CGF Topside E-House - Fire Rated Insulation Plan - Roof | ST | Drawing | 2025-08-03 | 2025-08-03 | 2025-12-05 |  | 2025-12-20 |  |  |  | 2026-06-15
2021-4592-91-0013 | ST-CGF Topside E-House - Fire Rated Insulation - Details | ST | Drawing | 2025-08-03 | 2025-08-03 | 2025-12-05 |  | 2025-12-20 |  |  |  | 2026-06-15
2021-4592-91-0014 | ST-CGF Topside E-House - Fire Rated Insulation - Sections | ST | Drawing | 2025-08-03 | 2025-08-03 | 2025-12-05 |  | 2025-12-20 |  |  |  | 2026-06-15
2021-4592-91-0015 | ST-CGF Topside E-House - Panel and Flooring Plan - 1st Floor | ST | Drawing | 2025-08-03 | 2025-08-03 | 2025-12-15 |  | 2025-12-25 |  |  |  | 2026-06-15
2021-4592-91-0016 | ST-CGF Topside E-House - Panel and Flooring Plan - 2nd Floor | ST | Drawing | 2025-08-03 | 2025-08-03 | 2025-12-15 |  | 2025-12-25 |  |  |  | 2026-06-15
2021-4592-91-0017 | ST-CGF Topside E-House - Panel and Flooring - Sections & Details | ST | Drawing | 2025-08-03 | 2025-08-03 | 2025-12-15 |  | 2025-12-25 |  |  |  | 2026-06-15
2021-4592-91-0018 | ST-CGF Topside E-House - Architectural Schedule of Finishes | ST | Drawing | 2025-08-03 | 2025-08-03 | 2025-12-15 |  | 2025-12-25 |  |  |  | 2026-06-15
2021-4592-91-0019 | ST-CGF Topside E-House - Door Schedule | ST | Drawing | 2025-08-03 | 2025-08-03 | 2025-12-15 |  | 2025-12-25 |  |  |  | 2026-06-15
2021-4592-91-0020 | ST-CGF Topside E-House - Door Details | ST | Drawing | 2025-08-03 | 2025-08-03 | 2025-12-15 |  | 2025-12-25 |  |  |  | 2026-06-15
2021-4592-91-0021 | ST-CGF Topside E-House - Master key system & Room signage schedule | ST | Drawing | 2025-08-03 | 2025-08-03 | 2025-12-15 |  | 2025-12-25 |  |  |  | 2026-06-15
2021-4592-91-0022 | ST-CGF Topside E-House - Furniture Schedule | ST | Drawing | 2025-08-03 | 2025-08-03 | 2025-12-15 |  | 2025-12-25 |  |  |  | 2026-06-15
2021-4592-91-0023 | ST-CGF Topside E-House - Furniture Details | ST | Drawing | 2025-08-03 | 2025-08-03 | 2025-12-15 |  | 2025-12-25 |  |  |  | 2026-06-15
2021-4592-91-0101 | ST-CGF Topside E-House - 1st Floor Framing Plan | ST | Drawing | 2025-09-10 | 2025-09-10 | 2025-11-16 |  | 2025-12-10 |  | 2026-02-08 |  | 2026-03-28
2021-4592-91-0102 | ST-CGF Topside E-House - 2nd Floor Framing Plan | ST | Drawing | 2025-09-10 | 2025-09-10 | 2025-11-16 |  | 2025-12-10 |  | 2026-02-08 |  | 2026-03-28
2021-4592-91-0103 | ST-CGF Topside E-House - Roof Floor Framing Plan | ST | Drawing | 2025-09-10 | 2025-09-10 | 2025-11-16 |  | 2025-12-10 |  | 2026-02-08 |  | 2026-03-28
2021-4592-91-0104 | ST-CGF Topside E-House - Truss Elevations and Sections | ST | Drawing | 2025-09-10 | 2025-09-10 | 2025-11-16 |  | 2025-12-10 |  | 2026-02-08 |  | 2026-03-28
2021-4592-91-0105 | ST-CGF Topside E-House - Joint Details | ST | Drawing | 2025-09-10 | 2025-09-10 | 2025-11-20 |  | 2025-12-10 |  | 2026-02-08 |  | 2026-03-28
2021-4592-91-0106 | ST-CGF Topside E-House - 1st Flooring Plan | ST | Drawing | 2025-09-10 | 2025-09-10 | 2025-11-30 |  | 2025-12-10 |  |  |  | 2026-03-28
2021-4592-91-0107 | ST-CGF Topside E-House - 2nd Flooring Plan | ST | Drawing | 2025-09-10 | 2025-09-10 | 2025-11-30 |  | 2025-12-10 |  |  |  | 2026-03-28
2021-4592-91-0108 | ST-CGF Topside E-House - Roof Flooring Plan | ST | Drawing | 2025-09-10 | 2025-09-10 | 2025-11-30 |  | 2025-12-10 |  |  |  | 2026-03-28
2021-4592-91-0109 | ST-CGF Topside E-House - Wall Elevation & Details | ST | Drawing | 2025-09-10 | 2025-09-10 | 2025-11-30 |  | 2025-12-10 |  |  |  | 2026-03-28
2021-4592-91-0110 | ST-CGF Topside E-House - Equipment Support Details | ST | Drawing | 2025-10-01 | 2025-10-01 | 2025-12-10 |  | 2026-01-12 |  |  |  | 2026-03-31
2021-4592-91-0111 | ST-CGF Topside Workshop Structural Building Layout | ST | Drawing | 2025-09-10 | 2025-09-10 | 2025-11-30 |  | 2026-01-12 |  |  |  | 2026-03-10
2021-4592-91-0112 | ST-CGF Topside Workshop Structural Building Section and Detail | ST | Drawing | 2025-09-10 | 2025-09-10 | 2025-11-30 |  | 2026-01-12 |  |  |  | 2026-03-10
2021-4591-66-0030-01 | ST-CGF Topsides - Deck Support Frame (DSF) Sections and Details - Sht 01 | ST | Drawing | 2026-01-15 |  | 2026-02-24 |  | 2026-04-17 |  | 2026-06-25 |  | 2026-07-15
2021-4591-66-0030-02 | ST-CGF Topsides - Deck Support Frame (DSF) Sections and Details - Sht 02 | ST | Drawing | 2026-01-15 |  | 2026-02-24 |  | 2026-04-17 |  | 2026-06-25 |  | 2026-07-15
2021-4591-66-0030-03 | ST-CGF Topsides - Deck Support Frame (DSF) Sections and Details - Sht 03 | ST | Drawing | 2026-01-15 |  | 2026-02-24 |  | 2026-04-17 |  | 2026-06-25 |  | 2026-07-15
2021-4591-66-0030-04 | ST-CGF Topsides - Deck Support Frame (DSF) Sections and Details - Sht 04 | ST | Drawing | 2026-01-15 |  | 2026-02-24 |  | 2026-04-17 |  | 2026-06-25 |  | 2026-07-15
2021-4591-66-0030-05 | ST-CGF Topsides - Deck Support Frame (DSF) Sections and Details - Sht 05 | ST | Drawing | 2026-01-15 |  | 2026-02-24 |  | 2026-04-17 |  | 2026-06-25 |  | 2026-07-15
2021-4591-66-0030-06 | ST-CGF Topsides - Deck Support Frame (DSF) Sections and Details - Sht 06 | ST | Drawing | 2026-01-15 |  | 2026-02-24 |  | 2026-04-17 |  | 2026-06-25 |  | 2026-07-15
2021-4591-66-0030-07 | ST-CGF Topsides - Deck Support Frame (DSF) Sections and Details - Sht 07 | ST | Drawing | 2026-01-15 |  | 2026-02-24 |  | 2026-04-17 |  | 2026-06-25 |  | 2026-07-15
2021-4591-66-0030-08 | ST-CGF Topsides - Deck Support Frame (DSF) Sections and Details - Sht 08 | ST | Drawing | 2026-01-15 |  | 2026-02-24 |  | 2026-04-17 |  | 2026-06-25 |  | 2026-07-15
2021-4591-66-0030-09 | ST-CGF Topsides - Deck Support Frame (DSF) Sections and Details - Sht 09 | ST | Drawing | 2026-01-15 |  | 2026-02-24 |  | 2026-04-17 |  | 2026-06-25 |  | 2026-07-15
2021-4591-66-0030-10 | ST-CGF Topsides - Deck Support Frame (DSF) Sections and Details - Sht 10 | ST | Drawing | 2026-01-15 |  | 2026-02-24 |  | 2026-04-17 |  | 2026-06-25 |  | 2026-07-15
2021-4591-63-0016-01 | ST-CGF Topsides - GTC Exhaust Support Plan, Section And Details sht 01 | ST | Drawing | 2026-03-16 |  | 2026-04-23 |  | 2026-05-28 |  |  |  | 2026-07-15
2021-4591-63-0017-01 | ST-CGF Topsides - Service Platform Support Plan, Section And Details sht 01 | ST | Drawing | 2026-03-16 |  | 2026-04-23 |  | 2026-05-16 |  |  |  | 2026-07-15
2021-4591-63-0018-01 | ST-CGF Topsides - Access Platform Support Plan, Section And Details sht 01 | ST | Drawing | 2026-03-16 |  | 2026-04-23 |  | 2026-05-16 |  |  |  | 2026-07-15
2021-4591-63-0019 | ST CGF Topsides - Pedestal Crane Diesel Storage Tank- Plan, Section And Details | ST | Drawing | 2026-01-15 |  | 2026-02-24 |  | 2026-04-17 |  |  |  | 2026-07-15
2021-4591-63-0020-01 | ST-CGF Topsides - Trimmer Beam Location Plan sht 01 | ST | Drawing | 2026-01-15 |  | 2026-03-14 |  | 2026-03-28 |  |  |  | 2026-07-15
2021-4591-63-0021-01 | ST CGF Topsides Pipe Rack - Plan, Sections And Details sht 01 | ST | Drawing | 2026-02-14 |  | 2026-03-26 |  | 2026-04-16 |  |  |  | 2026-06-15
2021-4591-63-0023-01 | ST CGF Topsides - Sub Cellar Deck Equipment Support Layout And Details sht 01 | ST | Drawing | 2026-03-30 |  | 2026-05-09 |  | 2026-05-30 |  |  |  | 2026-07-29
2021-4591-63-0023-02 | ST CGF Topsides - Sub Cellar Deck Equipment Support Layout And Details sht 02 | ST | Drawing | 2026-03-30 |  | 2026-05-09 |  | 2026-05-30 |  |  |  | 2026-07-29
2021-4591-63-0023-03 | ST CGF Topsides - Sub Cellar Deck Equipment Support Layout And Details sht 03 | ST | Drawing | 2026-03-30 |  | 2026-05-09 |  | 2026-05-30 |  |  |  | 2026-07-29
2021-4591-63-0024-01 | ST CGF Topsides - Cellar Deck Equipment Support Layout And Details sht 01 | ST | Drawing | 2026-02-28 |  | 2026-04-09 |  | 2026-05-15 |  |  |  | 2026-06-29
2021-4591-63-0024-02 | ST CGF Topsides - Cellar Deck Equipment Support Layout And Details sht 02 | ST | Drawing | 2026-02-28 |  | 2026-04-09 |  | 2026-05-15 |  |  |  | 2026-06-29
2021-4591-63-0024-03 | ST CGF Topsides - Cellar Deck Equipment Support Layout And Details sht 03 | ST | Drawing | 2026-02-28 |  | 2026-04-09 |  | 2026-05-15 |  |  |  | 2026-06-29
2021-4591-63-0024-04 | ST CGF Topsides - Cellar Deck Equipment Support Layout And Details sht 04 | ST | Drawing | 2026-02-28 |  | 2026-04-09 |  | 2026-05-15 |  |  |  | 2026-06-29
2021-4591-63-0024-05 | ST CGF Topsides - Cellar Deck Equipment Support Layout And Details sht 05 | ST | Drawing | 2026-02-28 |  | 2026-04-09 |  | 2026-05-15 |  |  |  | 2026-06-29
2021-4591-63-0024-06 | ST CGF Topsides - Cellar Deck Equipment Support Layout And Details sht 06 | ST | Drawing | 2026-02-28 |  | 2026-04-09 |  | 2026-05-15 |  |  |  | 2026-06-29
2021-4591-63-0024-07 | ST CGF Topsides - Cellar Deck Equipment Support Layout And Details sht 07 | ST | Drawing | 2026-02-28 |  | 2026-04-09 |  | 2026-05-15 |  |  |  | 2026-06-29
2021-4591-63-0024-08 | ST CGF Topsides - Cellar Deck Equipment Support Layout And Details sht 08 | ST | Drawing | 2026-02-28 |  | 2026-04-09 |  | 2026-05-15 |  |  |  | 2026-06-29
2021-4591-63-0024-09 | ST CGF Topsides - Cellar Deck Equipment Support Layout And Details sht 09 | ST | Drawing | 2026-02-28 |  | 2026-04-09 |  | 2026-05-15 |  |  |  | 2026-06-29
2021-4591-63-0024-10 | ST CGF Topsides - Cellar Deck Equipment Support Layout And Details sht 10 | ST | Drawing | 2026-02-28 |  | 2026-04-09 |  | 2026-05-15 |  |  |  | 2026-06-29
2021-4591-63-0025-01 | ST CGF Topsides - Intermediate Deck Equipment Support Layout And Details sht 01 | ST | Drawing | 2026-02-28 |  | 2026-04-02 |  | 2026-05-25 |  |  |  | 2026-07-02
2021-4591-63-0025-02 | ST CGF Topsides - Intermediate Deck Equipment Support Layout And Details sht 02 | ST | Drawing | 2026-02-28 |  | 2026-04-02 |  | 2026-05-25 |  |  |  | 2026-07-02
2021-4591-63-0025-03 | ST CGF Topsides - Intermediate Deck Equipment Support Layout And Details sht 03 | ST | Drawing | 2026-02-28 |  | 2026-04-02 |  | 2026-05-25 |  |  |  | 2026-07-02
2021-4591-63-0025-04 | ST CGF Topsides - Intermediate Deck Equipment Support Layout And Details sht 04 | ST | Drawing | 2026-02-28 |  | 2026-04-02 |  | 2026-05-25 |  |  |  | 2026-07-02
2021-4591-63-0025-05 | ST CGF Topsides - Intermediate Deck Equipment Support Layout And Details sht 05 | ST | Drawing | 2026-02-28 |  | 2026-04-02 |  | 2026-05-25 |  |  |  | 2026-07-02
2021-4591-63-0025-06 | ST CGF Topsides - Intermediate Deck Equipment Support Layout And Details sht 06 | ST | Drawing | 2026-02-28 |  | 2026-04-02 |  | 2026-05-25 |  |  |  | 2026-07-02
2021-4591-63-0026-01 | ST CGF Topsides - Main Deck Equipment Support Layout And Details sht 01 | ST | Drawing | 2026-03-30 |  | 2026-05-09 |  | 2026-05-30 |  |  |  | 2026-07-29
2021-4591-63-0026-02 | ST CGF Topsides - Main Deck Equipment Support Layout And Details sht 02 | ST | Drawing | 2026-03-30 |  | 2026-05-09 |  | 2026-05-30 |  |  |  | 2026-07-29
2021-4591-63-0026-03 | ST CGF Topsides - Main Deck Equipment Support Layout And Details sht 03 | ST | Drawing | 2026-03-30 |  | 2026-05-09 |  | 2026-05-30 |  |  |  | 2026-07-29
2021-4591-63-0026-04 | ST CGF Topsides - Main Deck Equipment Support Layout And Details sht 04 | ST | Drawing | 2026-03-30 |  | 2026-05-09 |  | 2026-05-30 |  |  |  | 2026-07-29
2021-4591-63-0026-05 | ST CGF Topsides - Main Deck Equipment Support Layout And Details sht 05 | ST | Drawing | 2026-03-30 |  | 2026-05-09 |  | 2026-05-30 |  |  |  | 2026-07-29
2021-4591-63-0027 | ST CGF Topsides - Caisson Layout and Details | ST | Drawing | 2026-03-16 |  | 2026-04-25 |  | 2026-05-28 |  |  |  | 2026-07-15
2021-4591-63-0028 | ST CGF Topsides - J-tube Layout and Details | ST | Drawing | 2026-03-16 |  | 2026-04-25 |  | 2026-05-28 |  |  |  | 2026-07-15
2021-4591-63-0029 | ST CGF Topsides - Safety Support Layout And Details | ST | Drawing | 2026-03-16 |  | 2026-05-07 |  | 2026-05-28 |  |  |  | 2026-07-15
2021-4591-63-0030 | ST CGF Topsides - Conductor Guide Details | ST | Drawing | 2026-03-16 |  | 2026-05-07 |  | 2026-05-28 |  |  |  | 2026-07-15
2021-4591-63-0031 | ST CGF Topsides - Hatch Cover Details | ST | Drawing | 2026-03-16 |  | 2026-05-07 |  | 2026-05-28 |  |  |  | 2026-07-15
2021-4991-6W-9001 | Technical Requisition for Structural steel (LQM2) | ST | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-16 | 2025-07-16 | 2025-08-28 | 2025-08-28 | 2025-12-23
2021-4991-6V-9001 | Bid Evaluation Criteria for Structural steel (LQM2) | ST | Procurement | 2025-09-13 | 2025-09-13 | 2025-09-15 | 2025-09-19 08:24 | 2025-09-15 | 2025-09-16 |  |  | 2025-09-30 | 2025-10-01
2021-4991-6W-9002 | Technical Bid Evaluation for Structural steel (LQM2) | ST | Procurement | 2025-09-05 | 2025-09-05 | 2025-09-28 |  | 2025-10-05 |  |  |  | 2025-10-19
2021-4991-6W-9003 | Technical Requisition for Grating (LQM2) | ST | Procurement | 2025-10-29 |  | 2025-11-13 |  | 2025-11-18 |  | 2025-12-11 |  | 2026-03-28
2021-4991-6V-9002 | Bid Evaluation Criteria for Grating (LQM2) | ST | Procurement | 2025-10-29 |  | 2025-11-13 |  | 2025-11-23 |  |  |  | 2025-12-08
2021-4991-6W-9004 | Technical Bid Evaluation for Grating (LQM2) | ST | Procurement | 2026-01-19 |  | 2026-02-25 |  | 2026-03-04 |  |  |  | 2026-03-18
2021-4992-6W-9001 | Technical Requisition for Architectural Items - Laundry & Dryer Equipment | ST | Procurement | 2025-11-16 |  | 2025-12-06 |  | 2025-12-06 |  | 2025-12-29 |  | 2026-04-15
2021-4992-6V-9001 | Bid Evaluation Criteria for Architectural Items - Laundry & Dryer Equipment | ST | Procurement | 2025-11-16 |  | 2025-12-11 |  | 2025-12-11 |  |  |  | 2025-12-26
2021-4992-6W-9002 | Technical Bid Evaluation for Architectural Items - Laundry & Dryer Equipment | ST | Procurement | 2026-02-06 |  | 2026-03-08 |  | 2026-03-08 |  |  |  | 2026-03-22
2021-4992-6W-9003 | Technical Requisition for Architectural Items-Insulation, deck covering, wall & ceiling panel and others (LQM2) | ST | Procurement | 2025-10-26 |  | 2025-11-10 |  | 2025-11-15 |  | 2025-12-08 |  | 2026-04-09
2021-4992-6V-9002 | Bid Evaluation Criteria for Architectural Items-Insulation, deck covering, wall & ceiling panel and others (LQM2) | ST | Procurement | 2025-10-26 |  | 2025-11-10 |  | 2025-11-20 |  |  |  | 2025-12-05
2021-4992-6W-9004 | Technical Bid Evaluation for Architectural Items-Insulation, deck covering, wall & ceiling panel and others (LQM2) | ST | Procurement | 2026-01-16 |  | 2026-02-23 |  | 2026-03-02 |  |  |  | 2026-03-16
2021-4992-6W-9005 | Technical Requisition for Architectural Items - Doors and Windows Incl. Fire Shutter | ST | Procurement | 2025-11-09 |  | 2025-11-24 |  | 2025-11-29 |  | 2025-12-22 |  | 2026-05-10
2021-4992-6V-9003 | Bid Evaluation Criteria for Architectural Items - Doors and Windows Incl. Fire Shutter | ST | Procurement | 2025-11-09 |  | 2025-11-24 |  | 2025-12-04 |  |  |  | 2025-12-19
2021-4992-6W-9006 | Technical Bid Evaluation for Architectural Items - Doors and Windows Incl. Fire Shutter | ST | Procurement | 2026-02-06 |  | 2026-03-16 |  | 2026-03-23 |  |  |  | 2026-04-06
2021-4992-6W-9007 | Technical Requisition for Architectural Items - Fixed & Loose Furniture and Miscellaneous | ST | Procurement | 2026-02-28 |  | 2026-03-15 |  | 2026-03-20 |  | 2026-04-12 |  | 2026-08-26
2021-4992-6V-9004 | Bid Evaluation Criteria for Architectural Items - Fixed & Loose Furniture and Miscellaneous | ST | Procurement | 2026-02-28 |  | 2026-03-15 |  | 2026-03-25 |  |  |  | 2026-04-09
2021-4992-6W-9008 | Technical Bid Evaluation for Architectural Items - Fixed & Loose Furniture and Miscellaneous | ST | Procurement | 2026-05-28 |  | 2026-06-20 |  | 2026-06-27 |  |  |  | 2026-07-11
2021-4992-6W-9009 | Technical Requisition for Architectural Items - Wet Units and Sanitary Fixture Incl. Cubicle Partitions | ST | Procurement | 2025-11-13 |  | 2025-12-03 |  | 2025-12-03 |  | 2025-12-26 |  | 2026-04-12
2021-4992-6V-9005 | Bid Evaluation Criteria for Architectural Items - Wet Units and Sanitary Fixture Incl. Cubicle Partitions | ST | Procurement | 2025-11-13 |  | 2025-12-08 |  | 2025-12-08 |  |  |  | 2025-12-23
2021-4992-6W-9010 | Technical Bid Evaluation for Architectural Items - Wet Units and Sanitary Fixture Incl. Cubicle Partitions | ST | Procurement | 2026-02-03 |  | 2026-03-05 |  | 2026-03-05 |  |  |  | 2026-03-19
2021-4900-1W-1001 | Technical Requisition for Piping Specialty Items (LQ) | PI | Procurement | 2025-09-05 | 2025-09-05 | 2026-01-23 |  | 2026-01-30 |  | 2026-02-27 |  | 2026-03-23
2021-4900-1W-1002 | Technical Requisition for Gaskets, insulating Gasket, Kamos Gasket (LQ) | PI | Procurement | 2025-11-18 |  | 2025-12-18 |  | 2025-12-28 |  | 2026-01-15 |  | 2026-05-03
2021-4900-1W-1003 | Technical Requisition for Bolt & Nut (LQ) | PI | Procurement | 2025-11-18 |  | 2025-12-18 |  | 2025-12-26 |  | 2026-01-20 |  | 2026-05-03
2021-4900-1W-1004 | Technical Requisition for Steel Piping Bulk (LQ & BF) | PI | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-29 | 2025-07-29 | 2025-07-29 | 2025-08-29 | 2025-09-23 | 2026-03-16
2021-4900-1W-1005 | Technical Requisition for Piping Insulation (LQ) | PI | Procurement | 2026-03-18 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-05-15 |  | 2026-09-28
2021-4900-1W-1006 | Technical Requisition for Piping Support (LQ) | PI | Procurement | 2025-07-22 | 2025-07-22 | 2025-09-03 | 2025-09-19 13:50 | 2025-09-18 | 2025-09-22 | 2025-10-17 |  | 2026-03-01
2021-4900-1W-1007 | Technical Requisition for FRP Piping (LQ) | PI | Procurement | 2025-10-05 | 2025-10-05 | 2025-11-04 | 2025-10-10 15:22 | 2025-11-07 |  |  |  | 2026-04-24
2021-4800-1W-1001 | Technical Requisition for Access Fitting (Chemical Injection Quill, Sample Connection, Corrosion Coupon, Corrosion Probe) (BF) | PI | Procurement | 2025-08-31 | 2025-08-31 | 2025-09-30 |  | 2025-10-28 |  | 2025-11-28 |  | 2026-02-27
2021-4800-1W-1002 | Technical Requisition for Mechanical Valve Interlock (BF) | PI | Procurement | 2026-02-15 |  | 2026-02-20 |  | 2026-02-26 |  | 2026-05-07 |  | 2026-08-23
2021-4800-1W-1003 | Technical Requisition for Flexible Hose and Quick Coupling (BF) | PI | Procurement | 2026-01-17 |  | 2026-02-16 |  | 2026-02-26 |  | 2026-03-16 |  | 2026-07-02
2021-4800-1W-1004 | Technical Requisition for Flame Arrestor (BF) | PI | Procurement | 2025-12-24 |  | 2025-12-29 |  | 2026-01-03 |  | 2026-03-16 |  | 2026-07-02
2021-4900-1W-2001 | Technical Bid Evaluation for Piping Specialty Items (LQ) | PI | Procurement | 2026-05-25 |  | 2026-06-08 |  | 2026-06-14 |  |  |  | 2026-06-28
2021-4900-1W-2002 | Technical Bid Evaluation for Gaskets, insulating Gasket, Kamos Gasket (LQ) | PI | Procurement | 2026-03-12 |  | 2026-03-26 |  | 2026-04-01 |  |  |  | 2026-04-15
2021-4900-1W-2003 | Technical Bid Evaluation for Bolt & Nut (LQ) | PI | Procurement | 2026-03-12 |  | 2026-03-26 |  | 2026-04-17 |  |  |  | 2026-05-01
2021-4900-1W-2004 | Technical Bid Evaluation for Steel Piping Bulk (LQ) | PI | Procurement | 2026-01-24 |  | 2026-02-07 |  | 2026-02-11 |  |  |  | 2026-03-06
2021-4900-1W-2005 | Technical Bid Evaluation for Piping Insulation (LQ) | PI | Procurement | 2026-07-10 |  | 2026-07-24 |  | 2025-12-31 |  |  |  | 2026-08-13
2021-4900-1W-2006 | Technical Bid Evaluation for Piping Support (LQ) | PI | Procurement | 2025-12-11 |  | 2025-12-25 |  | 2026-02-16 |  |  |  | 2026-01-14
2021-4900-1W-2007 | Technical Bid Evaluation for FRP Piping (LQ) | PI | Procurement | 2026-01-27 |  | 2026-02-10 |  | 2026-02-09 |  |  |  | 2026-03-02
2021-4800-1W-2001 | Technical Bid Evaluation for Access Fitting (Chemical Injection Quill, Sample Connection, Corrosion Coupon, Corrosion Probe) (BF) | PI | Procurement | 2025-11-29 |  | 2025-12-23 |  | 2026-01-08 |  |  |  | 2026-02-12
2021-4800-1W-2002 | Technical Bid Evaluation for Mechanical Valve Interlock (BF) | PI | Procurement | 2026-06-08 |  | 2026-07-02 |  | 2026-07-12 |  |  |  | 2026-07-22
2021-4800-1W-2003 | Technical Bid Evaluation for Flexible Hose and Quick Coupling (BF) | PI | Procurement | 2026-04-17 |  | 2026-05-11 |  | 2026-05-17 |  |  |  | 2026-05-31
2021-4800-1W-2004 | Technical Bid Evaluation for Flame Arrestor (BF) | PI | Procurement | 2026-04-17 |  | 2026-05-11 |  | 2026-05-19 |  |  |  | 2026-05-31
2021-5095-6H-0001 | SSIV Structural Basis of Design | PL | Report | 2025-09-05 | 2025-09-05 | 2025-10-16 | 2025-10-10 14:44 | 2025-10-24 |  | 2026-01-09 |  | 2026-02-06
2021-5095-6J-0003 | SSIV Protection Frame - Structural Analysis Report | PL | Report | 2025-10-13 | 2025-10-13 | 2025-11-27 |  | 2025-12-07 |  | 2026-02-06 |  | 2026-03-20
2021-5095-6J-0004 | SSIV Protection Frame - Structural Miscellaneous Calculation Report | PL | Report | 2025-10-18 |  | 2025-12-02 |  | 2025-12-12 |  | 2026-02-02 |  | 2026-03-20
2021-5095-6J-0005 | SSIV Protection Frame - Cathodic Protection Design Report | PL | Report | 2025-11-26 |  | 2026-01-10 |  | 2026-01-20 |  | 2026-02-13 |  | 2026-03-27
2021-5095-6L-0002 | SSIV Structure Steel Material Specification | PL | Specification | 2025-10-01 | 2025-10-01 | 2025-10-21 |  | 2025-10-31 |  | 2025-12-05 |  | 2026-01-09
2021-5095-0Q-0006 | SSIV Structure Weight Control Report | PL | Report | 2025-11-29 |  | 2026-01-13 |  | 2026-01-23 |  | 2026-03-06 |  | 2026-04-20
2021-5095-60-0001 | SSIV Structure Drawing Index | PL | Drawing | 2025-11-10 |  | 2025-12-04 |  | 2025-12-17 |  | 2026-02-09 |  | 2026-03-11
2021-5095-61-0002 | SSIV General Notes | PL | Drawing | 2025-11-10 |  | 2025-12-04 |  | 2025-12-17 |  | 2026-02-09 |  | 2026-03-11
2021-5095-63-0011 | SSIV Arrangement Drawing | PL | Drawing | 2025-11-10 |  | 2025-12-04 |  | 2025-12-17 |  | 2026-02-09 |  | 2026-03-11
2021-5095-66-0031 | SSIV Structure Frame Installation Sequence | PL | Drawing | 2025-11-10 |  | 2025-12-04 |  | 2025-12-17 |  | 2026-02-09 |  | 2026-03-11
2021-5095-63-0012 | SSIV Structure Framing Elevations and Details | PL | Drawing | 2025-11-10 |  | 2025-12-04 |  | 2025-12-17 |  | 2026-02-09 |  | 2026-03-11
2021-5095-63-0016 | SSIV - Pipe Support Detailed Drawings | PL | Drawing | 2025-11-10 |  | 2025-12-04 |  | 2025-12-17 |  | 2026-02-09 |  | 2026-03-11
2021-5095-63-0017 | SSIV-SUTU FRAME DETAILS | PL | Drawing | 2025-11-10 |  | 2025-12-04 |  | 2025-12-17 |  | 2026-02-09 |  | 2026-03-11
2021-5095-63-0013 | SSIV Structure Sacrificial Anodes Arrangement and Details | PL | Drawing | 2025-11-10 |  | 2025-12-10 |  | 2025-12-26 |  | 2026-02-15 |  | 2026-03-11
2021-5095-63-0015 | SSIV Lifting Configuration & Padeyes Detailes | PL | Drawing | 2025-11-10 |  | 2025-12-10 |  | 2025-12-26 |  | 2026-02-15 |  | 2026-03-11
2021-5095-63-0014 | SSIV Structure Grating and Marking Details | PL | Drawing | 2025-11-10 |  | 2025-12-10 |  | 2025-12-26 |  | 2026-02-15 |  | 2026-03-11
2021-5095-6U-0007 | SSIV Structure MTO | PL | Report | 2025-11-20 |  | 2025-12-19 |  | 2025-12-26 |  | 2026-02-19 |  | 2026-03-15
2021-5095-6V-0001 | Bid Evaluation Criteria for Subsea Structure Material Package | PL | Procurement | 2025-11-07 |  | 2025-12-22 |  | 2026-01-01 |  |  |  | 2026-01-25
2021-5095-6W-0001 | Technical Requisition for Subsea Structure Material Package | PL | Procurement | 2025-11-07 |  | 2025-12-22 |  | 2026-01-01 |  | 2026-01-25 |  | 2026-04-22
2021-5095-6W-0002 | Technical Bid Evaluation Report for Subsea Structure Material Package | PL | Procurement | 2026-01-12 |  | 2026-02-26 |  | 2026-03-08 |  |  |  | 2026-04-01
2021-4534-2H-0001 | Gas Export Riser System Design Basis (Riser, Tie-in Spool and Umbilical) | PL | Report | 2025-08-28 | 2025-08-28 | 2025-10-12 | 2025-10-03 08:49 | 2025-10-17 | 2025-10-10 | 2026-01-21 |  | 2026-02-20
2021-4534-2J-0001 | Gas Export Riser, Tie-in Spool, and SSIV Pipeline Wall Thickness Calculation Report | PL | Report | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-08-16 | 2025-10-10 | 2025-12-26
2021-4534-2J-0002 | Riser Free-Spanning Design Report | PL | Report | 2025-11-15 |  | 2025-12-30 |  | 2026-01-09 |  | 2026-03-31 |  | 2026-05-15
2021-4534-2J-0003 | Riser and Tie-in Spool Stress Analysis Report | PL | Report | 2025-10-10 | 2025-10-10 | 2025-11-06 |  | 2025-11-18 |  | 2026-04-15 |  | 2026-05-30
2021-4534-2J-0004 | Tie-in Spool On-bottom Stability Report | PL | Report | 2026-01-04 | 2025-10-03 17:36 | 2026-02-18 | 2025-10-03 17:36 | 2026-02-21 | 2025-10-03 | 2026-03-17 |  | 2026-05-01
2021-4534-2J-0005 | Cathodic Protection Report | PL | Report | 2025-12-28 |  | 2026-02-11 |  | 2026-02-21 |  | 2026-03-17 |  | 2026-05-01
2021-4534-2J-0006 | Pipeline Dropped Object Report | PL | Report | 2025-12-12 | 2025-09-19 09:19 | 2026-01-26 | 2025-09-19 09:19 | 2026-02-05 | 2025-09-26 | 2026-03-01 |  | 2026-04-15
2021-4534-2J-0007 | Pipe-Soil Interaction Analysis Report | PL | Report | 2025-12-17 |  | 2026-01-31 |  | 2026-02-10 |  | 2026-03-06 |  | 2026-04-20
2021-4534-2J-0008 | Preliminary Tie-In Spool Lifting Analysis Report | PL | Report | 2026-02-11 |  | 2026-03-28 |  | 2026-04-07 |  | 2026-05-01 |  | 2026-06-15
2021-4534-2L-0002 | Specification for LSAW Line Pipe | PL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-07-22 | 2025-09-26 | 2025-09-30 | 2025-10-10
2021-4534-2L-0003 | Specification for Line Pipe and Bend External Anti-Corrosion Coating | PL | Specification | 2025-10-11 | 2025-10-11 | 2025-11-25 | 2025-09-19 14:24 | 2025-11-28 | 2025-09-22 | 2026-02-23 |  | 2026-03-25
2021-4534-2L-0005 | Specification for Riser Splash Zone Coating | PL | Specification | 2025-07-29 | 2025-07-29 | 2025-09-18 | 2025-10-03 07:21 | 2025-09-22 | 2025-10-14 | 2025-10-09 |  | 2025-11-11
2021-4534-2L-0006 | Specification for Hot Induction Bends | PL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-08-12 | 2025-09-26 | 2025-09-30 | 2025-10-10
2021-4534-2L-0007 | Specification for Flange and Fittings | PL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-03 | 2025-07-02 | 2025-08-14 | 2025-10-03 | 2025-10-10
2021-4534-2L-0008 | Specification for SSIV Subsea Valve | PL | Specification | 2025-06-28 | 2025-06-28 | 2025-08-09 | 2025-08-16 15:31 | 2025-08-16 | 2025-08-16 | 2025-09-20 | 2025-10-01 | 2025-11-03 | 2025-10-01
2021-4534-2L-0001 | Specification for Riser, Tie-in Spool, and SSIV Welding | PL | Specification | 2025-12-13 |  | 2026-01-13 |  | 2026-01-23 |  | 2026-03-06 |  | 2026-04-10
2021-4534-2L-0009 | Specification for Seamless Line Pipe | PL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-07-22 | 2025-09-26 | 2025-09-30 | 2025-10-10
2021-4534-2L-0010 | Specification for Concrete Mattress | PL | Specification | 2025-07-23 | 2025-07-23 | 2025-09-06 | 2025-09-06 14:18 | 2025-09-09 | 2025-09-06 | 2025-09-21 | 2025-10-10 | 2025-10-05
2021-4534-2L-0011 | Specification for Concrete Weight Coating | PL | Specification | 2025-07-29 | 2025-07-29 | 2025-09-19 | 2025-09-17 14:19 | 2025-09-23 | 2025-09-17 | 2025-10-09 | 2025-10-10 | 2025-11-08
2021-4534-2L-0012 | Specification for Anodes | PL | Specification | 2025-07-29 | 2025-07-29 | 2025-09-18 | 2025-10-03 17:36 | 2025-09-22 | 2025-10-03 | 2025-10-16 |  | 2025-11-15
2021-4534-2L-0013 | Specification for Field Joint Coating | PL | Specification | 2025-08-11 | 2025-08-11 | 2025-09-25 | 2025-10-03 15:24 | 2025-10-05 |  | 2025-10-29 |  | 2025-12-13
2021-4534-2L-0014 | Specification for Tie-in Spool, Pre-Installed Riser Preservation | PL | Specification | 2026-01-16 |  | 2026-02-15 |  | 2026-02-25 |  | 2026-03-21 |  | 2026-05-05
2021-4506-4L-0010 | Specification for Umbilical | PL | Specification | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-07-31 | 2025-07-31 | 2025-11-16 | 2025-10-03
2021-4534-2M-0001 | Datasheet for LSAW Line Pipe | PL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-08-12 | 2025-09-26 | 2025-09-30 | 2025-10-10
2021-4534-2M-0002 | Datasheet for Hot Induction Bends | PL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-08-12 | 2025-09-26 | 2025-09-30 | 2025-10-10
2021-4534-2M-0003 | Datasheet for Flange and Fittings | PL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-08-14 | 2025-10-03 | 2025-10-10
2021-4534-2M-0005 | Datasheet for Seamless Line pipe | PL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-07-24 | 2025-09-26 | 2025-09-30 | 2025-10-10
2021-4534-2M-0007 | Datasheet for Concrete Mattress | PL | Datasheet | 2025-07-23 | 2025-07-23 | 2025-09-06 | 2025-09-06 14:18 | 2025-09-09 | 2025-09-06 | 2025-09-21 | 2025-10-10 | 2025-10-05
2021-4534-2M-0008 | Datasheet for Concrete Weight Coating | PL | Datasheet | 2025-07-29 | 2025-07-29 | 2025-09-17 | 2025-09-17 14:19 | 2025-09-22 | 2025-09-17 | 2025-10-09 | 2025-10-10 | 2025-11-08
2021-4534-2M-0009 | Datasheet for Anodes | PL | Datasheet | 2025-07-29 | 2025-07-29 | 2025-09-18 |  | 2025-09-22 |  | 2025-10-16 |  | 2025-11-15
2021-4534-2M-0010 | Datasheet for Line Pipe and Bend External Anti-Corrosion Coating | PL | Datasheet | 2025-10-11 | 2025-10-11 | 2025-11-25 |  | 2025-11-28 |  | 2026-02-23 |  | 2026-03-25
2021-4534-2M-0011 | Datasheet for Riser Splash Zone Coating | PL | Datasheet | 2025-07-29 | 2025-07-29 | 2025-09-18 |  | 2025-09-22 |  | 2025-10-09 |  | 2025-11-11
2021-4506-4M-0015 | Datasheet for SSIV | PL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-08-09 | 2025-08-16 18:04 | 2025-08-16 | 2025-08-16 | 2025-09-20 | 2025-10-01 | 2025-11-03 | 2025-10-01
2021-4534-2M-0013 | Datasheet for Field Joint Coating | PL | Datasheet | 2025-08-11 | 2025-08-11 | 2025-09-25 |  | 2025-10-05 |  | 2025-10-29 |  | 2025-12-13
2021-4534-2M-0014 | Datasheet for Umbilical | PL | Datasheet | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-07-31 | 2025-07-31 | 2025-11-16
2021-4534-2U-0001 | Pipeline Material Take-Off | PL | Report | 2025-09-06 | 2025-09-06 | 2025-10-21 |  | 2025-10-31 |  | 2026-02-09 |  | 2026-03-20
2021-4534-20-0001 | General Notes and Drawing Index | PL | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-07 | 2025-08-14 14:19 | 2025-08-14 | 2025-08-14 | 2026-01-10 |  | 2026-04-29
2021-4534-21-0001 | Pipeline Approach at ST-CGF - Gas Export Riser System | PL | Drawing | 2026-01-10 |  | 2026-02-24 |  | 2026-03-06 |  | 2026-03-30 |  | 2026-04-29
2021-4534-21-0002 | Riser Tie-in Spool General Arrangement Drawing - Gas Export Riser System | PL | Drawing | 2026-01-10 |  | 2026-02-24 |  | 2026-03-06 |  | 2026-03-30 |  | 2026-04-29
2021-4534-21-0004 | Riser General Arrangement Drawing - 16" Gas Export Riser System | PL | Drawing | 2026-01-06 |  | 2026-02-20 |  | 2026-03-06 |  | 2026-03-30 |  | 2026-04-29
2021-4533-24-0005 | Subsea Isolation Valve General Arrangement Drawing | PL | Drawing | 2026-01-06 |  | 2026-02-20 |  | 2026-03-06 |  | 2026-03-30 |  | 2026-04-29
2021-4533-24-0006 | General Arrangement Drawing for Pre-installed 12" Future Riser | PL | Drawing | 2026-01-06 |  | 2026-02-20 |  | 2026-03-06 |  | 2026-03-30 |  | 2026-04-29
2021-4533-24-0013 | General Arrangement Drawing for Pre-installed 10" Future Riser | PL | Drawing | 2026-01-10 |  | 2026-02-24 |  | 2026-03-06 |  | 2026-03-30 |  | 2026-04-29
2021-4533-24-0007 | Isometric for 16" Gas Export Riser | PL | Drawing | 2026-02-10 |  | 2026-03-12 |  | 2026-03-22 |  | 2026-04-15 |  | 2026-05-15
2021-4533-24-0008 | Isometric for 16" Gas Export Tie-in Spools | PL | Drawing | 2026-02-18 |  | 2026-03-20 |  | 2026-03-22 |  | 2026-04-15 |  | 2026-05-15
2021-4533-24-0009 | Isometric for 16" SSIV | PL | Drawing | 2026-02-18 |  | 2026-03-20 |  | 2026-03-22 |  | 2026-04-15 |  | 2026-05-15
2021-4533-24-0010 | Isometric for Pre-installed 12" Future Riser | PL | Drawing | 2026-02-18 |  | 2026-03-20 |  | 2026-03-22 |  | 2026-04-15 |  | 2026-05-15
2021-4533-24-0014 | Isometric for Pre-installed 10" Future Riser | PL | Drawing | 2026-02-18 |  | 2026-03-20 |  | 2026-03-22 |  | 2026-04-15 |  | 2026-05-15
2021-4533-26-0001 | Pipeline FJC Drawing | PL | Drawing | 2026-02-25 |  | 2026-03-27 |  | 2026-04-06 |  | 2026-04-30 |  | 2026-05-30
2021-4533-26-0003 | Pipeline Flange Protector Drawing | PL | Drawing | 2026-02-25 |  | 2026-03-27 |  | 2026-04-06 |  | 2026-04-30 |  | 2026-05-30
2021-4534-2W-0001 | Technical Requisition for Line Pipe and Bend | PL | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-07-24 | 2025-10-01 | 2025-10-30
2021-4534-2W-0003 | Bid Evaluation Criteria for Line Pipe and Bend | PL | Bid | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 |  |  | 2025-07-24 | 2025-10-01
2021-4534-2W-0002 | Technical Requisition for External Coating and Anodes | PL | Procurement | 2026-01-12 |  | 2026-02-26 |  | 2026-03-08 |  | 2026-04-01 |  | 2026-07-20
2021-4534-2V-0004 | Bid Evaluation Criteria for Coating and Anodes | PL | Bid | 2025-08-09 | 2025-08-09 | 2025-09-23 |  | 2025-10-03 |  |  |  | 2025-10-27
2021-4534-2W-0015 | Technical Requisition for Field Joint Coating | PL | Procurement | 2026-01-12 |  | 2026-02-26 |  | 2026-03-08 |  | 2026-04-01 |  | 2026-07-20
2021-4534-2V-0016 | Bid Evaluation Criteria for Field Joint Coating | PL | Bid | 2025-08-26 | 2025-08-26 | 2025-10-10 |  | 2025-10-20 |  |  |  | 2025-11-13
2021-4506-4W-1012 | Technical Requisition for SSIV Valve | PL | Procurement | 2025-06-28 | 2025-06-28 | 2025-08-09 | 2025-08-16 18:04 | 2025-08-16 | 2025-08-16 | 2025-09-22 | 2025-10-01 | 2026-01-09
2021-4506-4V-0012 | Bid Evaluation Criteria for SSIV | PL | Bid | 2025-06-30 | 2025-06-30 | 2025-08-14 | 2025-08-21 11:35 | 2025-08-21 | 2025-08-21 |  |  | 2025-09-20 | 2025-10-01
2021-4506-4W-1011 | Technical Requisition for Umbilical | PL | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-07-31 | 2025-07-31 | 2026-01-12
2021-4534-2W-0012 | Technical Requisition for Bolts, Nuts and Gaskets | PL | Procurement | 2025-10-16 | 2025-10-16 | 2025-10-31 | 2025-09-19 15:02 | 2025-11-10 | 2025-10-02 | 2025-11-24 |  | 2026-02-25
2021-4534-2V-0013 | Bid Evaluation Criteria for Bolts, Nuts and Gaskets | PL | Bid | 2025-07-30 | 2025-07-30 | 2025-09-13 | 2025-09-19 15:03 | 2025-09-23 | 2025-10-02 |  |  | 2025-10-17
2021-4534-2W-0006 | Technical Requisition for Flange and Fittings | PL | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 | 2025-07-21 | 2025-10-10 | 2025-12-20
2021-4534-2V-0005 | Bid Evaluation Criteria for Flange and Fittings | PL | Bid | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-07-02 |  |  | 2025-07-21 | 2025-07-21
2021-4534-2W-0010 | Technical Bid Evaluation for Line Pipe and Bend | PL | Procurement | 2025-07-27 | 2025-07-27 | 2025-09-17 |  | 2025-09-19 |  |  |  | 2025-09-27
2021-4534-2W-0014 | Technical Bid Evaluation Report for Line Pipe Coating, Bend Coating and Anode | PL | Procurement | 2026-04-23 |  | 2026-06-03 |  | 2026-06-06 |  |  |  | 2026-06-20
2021-4534-2W-0019 | Technical Bid Evaluation for Riser Flange and Fittings | PL | Procurement | 2025-09-12 | 2025-09-12 | 2025-10-27 |  | 2025-11-06 |  |  |  | 2025-11-20
2021-4534-2W-0020 | Technical Bid Evaluation for Field Joint Coating | PL | Procurement | 2025-11-25 |  | 2026-01-09 |  | 2026-01-19 |  |  |  | 2026-02-12
2021-4506-4W-1112 | Technical Bid Evaluation for SSIV | PL | Procurement | 2025-10-31 |  | 2025-11-28 |  | 2025-12-12 |  |  |  | 2026-01-02
2021-4506-4W-1111 | Technical Bid Evaluation for Umbilical | PL | Procurement | 2025-09-16 | 2025-09-16 | 2025-10-31 |  | 2025-11-06 |  |  |  | 2025-11-17
2021-4534-2W-0024 | Technical Bid Evaluation for Bolts, Nuts and Gaskets | PL | Procurement | 2025-10-20 |  | 2025-12-04 |  | 2025-12-14 |  |  |  | 2025-12-28
2021-4506-4V-0011 | Bid Evaluation Criteria for Umbilicals | PL | Bid | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-07-02 | 2025-05-28 |  |  | 2025-08-08 | 2025-08-08
2021-4500-1K-5001 | Material Selection and Corrosion Study Report | MAT | Report | 2025-08-10 | 2025-08-10 | 2025-08-19 | 2025-08-26 17:54 | 2025-08-26 | 2025-08-26 | 2026-02-18 |  | 2026-08-05
2021-4500-1L-5009 | Equipment Cathodic Protection Specification | MAT | Specification | 2025-09-06 | 2025-09-06 | 2025-09-12 | 2025-09-06 | 2025-09-20 | 2025-10-09 | 2025-10-30 |  | 2026-03-20
2021-4526-01-0209 | Piping and Instrumentation Diagram Gas Compressor Discharge Cooler A | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-16 | 2025-08-23 09:58 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4526-01-0210 | Piping and Instrumentation Diagram Gas Compressor Discharge Cooler B | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-16 | 2025-08-23 09:58 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4528-01-0201-02 | Piping and Instrumentation Diagram Production Wellheads QAY-2883 | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-16 | 2025-08-23 11:23 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4528-01-0201-03 | Piping and Instrumentation Diagram Production Wellheads QAY-2884 | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-16 | 2025-08-23 11:23 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4528-01-0201-04 | Piping and Instrumentation Diagram Production Wellheads QAY-2874 | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-16 | 2025-08-23 11:23 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4528-01-0201-05 | Piping and Instrumentation Diagram Production Wellheads QAY-2875 | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-16 | 2025-08-23 11:23 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4528-01-0201-06 | Piping and Instrumentation Diagram Production Wellheads QAY-2885 | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-16 | 2025-08-23 11:23 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4528-01-0201-07 | Piping and Instrumentation Diagram Production Wellheads QAY-2886 | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-16 | 2025-08-23 11:23 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4528-01-0201-08 | Piping and Instrumentation Diagram Production Wellheads QAY-2878 | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-16 | 2025-08-23 11:23 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4528-01-0201-09 | Piping and Instrumentation Diagram Production Wellheads QAY-2879 | PR | Drawing | 2025-06-28 | 2025-06-28 | 2025-08-16 | 2025-08-23 11:23 | 2025-08-23 | 2025-08-23 | 2026-01-10 |  | 2026-05-12
2021-4881-5W-0001 | Technical Requisition for Fire Fighting Equipment (BF) | TS | Procurement | 2025-12-05 |  | 2025-12-19 |  | 2025-12-29 |  | 2026-01-28 |  | 2026-06-07
2021-4885-5W-0001 | Technical Requisition for Life Saving Equipment (BF) | TS | Procurement | 2025-12-05 |  | 2025-12-19 |  | 2025-12-29 |  | 2026-01-28 |  | 2026-06-07
2021-4885-5W-0002 | Technical Requisition for Safety Sign Equipment (BF) | TS | Procurement | 2026-02-13 |  | 2026-02-27 |  | 2026-03-09 |  | 2026-04-08 |  | 2026-08-16
2021-4868-1V-9021 | Bid Evaluation Criteria For HVACR Package (BF) | ME | Bid | 2025-11-15 |  | 2025-12-15 |  | 2025-12-30 |  |  |  | 2026-01-30
2021-4868-1W-9020 | Technical Requistion For HVACR Package (BF) | ME | Procurement | 2025-12-01 |  | 2025-12-31 |  | 2026-01-15 |  | 2026-01-30 |  | 2026-05-18
2021-4868-1W-9060 | Technical Bid Evaluation for For HVACR Package (BF) | ME | Procurement | 2026-03-15 |  | 2026-03-29 |  | 2026-04-05 |  | 2026-04-13 |  | 2026-04-20
2021-4568-1V-9041 | Bid Evaluation Criteria For Walk-in Chiller & Freezer Units for LQM2 | ME | Bid | 2025-10-06 | 2025-10-06 | 2025-10-13 |  | 2025-10-20 |  |  |  | 2025-11-10
2021-4568-1W-9040 | Technical Requistion For Walk-in Chiller & Freezer Units for LQM2 | ME | Procurement | 2025-10-13 | 2025-10-13 | 2025-10-20 |  | 2025-10-27 |  | 2025-11-10 |  | 2026-03-31
2021-4568-1W-9070 | Technical Bid Evaluation for Walk-in Chiller & Freezer Units for LQM2 | ME | Procurement | 2026-01-07 |  | 2026-01-21 |  | 2026-01-28 |  | 2026-02-05 |  | 2026-02-12
2021-4975-3W-0002 | Technical Requisition for Lighting Fixtures (LQM2) | EL | Procurement | 2026-01-07 |  | 2026-01-14 |  | 2026-01-19 |  | 2026-02-02 |  | 2026-04-12
2021-4969-3W-0001 | Technical Requisition for E&I Cables (LQM2) | EL | Procurement | 2026-01-07 |  | 2026-01-14 |  | 2026-01-19 |  | 2026-02-02 |  | 2026-04-12
2021-4969-3W-0003 | Technical Requisition for E&I Cable Glands (LQM2) | EL | Procurement | 2026-02-16 |  | 2026-02-23 |  | 2026-02-28 |  | 2026-03-14 |  | 2026-04-12
2021-4969-3W-0004 | Technical Requisition for E&I Cable Tray, Ladder & Accessories (LQM2) | EL | Procurement | 2026-02-01 |  | 2026-02-08 |  | 2026-02-13 |  | 2026-02-27 |  | 2026-04-20
2021-4975-3W-0003 | Technical Requisition for E&I JB, Socket Outlet & RCU (LQM2) | EL | Procurement | 2026-01-07 |  | 2026-01-14 |  | 2026-01-19 |  | 2026-02-02 |  | 2026-04-20
2021-4969-3W-0005 | Technical Requisition for E&I Earthing Material (LQM2) | EL | Procurement | 2025-10-31 |  | 2025-11-07 |  | 2025-11-12 |  | 2025-11-26 |  | 2026-04-05
2021-4969-3W-0007 | Technical Requisition for E&I Steel Support (LQM2) | EL | Procurement | 2026-02-01 |  | 2026-02-08 |  | 2026-02-13 |  | 2026-02-27 |  | 2026-04-05
2021-4969-3W-0008 | Technical Requisition for E&I Miscellaneous (LQM2) | EL | Procurement | 2026-01-26 |  | 2026-02-02 |  | 2026-02-07 |  | 2026-02-21 |  | 2026-04-05
2021-4969-3W-0009 | Technical Requisition for E&I MCT (LQM2) | EL | Procurement | 2025-10-27 |  | 2025-11-03 |  | 2025-11-08 |  | 2025-11-22 |  | 2026-04-05
2021-4904-4W-9001 | Technical Requisition for Fire & Gas Detection Equipment (LQM2) | IN | Procurement | 2025-11-28 |  | 2025-12-30 |  | 2026-01-09 |  | 2026-02-21 |  | 2026-04-05
2021-4906-4W-1002 | Technical Requisition for Control Valves & Regulators (LQM2) | IN | Procurement | 2025-11-28 |  | 2025-12-30 |  | 2026-01-09 |  | 2026-02-06 |  | 2026-04-20
2021-4906-4W-9006 | Technical Requisition for Orifice Plates, Flange & Restriction Orifice Plates (LQM2) | IN | Procurement | 2025-11-28 |  | 2025-12-30 |  | 2026-01-09 |  | 2026-02-06 |  | 2026-04-20
2021-4906-4W-9016 | Technical Requisition For Electronic Transmitters (LQM2) | IN | Procurement | 2025-11-28 |  | 2025-12-30 |  | 2026-01-09 |  | 2026-02-06 |  | 2026-04-20
2021-4906-4W-9018 | Technical Requisition For Tubing, Fitting & Valves (LQM2) | IN | Procurement | 2025-11-28 |  | 2025-12-30 |  | 2026-01-09 |  | 2026-02-06 |  | 2026-04-20
2021-4891-6W-9005 | Technical Requisition for Structural steel (BF) | ST | Procurement | 2026-02-01 |  | 2026-02-01 |  | 2026-02-15 |  | 2026-03-01 |  | 2026-06-14
2021-4891-6V-9003 | Bid Evaluation Criteria for Structural steel (BF) | ST | Procurement | 2026-02-01 |  | 2026-02-01 |  | 2026-02-15 |  |  |  | 2026-03-08
2021-4891-6W-9006 | Technical Bid Evaluation for Structural steel (BF) | ST | Procurement | 2026-01-08 |  | 2026-01-31 |  | 2026-02-07 |  |  |  | 2026-03-07
2021-4891-6W-9007 | Technical Requisition for Grating (BF) | ST | Procurement | 2026-01-13 |  | 2026-01-28 |  | 2026-02-02 |  | 2026-02-25 |  | 2026-06-12
2021-4891-6V-9004 | Bid Evaluation Criteria for Grating (BF) | ST | Procurement | 2026-01-13 |  | 2026-01-28 |  | 2026-02-07 |  |  |  | 2026-02-22
2021-4891-6W-9008 | Technical Bid Evaluation for Grating (BF) | ST | Procurement | 2026-04-05 |  | 2026-04-14 |  | 2026-04-21 |  |  |  | 2026-06-02
2021-4992-6W-9011 | Technical Requisition for Architectural Items-Insulation, deck covering, wall & ceiling panel and others (BF) | ST | Procurement | 2026-04-15 |  | 2026-04-30 |  | 2026-05-05 |  | 2026-05-28 |  | 2026-04-09
2021-4992-6V-9006 | Bid Evaluation Criteria for Architectural Items-Insulation, deck covering, wall & ceiling panel and others (BF) | ST | Procurement | 2026-04-15 |  | 2026-04-30 |  | 2026-05-10 |  |  |  | 2025-12-05
2021-4992-6W-9012 | Technical Bid Evaluation for Architectural Items-Insulation, deck covering, wall & ceiling panel and others (BF) | ST | Procurement | 2026-07-06 |  | 2026-08-13 |  | 2026-08-20 |  |  |  | 2026-03-16
2021-4800-1W-1005 | Technical Requisition for Piping Insulation (BF) | PI | Procurement | 2026-02-18 |  | 2026-03-20 |  | 2026-03-27 |  | 2026-04-17 |  | 2026-04-17
2021-4800-1W-1006 | Technical Requisition for Piping Support (BF) | PI | Procurement | 2025-07-22 | 2025-07-22 | 2025-09-03 | 2025-10-03 | 2025-09-18 | 2025-10-10 | 2025-10-17 | 2025-10-10 | 2025-10-17
2021-4800-1W-1007 | Technical Requisition for FRP Piping (BF) | PI | Procurement | 2025-09-07 | 2025-09-07 | 2025-10-07 | 2025-10-07 | 2025-10-10 | 2025-10-14 | 2025-11-04 |  | 2026-02-27
2021-4800-1W-1008 | Technical Requisition for Gaskets, insulating Gasket, Kamos Gasket (BF) | PI | Procurement | 2025-10-21 |  | 2025-11-20 |  | 2025-11-30 |  | 2025-12-18 |  | 2026-04-05
2021-4800-1W-1009 | Technical Requisition for Bolt & Nut (BF) | PI | Procurement | 2025-10-21 |  | 2025-11-20 |  | 2025-11-30 |  | 2025-12-23 |  | 2026-04-05
2021-4800-1W-1010 | Technical Requisition for Steel Piping Bulk (BF) | PI | Procurement | 2025-06-28 | 2025-06-28 | 2025-06-29 |  | 2025-07-29 |  | 2025-08-29 |  | 2026-01-16
2021-4800-1W-2005 | Technical Bid Evaluation for Piping Insulation (BF) | PI | Procurement | 2026-05-19 |  | 2026-06-12 |  | 2026-06-19 |  |  |  | 2026-07-10
2021-4800-1W-2006 | Technical Bid Evaluation for Piping Support (BF) | PI | Procurement | 2025-10-20 |  | 2025-11-13 |  | 2026-01-05 |  |  |  | 2026-02-13
2021-4800-1W-2007 | Technical Bid Evaluation for FRP Piping (BF) | PI | Procurement | 2025-12-06 |  | 2025-12-30 |  | 2025-12-29 |  |  |  | 2026-01-19
2021-4800-1W-2008 | Technical Bid Evaluation for Gaskets, insulating Gasket, Kamos Gasket (BF) | PI | Procurement | 2026-01-19 |  | 2026-02-12 |  | 2026-02-18 |  |  |  | 2026-03-04
2021-4800-1W-2009 | Technical Bid Evaluation for Bolt & Nut (BF) | PI | Procurement | 2026-01-19 |  | 2026-02-12 |  | 2026-03-06 |  |  |  | 2026-03-20
2021-4800-1W-2010 | Technical Bid Evaluation for Steel Piping Bulk (BF) | PI | Procurement | 2025-11-20 |  | 2025-12-27 |  | 2025-12-31 |  |  |  | 2026-01-23
00:00:00